## Pre-Dev Final
Pre-Development Activities | Duration (Days)
Perform Business Analysis
• Business Analysis Group 1 Observation and Meetings | 3
• Business Analysis Group 2 Observation and Meetings | 3
• Business Analysis Group 3 Observation and Meetings | 2
• Business Analysis Group 4 Observation and Meetings | 2
• Business Analysis Group 5 Observation and Meetings | 1.5
• Business Analysis Checkin Meeting | 1
• Business Analysis Wrapup Meeting | 2
Investigate Stakeholder Requirements
o Management and Reporting - Conduct application design workshop #1 | 2
o Sales - Conduct application design workshop | 1
o Marketing and Development - Conduct application design workshop | 1
o Manufacturing - Conduct application design workshop | 0.5
o Customer and Vendor Relations - Conduct application design workshop | 1
o Purchasing and Inventory Management - Conduct application design workshop | 1.5
o Accounting - Conduct application design workshop | 1.5
o Management and Reporting - Conduct application design workshop #2 | 2
o System Administration - Conduct application design workshop | 1
o Analyze system user requirements gathered from application design workshops | 3
Perform feasibility study:
- Analyze the system configuration requirements for scale and interoperability/portability. | 3
- Perform a technology trawl to identify hardware and software required to deliver the system | 3
- Research and identify services that we might contract with to perform currency tracking | 3
- Research and identify services that we might contract with to perform fax-to-email | 2
- Research and identify RFID and barcode labeling requirements and suppliers | 3
Project planning:
- Revisit system requirements, integrating input from the stakeholder analysis and the feasibility study | 4
- Discuss and agree upon plan scope with key stakeholders | 3
- Rearrange interim deliverables, to reflect what we've learned | 1
- Revise the project plan, resource plan, effort, time and budget estimates and project schedule | 5
- Review and agree estimate and timescale changes with upper management | 5
- Revise project plans to accommodate any revisions to scope | 0.5

## Phase 1 Final
Pre-Development Activities | Duration (Days)
Phase 1: Develop Basic Integrated Business Management System
Phase 1 Kickoff Meeting | 2
Develop Initial System Management Subsystem
DBMS: Install & Configure DBMS Engine & SQL Interface
· Install & Configure DBMS engine | 8
· Install and test SQL interface software | 2
· Installing hardware server | 4
· Test Network connections | 8
· Evaluate the system | 2
DBMS: User Accounts and Permissions
· Design database | 8
· Implement and test database structure | 2
· Test accounts | 3
Server App: System management and security application
· Software requirements analysis | 6
· Software design | 8
· Development & coding
· Module documentation and acceptance test | 4
Client App: System management application
· Software requirements analysis | 6
· Software design & code | 8
· Module documentation and acceptance test | 9
Integrated User Interface: Provide integrated GUI to implement basic access stubs for all client apps. In Phase 1
· User navigation requirements analysis | 10
· UI design & scripting | 12
· UI documentation and acceptance test | 12
Subsystem/component integration test & documentation | 12
Develop Order Processing & Invoicing subsystem
DBMS: Orders & Invoicing Database – Full implementation
· Design database | 2
· Implement and test database structures | 2
Server App: Billing/Invoicing
· Software requirements analysis | 10
· Software design & code | 4
· Module documentation and acceptance test | 4
Client App: Sales
· Software requirements analysis | 4
· Software design & code | 8
· Module documentation and acceptance test | 3
Subsystem/component integration test & documentation | 12
Develop Billing/Accounting subsystem
DBMS: Budgeting and Accounting
· Design database | 12
· Implement and test database structures | 3
Server App: Billing/Invoicing
· Software requirements analysis | 3
· Software design & code | 8
· Unit test | 3
· Module documentation and acceptance test | 5
Client App: Accounting
· Software requirements analysis | 10
· Software design & code | 8
· Module documentation and acceptance test | 8
Develop Inventory management subsystem
DBMS: Resources & Inventory Database
· Design database | 12
· Implement and test database structures | 3
Server App: Purchasing & Inventory Management
· Software requirements analysis | 3
· Software design & code | 8
· Module documentation and acceptance test | 3
Subsystem/component integration test & documentation | 12
Client App: Inventory Management
· Software requirements analysis | 8
· Software design & code | 10
· Module documentation and acceptance test | 8
Develop System Management Subsystem (advanced functions)
DBMS: Logging & Audit Trail for Phase I functions.
· Design database | 14
· Implement and test database structures | 12
GUI & front-end menu implementation
Client App: Integrated user-navigation/access
· Software requirements analysis | 14
· Requirment gathering
· Requirment analysis phase
· Software design & code | 10
· Module documentation and acceptance test | 12
Subsystem/component integration test & documentation | 12
Client App: Provide advanced GUI to implement user menus and login form for UI client app.
· User navigation requirements analysis | 10
· UI design & scripting | 8
GUI unit tests | 9
· UI documentation and acceptance test | 7
Phase I Delivery Activities
Phase I Integration Test
· Integration test of Phase I software components | 10
· Redesign and rework following integration tests | 9
· Phase I software documentation and acceptance test | 6
Phase I Change management
· Training on new work procedures | 1
· Business process changes | 4
· User system training | 2
New process & systems evaluation
· Phase I systems installation | 8
· Phase I Testing | 7
· Phase I System Documentation | 6
· Phase I User evaluation | 2
· Evaluate the feedback | 1
Project Review
· Project plan review for Phase I | 1
· Management approval and signoff for Phase I | 4

## Phase 2 Final
Phase 2 Activities | Duration (Days)
Phase 2 Kickoff Meeting | 2
Phase 1 follow up
Review Phase I software components | 5
Review Phase I hardware components | 5
Upgrade the software requirements | 10
Upgrade System Management Subsystem (Basic)
Server App: Upgraded system management and security management
- Software requirements analysis
-Requirements Scope | 2
-Stakeholder Identification | 2
-Requirements Elicitation and Analysis | 5
-Software requirement specification and Management | 5
- Software design | 5
- Software code | 5
- Module documentation and acceptance test | 12
Client App: System management and security integration
- Software requirements analysis
-Requirements Scope | 2
-Stakeholder Identification | 2
-Requirements Elicitation and Analysis | 5
-Software requirement specification and Management | 5
- Software design | 5
- Software code | 5
Develop Operations Management & Reporting subsystem
DBMS: Sales and Market
- Design database by creating tables, developing packages and integrating with the server application | 10
- Implement and test database structures | 11
- Gather information regarding previous sales and market demands. | 5
Server App: Sales Analysis and Reporting
- Software requirements analysis | 5
- Software design & code | 4
- Write a program to display the analysis using charts and graphs for easy understanding. | 1
- Module documentation and acceptance test | 2
Client App: Management and Reporting
- Software requirements analysis | 5
- Software design & code
- Develop a user friendly UI that shows the graph and charts of sales against time duration and scale. | 1
- Application used to report | 2
- Develop the GUI | 1
- Unit testing of GUI | 1
- Module documentation and acceptance test | 2
Develop Forecasting and Analysis subsystem
DBMS: Update Sales and Market Database – add forecasting & analysis table
#NAME? | 2
- Implement and test database structures | 2
Server App: Demand Forecasting
- Software requirements analysis
-Requirements Scope | 2
-Stakeholder Identification | 2
-Requirements Elicitation and Analysis | 5
-Software requirement specification and Management | 5
- Software design | 5
- Software code | 5
- Software design & code | 2
- Develop UI to view the forecasted demand value | 1
- Module documentation and acceptance test | 2
Develop Product code database and Lookup subsystem
DBMS: Product Management (only product code-related tables)
- Design database by creating tables, developing packages and integrating with the server application | 8
- Implement and test database structures | 4
Server App: Marketing and Development (functions related to product code)
- Software requirements analysis | 3
- Software design & code | 2
- Module documentation and acceptance test | 2
Client App: Marketing and Development Application (functions related to product code)
- Software requirements analysis | 3
- Software design & code | 4
- Module documentation and acceptance test | 2
Service: Product code lookup service
- Software requirements analysis | 3
- Software design & code | 2
- Integration testing | 2
- Documentation and acceptance test | 3
Develop Currency prediction and Conversion subsystem
Server App: API to Vendor currency database
- Software requirements analysis | 3
- Software design & code | 2
- Module documentation and acceptance test | 2
Upgrade System Management Subsystem (advanced functions)
DBMS: Logging & Audit Trail for Phase II functions.
- Design database by creating tables, developing packages and integrating with the server application | 4
- Implement and test database structures | 2
DBMS: Permissions for Phase II functions.
- Update database | 1
- Implement and test database structures | 1
Server App: Upgraded system management and security application for Phase II functions
- Software requirements analysis | 2
- Software design & code | 1
- Module documentation and acceptance test | 1
Client App: user-navigation/access and reporting for Phase II Enhancements
- Software requirements analysis | 1
- Software design & code | 1
- Module documentation and acceptance test | 1
Client app: Provide advanced GUI to implement user menus and login form for UI client app. (Phase II)
- User navigation requirements analysis | 1
- UI design & scripting | 1
- UI documentation and acceptance test | 1
Develop Inventory management subsystem
DBMS: Resources & Inventory Database
- Design database by creating tables and integrating with the server application | 10
- Implement and test database structures | 4
Server App: Purchasing & Inventory Management
- Software requirements analysis | 2
- Software design & code | 3
- Module documentation and acceptance test | 2
Client App: Inventory Management
- Software requirements analysis | 2
- Software design & code | 2
- Module documentation and acceptance test | 1
Phase II Delivery Activities
Integrate all the software components developed.
Phase II Integration Test
- Integration test of Phase II software components | 8
- Redesign and rework following integration tests | 10
- Phase I software documentation and acceptance test | 8
Phase II change management
- Business process changes | 1
- Training in new work procedures | 1
- User system training | 1
New process & systems evaluation
- Phase II systems installation | 8
- Phase II pilot study | 8
- Phase II user evaluation | 2
- Evaluation feedback and client review | 2
Project Review (Stagegate)
- Stagegate (project plan) review for Phase II | 2
- Agreement of client issues to be remedied in Phase II | 4
- Client approval and signoff for Phase II | 4

## Phase 3 Final
Phase 3 Activities | Duration (Days)
Phase III Kickoff Meeting | 2
Follow up on Phase II activities
· Review lessons learned from Phase 2 prototype and user evaluation | 8
· Review software and hardware requirements | 10
· Agree on changes to be made and assign tasks | 8
Upgrade System Management Subsystem (Basic)
Server App: Upgraded system management and security management
· Software requirements analysis | 12
· Software design & code | 12
· Module documentation and acceptance test | 12
Client App: System management and security integration
· Software requirements analysis | 10
· Software design & code | 12
· Module documentation and acceptance test | 12
Client app: Provide integrated GUI to implement basic access stubs for all client apps. In Phase II
· User navigation requirements analysis | 10
· UI design & scripting | 12
· UI documentation and acceptance test | 10
Develop Product management subsystem
DBMS: Product management - continue development
· Design additional tables | 10
· Implement and test database structures | 12
Server App: Update Marketing and Development Application
· Software requirements analysis | 10
· Software design & code | 12
· Module documentation and acceptance test | 12
Client App: Update Marketing and Development Application
· Software requirements analysis | 10
· Software design & code | 12
· Module documentation and acceptance test | 12
Develop Customer and Vendor Relations subsystem
DBMS: Customer Relationship Management
· Design database | 12
· Implement and test database structures | 12
Server App: CRM & Vendor Relations
· Software requirements analysis | 12
· Software design & code | 12
· Module documentation and acceptance test | 12
Client App: Customer and Vendor Relations
· Software requirements analysis | 12
· Software design & code | 12
· Module documentation and acceptance test | 12
Develop Interface and Security for Supplier Web UI
DBMS: Update Orders and Invoicing Database – add quotations table
· Design database | 8
· Implement and test database structures | 10
Server App: Purchasing/Inventory
· Software requirements analysis | 12
· Software design & code | 12
· Module documentation and acceptance test | 12
Client App: Supplier Web UI
· Software requirements analysis | 12
· Software design & code | 12
· Module documentation and acceptance test | 12
Develop Knowledge Management and Training subsystem
DBMS: Knowledgebase database
· Design database | 8
· Implement and test database structures | 10
Server App: Knowledgebase and Training Manual
· Software requirements analysis | 9
· Software design & code | 9
· Module documentation and acceptance test | 9
Client App: Training Manual and Knowledgebase application
· Software requirements analysis | 9
· Software design & code | 9
· Module documentation and acceptance test | 9
Review Currency Prediction and Conversion subsystem
· Code and test software changes | 10
· Integration and regression testing for each component | 10
· Validate and test results | 10
· UAT | 9
· Sign-off | 2
Upgrade Operations Management & Reporting subsystem
DBMS: Sales and Market Phase III functions
· Design database | 12
· Implement and test database structures | 12
Server App: Upgraded Sales Analysis and Reporting for Phase III functions
· Software requirements analysis | 12
· Software design & code | 12
· Module documentation and acceptance test | 12
Client App: Management and Reporting for Phase II and III enhancements
· Software requirements analysis | 12
· Software design & code | 12
· Module documentation and acceptance test | 12
Upgrade System Management Subsystem (advanced functions)
DBMS: Logging & Audit Trail for Phase III functions.
· Design database | 12
· Implement and test database structures | 12
Server App: Upgraded system management and security application for Phase III functions
· Software requirements analysis | 12
· Software design & code | 12
· Module documentation and acceptance test | 12
Client App: user-navigation/access and reporting for Phase II Enhancements
· Software requirements analysis | 12
· Software design & code | 12
· Module documentation and acceptance test | 12
Web client: Provide advanced GUI to implement user menus & login form for UI client app. Phase III
· User navigation requirements analysis | 12
· UI design & scripting | 12
· UI documentation and acceptance test | 12
Phase III Delivery Activities
Phase III Integration Test
· Integration test of Phase III software components | 12
· Redesign and rework following integration tests | 12
· Phase I & II software documentation and acceptance test | 6
Phase III Change Management
· Business process change | 2
· Training on new work procedures | 8
· Update standard operating procedures | 2
· User training/train the trainer sessions | 8
· Set up and train support team (first-level and second-level) | 8
Process and System Evaluation
· Systems installation | 12
· Pilot test | 12
· User evaluation/feedback | 6
Project Review (Stagegate)
Stagegate review for the final system | 12
Remediation of client issues | 12
Client approval and signoff for final system | 12
Project Closure
Procurement close | 8
Obtain formal acceptance | 12
Release resources | 4

## Pre-Dev 3Pt Est
Pre-Development Activities | Optimistic | Most Likely | Pessimistic | Risk | Risk Estimate | 3-point Estimate* | 3-point Estimate (Average) | Assumptions
Perform Business Analysis | [7 empty] | This will take longer because of the complexity of the business and because of the fact that the different business areas are located in different countries
• Business Analysis Group 1 Observation and Meetings | 1.5 | 2 | 3 | High | 3 | 2.5 | 2.1667
• Business Analysis Group 2 Observation and Meetings | 1.5 | 2 | 3 | High | 3 | 2.5 | 2.1667
• Business Analysis Group 3 Observation and Meetings | 1.5 | 2 | 3 | Mid | 2 | 2.5 | 2.1667
• Business Analysis Group 4 Observation and Meetings | 1.5 | 2 | 3 | Mid | 2 | 2.5 | 2.1667
• Business Analysis Group 5 Observation and Meetings | 1.5 | 2 | 3 | Low | 1.5 | 2.5 | 2.1667
• Business Analysis Checkin Meeting | 1 | 1 | 1 | Mid | 1 | 1 | 1
• Business Analysis Wrapup Meeting | 1 | 1.5 | 2 | High | 2 | 1.5 | 1.5
Investigate Stakeholder Requirements
o Management and Reporting - Conduct application design workshop #1 | 1 | 1.5 | 2 | High | 2 | 1.5 | 1.5
o Sales - Conduct application design workshop | 0.5 | 1 | 1.5 | Mid | 1 | 1 | 1
o Marketing and Development - Conduct application design workshop | 1 | 1 | 1.5 | Mid | 1 | 1.5 | 1.1667
o Manufacturing - Conduct application design workshop | 0.5 | 0.5 | 1 | Mid | 0.5 | 1 | 0.66667
o Customer and Vendor Relations - Conduct application design workshop | 0.5 | 1 | 1.5 | Mid | 1 | 1 | 1
o Purchasing and Inventory Management - Conduct application design workshop | 1 | 1.5 | 2 | Mid | 1.5 | 1.5 | 1.5
o Accounting - Conduct application design workshop | 1 | 1.5 | 2.5 | Mid | 1.5 | 2 | 1.6667
o Management and Reporting - Conduct application design workshop #2 | 1 | 1.5 | 2 | High | 2 | 1.5 | 1.5
o System Administration - Conduct application design workshop | 0.5 | 1 | 1.5 | Mid | 1 | 1 | 1
o Analyze system user requirements gathered from application design workshops | 2 | 3 | 4 | Mid | 3 | 3 | 3
Perform feasibility study:
- Analyze the system configuration requirements for scale and interoperability/portability. | 2 | 3 | 4 | Mid | 3 | 3 | 3
- Perform a technology trawl to identify hardware and software required to deliver the system | 2 | 3 | 5 | Mid | 3 | 3.5 | 3.3333
- Research and identify services that we might contract with to perform currency tracking | 2 | 3 | 4 | Mid | 3 | 3 | 3
- Research and identify services that we might contract with to perform fax-to-email | 2 | 3 | 4 | Low | 2 | 3 | 3
- Research and identify RFID and barcode labeling requirements and suppliers | 2 | 3 | 4 | Mid | 3 | 3 | 3
Project planning:
- Revisit system requirements, integrating input from the stakeholder analysis and the feasibility study | 3 | 4 | 5 | Mid | 4 | 4 | 4
- Discuss and agree upon plan scope with key stakeholders | 1 | 2 | 3 | High | 3 | 2 | 2
- Rearrange interim deliverables, to reflect what we've learned | 1 | 1 | 1 | Low | 1 | 1 | 1
- Revise the project plan, resource plan, effort, time and budget estimates and project schedule | 3 | 4 | 5 | High | 5 | 4 | 4
- Review and agree estimate and timescale changes with upper management | 2 | 3 | 5 | High | 5 | 3.5 | 3.3333
- Revise project plans to accommodate any revisions to scope | 0.5 | 1 | 1.5 | Low | 0.5 | 1 | 1

## Phase 1 3Pt Est
| Optimistic | Most Likely | Pessimistic | Risk | Risk Estimate | 3-point Estimate* | 3-point Estimate (Average) | The three columns on the right just show alternative
Phase 1: Develop Basic Integrated Business Management System | [7 empty] | methods for obtaining a final estimate from the
Phase 1 Kickoff Meeting | 2 | 2 | 2 | Mid | 2 | 2 | 2 | best-case, average-case, worst-case estimates
Develop Initial System Management Subsystem | [7 empty] | to the left.
DBMS: Install & Configure DBMS Engine & SQL Interface
· Install & Configure DBMS engine | 5 | 8 | 12 | Mid | 8 | 8.5 | 8.3333 | I prefer the risk-based method, as this allows you to
· Install and test SQL interface software | 2 | 2 | 4 | Mid | 2 | 2.5 | 2.6667 | consider how difficult or risky each task is likely to be.
· Installing hardware server | 2 | 4 | 6 | Mid | 4 | 4 | 4
· Test Network connections | 5 | 8 | 10 | Mid | 8 | 8 | 7.6667 | * 3-point estimate is rounded up to the nearest 0.5 day.
· Evaluate the system | 2 | 2 | 3 | Mid | 2 | 2.5 | 2.3333
DBMS: User Accounts and Permissions
· Design database | 4 | 6 | 8 | High | 8 | 6 | 6
· Implement and test database structure | 2 | 2 | 4 | Mid | 2 | 2.5 | 2.6667
· Test accounts | 2 | 3 | 4 | Mid | 3 | 3 | 3
Server App: System management and security application
· Software requirements analysis | 8 | 4 | 6 | High | 6 | 5 | 6
· Software design | 6 | 8 | 9 | Mid | 8 | 8 | 7.6667
· Development & coding | 2 | 4 | 6 | Mid
· Module documentation and acceptance test | 2 | 4 | 6 | Mid | 4 | 4 | 4
Client App: System management application
· Software requirements analysis | 8 | 7 | 6 | High | 6 | 7 | 7
· Software design & code | 7 | 8 | 6 | Mid | 8 | 7.5 | 7
· Module documentation and acceptance test | 8 | 9 | 8 | Mid | 9 | 9 | 8.3333
Integrated User Interface: Provide integrated GUI to implement basic access stubs for all client apps. In Phase 1
· User navigation requirements analysis | 7 | 8 | 10 | High | 10 | 8.5 | 8.3333
· UI design & scripting | 8 | 10 | 12 | High | 12 | 10 | 10
· UI documentation and acceptance test | 10 | 11 | 12 | High | 12 | 11 | 11
Subsystem/component integration test & documentation | 6 | 10 | 12 | High | 12 | 10 | 9.3333
Develop Order Processing & Invoicing subsystem
DBMS: Orders & Invoicing Database – Full implementation
· Design database | 2 | 3 | 4 | Low | 2 | 3 | 3
· Implement and test database structures | 2 | 2 | 2 | Mid | 2 | 2 | 2
Server App: Billing/Invoicing
· Software requirements analysis | 5 | 8 | 10 | High | 10 | 8 | 7.6667
· Software design & code | 4 | 4 | 4 | Mid | 4 | 4 | 4
· Module documentation and acceptance test | 2 | 4 | 6 | Mid | 4 | 4 | 4
Client App: Sales
· Software requirements analysis | 2 | 3 | 4 | High | 4 | 3 | 3
· Software design & code | 5 | 8 | 12 | Mid | 8 | 8.5 | 8.3333
· Module documentation and acceptance test | 2 | 3 | 4 | Mid | 3 | 3 | 3
Subsystem/component integration test & documentation | 6 | 10 | 12 | High | 12 | 10 | 9.3333
Develop Billing/Accounting subsystem
DBMS: Budgeting and Accounting
· Design database | 4 | 7 | 12 | High | 12 | 7.5 | 7.6667
· Implement and test database structures | 3 | 3 | 4 | Mid | 3 | 3.5 | 3.3333
Server App: Billing/Invoicing
· Software requirements analysis | 2 | 3 | 3 | Mid | 3 | 3 | 2.6667
· Software design & code | 7 | 8 | 12 | Mid | 8 | 8.5 | 9
· Unit test | 2 | 3 | 4 | Mid | 3 | 3 | 3
· Module documentation and acceptance test | 2 | 5 | 7 | Mid | 5 | 5 | 4.6667
Client App: Accounting
· Software requirements analysis | 8 | 10 | 10 | Mid | 10 | 10 | 9.3333
· Software design & code | 4 | 8 | 12 | Mid | 8 | 8 | 8
· Module documentation and acceptance test | 3 | 8 | 12 | Mid | 8 | 8 | 7.6667
Develop Inventory management subsystem
DBMS: Resources & Inventory Database
· Design database | 4 | 7 | 12 | High | 12 | 7.5 | 7.6667
· Implement and test database structures | 3 | 3 | 4 | Mid | 3 | 3.5 | 3.3333
Server App: Purchasing & Inventory Management
· Software requirements analysis | 2 | 3 | 3 | Mid | 3 | 3 | 2.6667
· Software design & code | 7 | 8 | 12 | Mid | 8 | 8.5 | 9
· Module documentation and acceptance test | 2 | 3 | 4 | Mid | 3 | 3 | 3
Subsystem/component integration test & documentation | 6 | 10 | 12 | High | 12 | 10 | 9.3333
Client App: Inventory Management
· Software requirements analysis | 4 | 8 | 12 | Mid | 8 | 8 | 8
· Software design & code | 6 | 10 | 14 | Mid | 10 | 10 | 10
· Module documentation and acceptance test | 2 | 8 | 4 | Mid | 8 | 6.5 | 4.6667
Develop System Management Subsystem (advanced functions) | [6 empty] | #DIV/0!
DBMS: Logging & Audit Trail for Phase I functions.
· Design database | 7 | 10 | 14 | High | 14 | 10.5 | 10.3333
· Implement and test database structures | 4 | 8 | 12 | High | 12 | 8 | 8
GUI & front-end menu implementation
Client App: Integrated user-navigation/access
· Software requirements analysis | 10 | 14 | 14 | High | 14 | 13.5 | 12.6667
· Requirment gathering | 2 | 4 | 4 | Mid
· Requirment analysis phase | 8 | 10 | 10 | High
· Software design & code | 8 | 10 | 10 | High | 10 | 10 | 9.3333
· Module documentation and acceptance test | 7 | 10 | 12 | High | 12 | 10 | 9.6667
Subsystem/component integration test & documentation | 6 | 10 | 12 | High | 12 | 10 | 9.3333
Client App: Provide advanced GUI to implement user menus and login form for UI client app.
· User navigation requirements analysis | 8 | 9 | 10 | High | 10 | 9 | 9
· UI design & scripting | 7 | 8 | 8 | High | 8 | 8 | 7.6667
GUI unit tests | 8 | 8 | 9 | High | 9 | 8.5 | 8.3333
· UI documentation and acceptance test | 7 | 7 | 7 | High | 7 | 7 | 7
Phase I Delivery Activities
Phase I Integration Test
· Integration test of Phase I software components | 7 | 8 | 10 | High | 10 | 8.5 | 8.3333
· Redesign and rework following integration tests | 6 | 8 | 9 | High | 9 | 8 | 7.6667
· Phase I software documentation and acceptance test | 4 | 6 | 8 | Mid | 6 | 6 | 6
Phase I Change management
· Training on new work procedures | 1 | 1 | 1 | Mid | 1 | 1 | 1
· Business process changes | 2 | 4 | 4 | Mid | 4 | 4 | 3.3333
· User system training | 2 | 2 | 2 | Mid | 2 | 2 | 2
New process & systems evaluation
· Phase I systems installation | 2 | 8 | 4 | Mid | 8 | 6.5 | 4.6667
· Phase I Testing | 5 | 7 | 9 | Mid | 7 | 7 | 7
· Phase I System Documentation | 4 | 6 | 8 | Mid | 6 | 6 | 6
· Phase I User evaluation | 1 | 2 | 2 | Mid | 2 | 2 | 1.6667
· Evaluate the feedback | 1 | 1 | 1 | Mid | 1 | 1 | 1
Project Review
· Project plan review for Phase I | 1 | 2 | 1 | High | 1 | 2 | 1.3333
· Management approval and signoff for Phase I | 2 | 3 | 4 | High | 4 | 3 | 3

## Phase 2 3Pt Est
Phase 2 Activities | Optimistic | Most Likely | Pessimistic | Risk | Risk Estimate | 3-point Estimate* | 3-point Estimate (Average)
Phase 2 Kickoff Meeting | 2 | 2 | 2 | Mid | 2 | 2 | 2
Phase 1 follow up
Review Phase I software components | 5 | 5 | 6 | Mid | 5 | 5.5 | 5.3333
Review Phase I hardware components | 5 | 5 | 6 | Mid | 5 | 5.5 | 5.3333
Upgrade the software requirements | 6 | 8 | 10 | High | 10 | 8 | 8
Upgrade System Management Subsystem (Basic)
Server App: Upgraded system management and security management
- Software requirements analysis
-Requirements Scope | 1 | 2 | 2 | Mid | 2 | 2 | 1.6667
-Stakeholder Identification | 1 | 2 | 2 | Mid | 2 | 2 | 1.6667
-Requirements Elicitation and Analysis | 3 | 3 | 5 | High | 5 | 3.5 | 3.6667
-Software requirement specification and Management | 4 | 5 | 5 | High | 5 | 5 | 4.6667
- Software design | 4 | 4 | 5 | High | 5 | 4.5 | 4.3333
- Software code | 4 | 4 | 5 | High | 5 | 4.5 | 4.3333
- Module documentation and acceptance test | 8 | 10 | 12 | High | 12 | 10 | 10
Client App: System management and security integration
- Software requirements analysis
-Requirements Scope | 1 | 2 | 2 | Mid | 2 | 2 | 1.6667
-Stakeholder Identification | 1 | 2 | 2 | Mid | 2 | 2 | 1.6667
-Requirements Elicitation and Analysis | 3 | 3 | 5 | High | 5 | 3.5 | 3.6667
-Software requirement specification and Management | 4 | 5 | 5 | High | 5 | 5 | 4.6667
- Software design | 4 | 4 | 5 | High | 5 | 4.5 | 4.3333
- Software code | 4 | 4 | 5 | High | 5 | 4.5 | 4.3333
Develop Operations Management & Reporting subsystem
DBMS: Sales and Market
- Design database by creating tables, developing packages and integrating with the server application | 8 | 8 | 10 | High | 10 | 8.5 | 8.6667
- Implement and test database structures | 9 | 10 | 11 | High | 11 | 10 | 10
- Gather information regarding previous sales and market demands. | 5 | 5 | 5 | Low | 5 | 5 | 5
Server App: Sales Analysis and Reporting
- Software requirements analysis | 3 | 5 | 6 | Mid | 5 | 5 | 4.6667
- Software design & code | 4 | 4 | 4 | Low | 4 | 4 | 4
- Write a program to display the analysis using charts and graphs for easy understanding. | 1 | 1 | 2 | Low | 1 | 1.5 | 1.3333
- Module documentation and acceptance test | 2 | 2 | 2 | Low | 2 | 2 | 2
Client App: Management and Reporting
- Software requirements analysis | 3 | 5 | 6 | Mid | 5 | 5 | 4.6667
- Software design & code
- Develop a user friendly UI that shows the graph and charts of sales against time duration and scale. | 1 | 1 | 2 | Low | 1 | 1.5 | 1.3333
- Application used to report | 2 | 2 | 3 | Mid | 2 | 2.5 | 2.3333
- Develop the GUI | 1 | 1 | 2 | Mid | 1 | 1.5 | 1.3333
- Unit testing of GUI | 1 | 1 | 2 | Low | 1 | 1.5 | 1.3333
- Module documentation and acceptance test | 2 | 2 | 2 | Low | 2 | 2 | 2
Develop Forecasting and Analysis subsystem
DBMS: Update Sales and Market Database – add forecasting & analysis table
#NAME? | 2 | 2 | 3 | Mid | 2 | 2.5 | 2.3333
- Implement and test database structures | 2 | 2 | 2 | Mid | 2 | 2 | 2
Server App: Demand Forecasting
- Software requirements analysis
-Requirements Scope | 1 | 2 | 2 | Mid | 2 | 2 | 1.6667
-Stakeholder Identification | 1 | 2 | 2 | Mid | 2 | 2 | 1.6667
-Requirements Elicitation and Analysis | 3 | 3 | 5 | High | 5 | 3.5 | 3.6667
-Software requirement specification and Management | 4 | 5 | 5 | High | 5 | 5 | 4.6667
- Software design | 4 | 4 | 5 | High | 5 | 4.5 | 4.3333
- Software code | 4 | 4 | 5 | High | 5 | 4.5 | 4.3333
- Software design & code | 3 | 2 | 2 | Mid | 2 | 2.5 | 2.3333
- Develop UI to view the forecasted demand value | 1 | 1 | 1 | Low | 1 | 1 | 1
- Module documentation and acceptance test | 2 | 2 | 4 | Mid | 2 | 2.5 | 2.6667
Develop Product code database and Lookup subsystem
DBMS: Product Management (only product code-related tables)
- Design database by creating tables, developing packages and integrating with the server application | 8 | 8 | 10 | Mid | 8 | 8.5 | 8.6667
- Implement and test database structures | 4 | 5 | 5 | Low | 4 | 5 | 4.6667
Server App: Marketing and Development (functions related to product code)
- Software requirements analysis | 3 | 3 | 4 | Mid | 3 | 3.5 | 3.3333
- Software design & code | 3 | 2 | 2 | Mid | 2 | 2.5 | 2.3333
- Module documentation and acceptance test | 2 | 2 | 4 | Mid | 2 | 2.5 | 2.6667
Client App: Marketing and Development Application (functions related to product code)
- Software requirements analysis | 3 | 3 | 4 | Mid | 3 | 3.5 | 3.3333
- Software design & code | 3 | 4 | 4 | Mid | 4 | 4 | 3.6667
- Module documentation and acceptance test | 2 | 2 | 4 | Mid | 2 | 2.5 | 2.6667
Service: Product code lookup service
- Software requirements analysis | 3 | 3 | 4 | Mid | 3 | 3.5 | 3.3333
- Software design & code | 3 | 2 | 3 | Mid | 2 | 2.5 | 2.6667
- Integration testing | 3 | 2 | 3 | Mid | 2 | 2.5 | 2.6667
- Documentation and acceptance test | 3 | 2 | 2 | Low | 3 | 2.5 | 2.3333
Develop Currency prediction and Conversion subsystem
Server App: API to Vendor currency database
- Software requirements analysis | 3 | 3 | 4 | Mid | 3 | 3.5 | 3.3333
- Software design & code | 2 | 2 | 3 | Mid | 2 | 2.5 | 2.3333
- Module documentation and acceptance test | 2 | 2 | 3 | Low | 2 | 2.5 | 2.3333
Upgrade System Management Subsystem (advanced functions)
DBMS: Logging & Audit Trail for Phase II functions.
- Design database by creating tables, developing packages and integrating with the server application | 4 | 4 | 5 | Mid | 4 | 4.5 | 4.3333
- Implement and test database structures | 2 | 2 | 3 | Mid | 2 | 2.5 | 2.3333
DBMS: Permissions for Phase II functions.
- Update database | 1 | 1 | 2 | Mid | 1 | 1.5 | 1.3333
- Implement and test database structures | 1 | 1 | 1 | Low | 1 | 1 | 1
Server App: Upgraded system management and security application for Phase II functions
- Software requirements analysis | 1 | 2 | 2 | Mid | 2 | 2 | 1.6667
- Software design & code | 1 | 1 | 2 | Mid | 1 | 1.5 | 1.3333
- Module documentation and acceptance test | 1 | 1 | 2 | Mid | 1 | 1.5 | 1.3333
Client App: user-navigation/access and reporting for Phase II Enhancements
- Software requirements analysis | 1 | 1 | 2 | Low | 1 | 1.5 | 1.3333
- Software design & code | 1 | 1 | 2 | Low | 1 | 1.5 | 1.3333
- Module documentation and acceptance test | 1 | 2 | 2 | Low | 1 | 2 | 1.6667
Client app: Provide advanced GUI to implement user menus and login form for UI client app. (Phase II)
- User navigation requirements analysis | 1 | 1 | 2 | Low | 1 | 1.5 | 1.3333
- UI design & scripting | 1 | 2 | 2 | Low | 1 | 2 | 1.6667
- UI documentation and acceptance test | 1 | 1 | 2 | Low | 1 | 1.5 | 1.3333
Develop Inventory management subsystem
DBMS: Resources & Inventory Database
- Design database by creating tables and integrating with the server application | 8 | 8 | 10 | High | 10 | 8.5 | 8.6667
- Implement and test database structures | 4 | 4 | 5 | Mid | 4 | 4.5 | 4.3333
Server App: Purchasing & Inventory Management
- Software requirements analysis | 3 | 2 | 2 | Mid | 2 | 2.5 | 2.3333
- Software design & code | 3 | 3 | 2 | Mid | 3 | 3 | 2.6667
- Module documentation and acceptance test | 2 | 2 | 1 | Low | 2 | 2 | 1.6667
Client App: Inventory Management
- Software requirements analysis | 2 | 2 | 1 | Mid | 2 | 2 | 1.6667
- Software design & code | 2 | 1 | 1 | Low | 2 | 1.5 | 1.3333
- Module documentation and acceptance test | 2 | 1 | 1 | Mid | 1 | 1.5 | 1.3333
Phase II Delivery Activities
Integrate all the software components developed.
Phase II Integration Test
- Integration test of Phase II software components | 6 | 6 | 8 | High | 8 | 6.5 | 6.6667
- Redesign and rework following integration tests | 6 | 8 | 10 | High | 10 | 8 | 8
- Phase I software documentation and acceptance test | 6 | 8 | 10 | Mid | 8 | 8 | 8
Phase II change management
- Business process changes | 1 | 1 | 2 | Low | 1 | 1.5 | 1.3333
- Training in new work procedures | 1 | 2 | 2 | Low | 1 | 2 | 1.6667
- User system training | 1 | 2 | 2 | Low | 1 | 2 | 1.6667
New process & systems evaluation
- Phase II systems installation | 8 | 8 | 10 | Mid | 8 | 8.5 | 8.6667
- Phase II pilot study | 8 | 8 | 10 | Mid | 8 | 8.5 | 8.6667
- Phase II user evaluation | 1 | 1 | 2 | High | 2 | 1.5 | 1.3333
- Evaluation feedback and client review | 1 | 2 | 2 | High | 2 | 2 | 1.6667
Project Review (Stagegate)
- Stagegate (project plan) review for Phase II | 1 | 1 | 2 | High | 2 | 1.5 | 1.3333
- Agreement of client issues to be remedied in Phase II | 2 | 4 | 4 | High | 4 | 4 | 3.3333
- Client approval and signoff for Phase II | 2 | 3 | 4 | High | 4 | 3 | 3

## Phase 3 3Pt Est
Effort Estimates For Each Task
Phase 3 Activities | Optimistic | Most Likely | Pessimistic | Risk | Risk Estimate | 3-point Estimate* | 3-point Estimate (Average)
Phase III Kickoff Meeting | 2 | 2 | 2 | Mid | 2 | 2 | 2
Follow up on Phase II activities
· Review lessons learned from Phase 2 prototype and user evaluation | 6 | 8 | 10 | Mid | 8 | 8 | 8
· Review software and hardware requirements | 8 | 10 | 12 | Mid | 10 | 10 | 10
· Agree on changes to be made and assign tasks | 6 | 8 | 10 | Mid | 8 | 8 | 8
Upgrade System Management Subsystem (Basic)
Server App: Upgraded system management and security management
· Software requirements analysis | 9 | 11 | 12 | High | 12 | 11 | 10.6667
· Software design & code | 8 | 10 | 12 | High | 12 | 10 | 10
· Module documentation and acceptance test | 8 | 10 | 12 | High | 12 | 10 | 10
Client App: System management and security integration
· Software requirements analysis | 6 | 8 | 10 | High | 10 | 8 | 8
· Software design & code | 8 | 10 | 12 | High | 12 | 10 | 10
· Module documentation and acceptance test | 8 | 10 | 12 | High | 12 | 10 | 10
Client app: Provide integrated GUI to implement basic access stubs for all client apps. In Phase II
· User navigation requirements analysis | 6 | 8 | 10 | High | 10 | 8 | 8
· UI design & scripting | 8 | 10 | 12 | High | 12 | 10 | 10
· UI documentation and acceptance test | 5 | 7 | 10 | High | 10 | 7.5 | 7.3333
Develop Product management subsystem
DBMS: Product management - continue development
· Design additional tables | 7 | 8 | 10 | High | 10 | 8.5 | 8.3333
· Implement and test database structures | 9 | 10 | 12 | High | 12 | 10.5 | 10.3333
Server App: Update Marketing and Development Application
· Software requirements analysis | 6 | 8 | 10 | High | 10 | 8 | 8
· Software design & code | 8 | 10 | 12 | High | 12 | 10 | 10
· Module documentation and acceptance test | 8 | 10 | 12 | High | 12 | 10 | 10
Client App: Update Marketing and Development Application
· Software requirements analysis | 6 | 8 | 10 | High | 10 | 8 | 8
· Software design & code | 8 | 10 | 12 | High | 12 | 10 | 10
· Module documentation and acceptance test | 8 | 10 | 12 | High | 12 | 10 | 10
Develop Customer and Vendor Relations subsystem
DBMS: Customer Relationship Management
· Design database | 10 | 10 | 12 | High | 12 | 10.5 | 10.6667
· Implement and test database structures | 10 | 10 | 12 | High | 12 | 10.5 | 10.6667
Server App: CRM & Vendor Relations
· Software requirements analysis | 10 | 10 | 12 | High | 12 | 10.5 | 10.6667
· Software design & code | 10 | 10 | 12 | High | 12 | 10.5 | 10.6667
· Module documentation and acceptance test | 10 | 10 | 12 | High | 12 | 10.5 | 10.6667
Client App: Customer and Vendor Relations
· Software requirements analysis | 10 | 10 | 12 | High | 12 | 10.5 | 10.6667
· Software design & code | 10 | 10 | 12 | High | 12 | 10.5 | 10.6667
· Module documentation and acceptance test | 10 | 10 | 12 | High | 12 | 10.5 | 10.6667
Develop Interface and Security for Supplier Web UI
DBMS: Update Orders and Invoicing Database – add quotations table
· Design database | 6 | 8 | 10 | Mid | 8 | 8 | 8
· Implement and test database structures | 8 | 10 | 12 | Mid | 10 | 10 | 10
Server App: Purchasing/Inventory
· Software requirements analysis | 10 | 10 | 12 | High | 12 | 10.5 | 10.6667
· Software design & code | 10 | 10 | 12 | High | 12 | 10.5 | 10.6667
· Module documentation and acceptance test | 10 | 10 | 12 | High | 12 | 10.5 | 10.6667
Client App: Supplier Web UI
· Software requirements analysis | 10 | 10 | 12 | High | 12 | 10.5 | 10.6667
· Software design & code | 10 | 10 | 12 | High | 12 | 10.5 | 10.6667
· Module documentation and acceptance test | 10 | 10 | 12 | High | 12 | 10.5 | 10.6667
Develop Knowledge Management and Training subsystem
DBMS: Knowledgebase database
· Design database | 6 | 8 | 10 | Mid | 8 | 8 | 8
· Implement and test database structures | 8 | 10 | 12 | Mid | 10 | 10 | 10
Server App: Knowledgebase and Training Manual
· Software requirements analysis | 7 | 9 | 12 | Mid | 9 | 9.5 | 9.3333
· Software design & code | 8 | 9 | 12 | Mid | 9 | 9.5 | 9.6667
· Module documentation and acceptance test | 8 | 9 | 12 | Mid | 9 | 9.5 | 9.6667
Client App: Training Manual and Knowledgebase application
· Software requirements analysis | 7 | 9 | 12 | Mid | 9 | 9.5 | 9.3333
· Software design & code | 8 | 9 | 12 | Mid | 9 | 9.5 | 9.6667
· Module documentation and acceptance test | 8 | 9 | 12 | Mid | 9 | 9.5 | 9.6667
Review Currency Prediction and Conversion subsystem
· Code and test software changes | 8 | 9 | 10 | High | 10 | 9 | 9
· Integration and regression testing for each component | 8 | 9 | 10 | High | 10 | 9 | 9
· Validate and test results | 8 | 9 | 10 | High | 10 | 9 | 9
· UAT | 5 | 7 | 9 | High | 9 | 7 | 7
· Sign-off | 2 | 2 | 2 | Mid | 2 | 2 | 2
Upgrade Operations Management & Reporting subsystem
DBMS: Sales and Market Phase III functions
· Design database | 7 | 10 | 12 | High | 12 | 10 | 9.6667
· Implement and test database structures | 7 | 10 | 12 | High | 12 | 10 | 9.6667
Server App: Upgraded Sales Analysis and Reporting for Phase III functions
· Software requirements analysis | 7 | 10 | 12 | High | 12 | 10 | 9.6667
· Software design & code | 7 | 10 | 12 | High | 12 | 10 | 9.6667
· Module documentation and acceptance test | 7 | 10 | 12 | High | 12 | 10 | 9.6667
Client App: Management and Reporting for Phase II and III enhancements
· Software requirements analysis | 7 | 10 | 12 | High | 12 | 10 | 9.6667
· Software design & code | 7 | 10 | 12 | High | 12 | 10 | 9.6667
· Module documentation and acceptance test | 7 | 10 | 12 | High | 12 | 10 | 9.6667
Upgrade System Management Subsystem (advanced functions)
DBMS: Logging & Audit Trail for Phase III functions.
· Design database | 8 | 10 | 12 | High | 12 | 10 | 10
· Implement and test database structures | 8 | 10 | 12 | High | 12 | 10 | 10
Server App: Upgraded system management and security application for Phase III functions
· Software requirements analysis | 8 | 10 | 12 | High | 12 | 10 | 10
· Software design & code | 8 | 10 | 12 | High | 12 | 10 | 10
· Module documentation and acceptance test | 8 | 10 | 12 | High | 12 | 10 | 10
Client App: user-navigation/access and reporting for Phase II Enhancements
· Software requirements analysis | 8 | 10 | 12 | High | 12 | 10 | 10
· Software design & code | 8 | 10 | 12 | High | 12 | 10 | 10
· Module documentation and acceptance test | 8 | 10 | 12 | High | 12 | 10 | 10
Web client: Provide advanced GUI to implement user menus & login form for UI client app. Phase III
· User navigation requirements analysis | 8 | 10 | 12 | High | 12 | 10 | 10
· UI design & scripting | 8 | 10 | 12 | High | 12 | 10 | 10
· UI documentation and acceptance test | 8 | 10 | 12 | High | 12 | 10 | 10
Phase III Delivery Activities
Phase III Integration Test
· Integration test of Phase III software components | 7 | 10 | 12 | High | 12 | 10 | 9.6667
· Redesign and rework following integration tests | 10 | 10 | 12 | High | 12 | 10.5 | 10.6667
· Phase I & II software documentation and acceptance test | 4 | 6 | 12 | Mid | 6 | 7 | 7.3333
Phase III Change Management
· Business process change | 2 | 2 | 2 | Mid | 2 | 2 | 2
· Training on new work procedures | 5 | 7 | 8 | High | 8 | 7 | 6.6667
· Update standard operating procedures | 2 | 2 | 2 | Mid | 2 | 2 | 2
· User training/train the trainer sessions | 5 | 7 | 8 | High | 8 | 7 | 6.6667
· Set up and train support team (first-level and second-level) | 5 | 7 | 8 | High | 8 | 7 | 6.6667
Process and System Evaluation
· Systems installation | 8 | 10 | 12 | High | 12 | 10 | 10
· Pilot test | 10 | 10 | 12 | High | 12 | 10.5 | 10.6667
· User evaluation/feedback | 2 | 4 | 6 | High | 6 | 4 | 4
Project Review (Stagegate)
Stagegate review for the final system | 10 | 10 | 12 | High | 12 | 10.5 | 10.6667
Remediation of client issues | 10 | 10 | 12 | High | 12 | 10.5 | 10.6667
Client approval and signoff for final system | 9 | 10 | 12 | High | 12 | 10.5 | 10.3333
Project Closure
Procurement close | 4 | 8 | 10 | Mid | 8 | 8 | 7.3333
Obtain formal acceptance | 10 | 10 | 12 | High | 12 | 10.5 | 10.6667
Release resources | 2 | 4 | 6 | Mid | 4 | 4 | 4