## Original3
Name | Start | Finish | Work | Work Days | Usage | Cost
Business Analyst 1 | Mon 1/7/19 | Tue 8/9/22 | 1,808 hrs | 937 | 24.12% | 1157382.4
Business Analyst 2 | Mon 1/7/19 | Tue 6/1/21 | 368 hrs | 627 | 7.337% | 774470.4
System Analyst | Mon 1/7/19 | Thu 8/25/22 | 3,400 hrs | 949 | 44.78% | 1264068
Project Manager | Mon 1/7/19 | Thu 10/20/22 | 4,464 hrs | 989 | 56.42% | 1758837.6
Documentation Specialist | Mon 1/7/19 | Tue 6/28/22 | 976 hrs | 907 | 13.45% | 963379.12
Consultant Requirements Analyst | Mon 1/7/19 | Mon 2/18/19 | 240 hrs | 31 | 96.77% | 56432.4
Consultant Network Specialist | Thu 2/28/19 | Thu 3/7/19 | 48 hrs | 6 | 100% | 9936
Database Administrator | Fri 2/22/19 | Thu 8/25/22 | 1,704 hrs | 915 | 23.28% | 327862.8
Software Test Engineer | Mon 12/9/19 | Thu 2/18/21 | 568 hrs | 314 | 22.61% | 112989.76
Software Tester 1 | Fri 2/22/19 | Tue 8/9/22 | 1,448 hrs | 903 | 20.04% | 242726.4
Software Tester 2 | Mon 12/9/19 | Wed 4/29/20 | 200 hrs | 103 | 24.27% | 27686.4
Programmer 1 | Fri 2/22/19 | Mon 6/20/22 | 1,856 hrs | 867 | 26.76% | 1133203.68
Programmer 2 | Fri 4/19/19 | Thu 7/14/22 | 1,560 hrs | 845 | 23.08% | 1104448.8
Programmer 3 | Mon 7/13/20 | Tue 10/20/20 | 160 hrs | 72 | 27.78% | 94106.88
UI Designer 1 | Fri 2/22/19 | Tue 5/17/22 | 1,632 hrs | 843 | 24.2% | 1004046.72
UI Designer 2 | Thu 3/12/20 | Tue 3/24/20 | 72 hrs | 9 | 100% | 10719.36
Database Analyst 1 | Fri 2/22/19 | Mon 8/1/22 | 1,760 hrs | 897 | 24.53% | 1039084.8
|  |  |  | Average | 38.79% | 11081381.52 | Total
Formulas:
Work Days = NETWORKDAYS(DATEVALUE(RIGHT([Start],LEN([Start])-4)),DATEVALUE(RIGHT([Finish],LEN([Finish])-4)))

## CutAndLevel3
Name | Start | Finish | Work | Work Days | Usage | Cost
Consultant Requirements Analyst | Mon 1/7/19 | Mon 2/18/19 | 240 hrs | 31 | 96.77% | 56432.4
Business Analyst 1 | Mon 1/7/19 | Mon 7/25/22 | 1,952 hrs | 926 | 26.35% | 1143795.2
Business Analyst 2 | Mon 1/7/19 | Tue 2/12/19 | 192 hrs | 27 | 88.89% | 33350.4
System Analyst | Mon 1/7/19 | Wed 8/10/22 | 3,432 hrs | 938 | 45.74% | 1249416
Project Manager | Mon 1/7/19 | Wed 10/5/22 | 4,464 hrs | 978 | 57.06% | 1739275.2
Documentation Specialist | Mon 1/7/19 | Mon 6/13/22 | 976 hrs | 896 | 13.62% | 951695.36
Consultant Network Specialist | Thu 2/28/19 | Thu 3/7/19 | 48 hrs | 6 | 100% | 9936
Database Administrator | Fri 2/22/19 | Wed 8/10/22 | 1,704 hrs | 904 | 23.56% | 323921.28
Database Analyst 1 | Fri 2/22/19 | Fri 7/15/22 | 1,760 hrs | 886 | 24.83% | 1026342.4
Programmer 1 | Fri 2/22/19 | Fri 6/3/22 | 2,016 hrs | 856 | 29.44% | 1118826.24
Programmer 2 | Fri 4/19/19 | Wed 6/29/22 | 1,560 hrs | 834 | 23.38% | 1090071.36
UI Designer 1 | Fri 2/22/19 | Mon 5/2/22 | 1,632 hrs | 832 | 24.52% | 990945.28
Software Test Engineer | Mon 12/9/19 | Wed 2/3/21 | 624 hrs | 303 | 25.74% | 109031.52
Software Tester 1 | Fri 2/22/19 | Mon 7/25/22 | 1,496 hrs | 892 | 20.96% | 239769.6
|  |  |  | Average | 42.92% | 10082808.24 | Total
Formulas:
Work Days = NETWORKDAYS(DATEVALUE(RIGHT([Start],LEN([Start])-4)),DATEVALUE(RIGHT([Finish],LEN([Finish])-4)))

## ReorderLevel4
Name | Start | Finish | Work | Work Days | Usage | Cost
Consultant Requirements Analyst | Mon 1/7/19 | Fri 2/15/19 | 224 hrs | 30 | 93.33% | 54612
Business Analyst 1 | Mon 1/7/19 | Fri 6/18/21 | 2,032 hrs | 640 | 39.69% | 790528
Business Analyst 2 | Mon 1/7/19 | Tue 2/12/19 | 192 hrs | 27 | 88.89% | 33350.4
System Analyst | Mon 1/7/19 | Tue 7/6/21 | 3,432 hrs | 652 | 65.8% | 868464
Project Manager | Mon 1/7/19 | Tue 8/31/21 | 4,256 hrs | 692 | 76.88% | 1230652.8
Documentation Specialist | Mon 1/7/19 | Fri 5/7/21 | 896 hrs | 610 | 18.36% | 647917.6
Consultant Network Specialist | Mon 2/25/19 | Mon 3/4/19 | 48 hrs | 6 | 100% | 9936
Database Administrator | Thu 2/21/19 | Tue 7/6/21 | 1,624 hrs | 619 | 32.79% | 221800.08
Database Analyst 1 | Thu 2/21/19 | Thu 6/10/21 | 1,728 hrs | 601 | 35.94% | 696198.4
Programmer 1 | Thu 2/21/19 | Thu 4/29/21 | 2,080 hrs | 571 | 45.53% | 746319.84
Programmer 2 | Fri 3/1/19 | Tue 5/25/21 | 1,536 hrs | 583 | 32.93% | 762004.32
UI Designer 1 | Thu 2/21/19 | Fri 3/12/21 | 1,632 hrs | 537 | 37.99% | 639588.48
Software Test Engineer | Wed 6/19/19 | Mon 5/11/20 | 528 hrs | 234 | 28.21% | 84202.56
Software Tester 1 | Thu 2/21/19 | Fri 6/18/21 | 1,528 hrs | 607 | 31.47% | 163161.6
|  |  |  | Average | 51.99% | 6948736.08 | Total
Formulas:
Work Days = NETWORKDAYS(DATEVALUE(RIGHT([Start],LEN([Start])-4)),DATEVALUE(RIGHT([Finish],LEN([Finish])-4)))

## RemoveOverlap5
Name | Start | Finish | Work | Work Days | Usage | Cost
Consultant Requirements Analyst | Mon 1/7/19 | Fri 2/15/19 | 224 hrs | 30 | 93.33% | 54612
Business Analyst 1 | Mon 1/7/19 | Mon 5/17/21 | 1,208 hrs | 616 | 24.51% | 760883.2
Business Analyst 2 | Mon 1/7/19 | Tue 2/12/19 | 192 hrs | 27 | 88.89% | 33350.4
System Analyst | Mon 1/7/19 | Wed 6/2/21 | 2,096 hrs | 628 | 41.72% | 836496
Project Manager | Mon 1/7/19 | Wed 7/28/21 | 3,240 hrs | 668 | 60.63% | 1187971.2
Documentation Specialist | Mon 1/7/19 | Fri 3/12/21 | 664 hrs | 570 | 14.56% | 605431.2
Consultant Network Specialist | Mon 2/25/19 | Mon 3/4/19 | 48 hrs | 6 | 100% | 9936
Database Administrator | Wed 2/27/19 | Wed 4/21/21 | 1,040 hrs | 561 | 23.17% | 201017.52
Database Analyst 1 | Thu 2/21/19 | Fri 5/7/21 | 1,256 hrs | 577 | 27.21% | 668396.8
Programmer 1 | Thu 2/21/19 | Thu 3/4/21 | 1,776 hrs | 531 | 41.81% | 694038.24
Programmer 2 | Fri 3/1/19 | Wed 4/21/21 | 984 hrs | 559 | 22% | 730635.36
UI Designer 1 | Tue 4/2/19 | Fri 1/29/21 | 968 hrs | 479 | 25.26% | 570508.16
Software Test Engineer | Thu 4/4/19 | Thu 3/12/20 | 360 hrs | 246 | 18.29% | 88520.64
Software Tester 1 | Fri 3/1/19 | Fri 5/7/21 | 872 hrs | 571 | 19.09% | 153484.8
|  |  |  | Average | 42.89% | 6595281.52 | Total
Formulas:
Work Days = NETWORKDAYS(DATEVALUE(RIGHT([Start],LEN([Start])-4)),DATEVALUE(RIGHT([Finish],LEN([Finish])-4)))

## RawLaborCosts-WBS4
WBS | Task Name | Duration | Predecessors | Successors | Start | Finish | WBS Successors | Resource Initials | WBS Level | Type | Task Cost | Activity Cost | Component Cost | Phase Cost | Total Cost
1 | Pre-Development Activities | 54 days |  |  | Mon 1/7/19 | Thu 3/21/19 |  |  | 0 | Phase |  |  |  | 238037.28 | 4985759.04
1.1 | Project Planning Kickoff | 1 day |  | 4,5,6,7,8,9FS+2 days | Mon 1/7/19 | Mon 1/7/19 | 1.2.1,1.2.2,1.2.3,1.2.4,1.2.5,1.2.6[FS+2 days] | BA1,BA2,CRA1,PM1,SA1,DS1 | 1 | Task | 8463.36
1.2 | Perform Business Analysis | 7 days |  |  | Tue 1/8/19 | Wed 1/16/19 |  |  | 1 | Activity |  | 46110.08
1.2.1 | Business Analysis Group 1 Observation and Meetings | 2 days | 2 | 12,10 | Tue 1/8/19 | Wed 1/9/19 | 1.2.9,1.2.7 | BA1 | 2 | Task | 2470.4
1.2.2 | Business Analysis Group 2 Observation and Meetings | 2 days | 2 | 12,11 | Tue 1/8/19 | Wed 1/9/19 | 1.2.9,1.2.8 | BA2 | 2 | Task | 2470.4
1.2.3 | Business Analysis Group 3 Observation and Meetings | 2 days | 2 | 12 | Tue 1/8/19 | Wed 1/9/19 | 1.2.9 | CRA1 | 2 | Task | 3640.8
1.2.4 | Business Analysis Group 4 Observation and Meetings | 2 days | 2 | 12 | Tue 1/8/19 | Wed 1/9/19 | 1.2.9 | PM1 | 2 | Task | 3556.8
1.2.5 | Business Analysis Group 5 Observation and Meetings | 2 days | 2 | 12 | Fri 1/11/19 | Mon 1/14/19 | 1.2.9 | CRA1 | 2 | Task | 3640.8
1.2.6 | Business Analysis Checkin Meeting | 1 day | 2FS+2 days | 12,10,11 | Thu 1/10/19 | Thu 1/10/19 | 1.2.9,1.2.7,1.2.8 | BA1,BA2,CRA1,PM1,SA1,DS1 | 2 | Task | 8463.36
1.2.7 | Business Analysis Group 1 Pt2 Observation and Meetings | 2 days | 4,9 | 12 | Fri 1/11/19 | Mon 1/14/19 | 1.2.9 | BA1 | 2 | Task | 2470.4
1.2.8 | Business Analysis Group 2 Pt2 Observation and Meetings | 2 days | 5,9 | 12 | Fri 1/11/19 | Mon 1/14/19 | 1.2.9 | BA2 | 2 | Task | 2470.4
1.2.9 | Business Analysis Wrapup Meeting | 2 days | 4,5,6,7,8,9,10,11 | 14 | Tue 1/15/19 | Wed 1/16/19 | 1.3.1 | BA1,BA2,CRA1,PM1,SA1,DS1 | 2 | Task | 16926.72
1.3 | Investigate Stakeholder Requirements | 11 days |  |  | Thu 1/17/19 | Thu 1/31/19 |  |  | 1 | Activity |  | 70282
1.3.1 | Management and Reporting - Conduct application design workshop #1 | 2 days | 12 | 15,16,17,18,19,20,21 | Thu 1/17/19 | Fri 1/18/19 | 1.3.2,1.3.3,1.3.4,1.3.5,1.3.6,1.3.7,1.3.8 | BA1,BA2,CRA1,PM1,SA1 | 2 | Task | 14802.4
1.3.2 | Sales - Conduct application design workshop | 1 day | 14 | 22,21 | Mon 1/21/19 | Mon 1/21/19 | 1.3.9,1.3.8 | BA1 | 2 | Task | 1235.2
1.3.3 | Marketing and Development - Conduct application design workshop | 1 day | 14 | 22,21 | Mon 1/21/19 | Mon 1/21/19 | 1.3.9,1.3.8 | BA2 | 2 | Task | 1235.2
1.3.4 | Manufacturing - Conduct application design workshop | 1 day | 14 | 22,21 | Tue 1/22/19 | Tue 1/22/19 | 1.3.9,1.3.8 | BA2 | 2 | Task | 1235.2
1.3.5 | Customer and Vendor Relations - Conduct application design workshop | 1 day | 14 | 22,21 | Wed 1/23/19 | Wed 1/23/19 | 1.3.9,1.3.8 | CRA1 | 2 | Task | 1820.4
1.3.6 | Purchasing and Inventory Management - Conduct application design workshop | 2 days | 14 | 22,21 | Mon 1/21/19 | Tue 1/22/19 | 1.3.9,1.3.8 | SA1 | 2 | Task | 2664
1.3.7 | Accounting - Conduct application design workshop | 2 days | 14 | 22,21 | Mon 1/21/19 | Tue 1/22/19 | 1.3.9,1.3.8 | CRA1 | 2 | Task | 3640.8
1.3.8 | Management and Reporting - Conduct application design workshop #2 | 2 days | 14,15,16,17,18,19,20 | 22 | Thu 1/24/19 | Fri 1/25/19 | 1.3.9 | BA1,BA2,CRA1,PM1,SA1,DS1 | 2 | Task | 16926.72
1.3.9 | System Administration - Conduct application design workshop | 1 day | 15,16,17,18,19,20,21 | 23 | Mon 1/28/19 | Mon 1/28/19 | 1.3.10 | SA1 | 2 | Task | 1332
1.3.10 | Analyze system user requirements gathered from application design workshops | 3 days | 22 | 25,26,28,29,30 | Tue 1/29/19 | Thu 1/31/19 | 1.4.1,1.4.2,1.4.4,1.4.5,1.4.6 | BA1,BA2,CRA1,PM1,SA1,DS1 | 2 | Task | 25390.08
1.4 | Perform feasibility study: | 4 days |  |  | Fri 2/1/19 | Wed 2/6/19 |  |  | 1 | Activity |  | 28812.32
1.4.1 | Analyze the system configuration requirements for scale and interoperability/portability. | 3 days | 23 | 32 | Fri 2/1/19 | Tue 2/5/19 | 1.5.1 | SA1 | 2 | Task | 3996
1.4.2 | Begin a technology trawl to identify hardware and software required to deliver the system | 2 days | 23 | 27 | Fri 2/1/19 | Mon 2/4/19 | 1.4.3 | CRA1 | 2 | Task | 3640.8
1.4.3 | Review and complete technology trawl | 2 days | 26 | 32 | Tue 2/5/19 | Wed 2/6/19 | 1.5.1 | CRA1,SA1 | 2 | Task | 6304.8
1.4.4 | Research and identify services that we might contract with to perform currency tracking | 3 days | 23 | 32FF | Fri 2/1/19 | Tue 2/5/19 | 1.5.1[FF] | BA1,BA2 | 2 | Task | 7411.2
1.4.5 | Research and identify services that we might contract with to perform fax-to-email | 2 days | 23 | 32FF | Fri 2/1/19 | Mon 2/4/19 | 1.5.1[FF] | DS1 | 2 | Task | 2124.32
1.4.6 | Research and identify RFID and barcode labeling requirements and suppliers | 3 days | 23 | 32 | Fri 2/1/19 | Tue 2/5/19 | 1.5.1 | PM1 | 2 | Task | 5335.2
1.5 | Project planning: | 31 days |  |  | Thu 2/7/19 | Thu 3/21/19 |  |  | 1 | Activity |  | 84369.52
1.5.1 | Revisit system requirements, integrating input from the stakeholder analysis and the feasibility study | 4 days | 25,28FF,29FF,30,27 | 33 | Thu 2/7/19 | Tue 2/12/19 | 1.5.2 | PM1,SA1,DS1,CRA1,BA1,BA2 | 2 | Task | 33853.44
1.5.2 | Discuss and agree upon plan scope with key stakeholders | 3 days | 32 | 34 | Wed 2/13/19 | Fri 2/15/19 | 1.5.3 | BA1,DS1,PM1,CRA1 | 2 | Task | 17688.48
1.5.3 | Rearrange interim deliverables, to reflect what we've learned | 1 day | 33 | 35,39FS+2 days | Mon 2/18/19 | Mon 2/18/19 | 1.5.4,2.1[FS+2 days] | PM1 | 2 | Task | 1778.4
1.5.4 | Revise the project plan, resource plan, effort, time and budget estimates and project schedule | 5 days | 34 | 36 | Tue 2/19/19 | Fri 3/1/19 | 1.5.5 | PM1 | 2 | Task | 8892
1.5.5 | Review and agree estimate and timescale changes with upper management | 5 days | 35 | 37 | Thu 3/14/19 | Wed 3/20/19 | 1.5.6 | BA1,DS1,PM1 | 2 | Task | 20378.8
1.5.6 | Revise project plans to accommodate any revisions to scope | 1 day | 36 | 65 | Thu 3/21/19 | Thu 3/21/19 | 2.3.1.1 | PM1 | 2 | Task | 1778.4
2 | Phase I: Develop Basic Integrated Business Management System | 246 days |  |  | Thu 2/21/19 | Thu 1/30/20 |  |  | 0 | Phase |  |  |  | 1825323.2
2.1 | Phase 1 Kickoff Meeting | 2 days | 34FS+2 days | 42,48,56,78,81,75,86,89,93,116,119,122,132 | Thu 2/21/19 | Fri 2/22/19 | 2.2.1.1,2.2.2.1,2.2.4.1,2.4.2.1,2.4.3.1,2.4.1.1,2.5.1.1,2.5.2.1,2.5.3.1,2.8.1.1,2.8.2.1,2.8.3.1,2.9.2.1.1.1 | PM1,PA1,BA1,DBA1,DA1,ST1,SA1,UI1 | 1 | Task | 20708.8
2.2 | Develop Initial System Management Subsystem | 110 days |  |  | Mon 2/25/19 | Fri 7/26/19 |  |  | 1 | Component |  |  | 368178.32
2.2.1 | DBMS: Install & Configure DBMS Engine & SQL Interface | 41 days |  |  | Mon 2/25/19 | Mon 4/22/19 |  |  | 2 | Activity |  | 37620.64
2.2.1.1 | · Installing hardware server | 4 days | 39 | 43 | Mon 2/25/19 | Thu 2/28/19 | 2.2.1.2 | CNS1,PA1 | 3 | Task | 11852.16
2.2.1.2 | · TestNetwork connections | 2 days | 42 | 44 | Fri 3/1/19 | Mon 3/4/19 | 2.2.1.3 | CNS1 | 3 | Task | 3312
2.2.1.3 | · Install & Configure DBMS engine | 2 days | 43 | 45 | Mon 3/11/19 | Tue 3/12/19 | 2.2.1.4 | DA1 | 3 | Task | 3640.8
2.2.1.4 | · Install and test SQL interface software | 4 days | 44 | 46 | Mon 3/25/19 | Thu 3/28/19 | 2.2.1.5 | DBA1 | 3 | Task | 6374.08
2.2.1.5 | · Evaluate the system | 4 days | 45 | 49 | Fri 3/29/19 | Mon 4/22/19 | 2.2.2.2 | PM1,ST1 | 3 | Task | 12441.6
2.2.2 | DBMS: User Accounts and Permissions | 66 days |  |  | Wed 3/13/19 | Wed 6/12/19 |  |  | 2 | Activity |  | 33329.52
2.2.2.1 | · Design database | 2 days | 39 | 49 | Wed 3/13/19 | Thu 3/14/19 | 2.2.2.2 | DA1 | 3 | Task | 3640.8
2.2.2.2 | · Implement and test database structure | 3 days | 46,48 | 50,52 | Tue 4/23/19 | Thu 4/25/19 | 2.2.2.3,2.2.3.1 | DA1,ST1 | 3 | Task | 9457.2
2.2.2.3 | · Test accounts | 6 days | 49 | 62 | Fri 4/26/19 | Wed 6/12/19 | 2.2.5.4 | DBA1,PM1 | 3 | Task | 20231.52
2.2.3 | Server App: System management and security application | 46 days |  |  | Fri 4/26/19 | Fri 6/28/19 |  |  | 2 | Activity |  | 64476.8
2.2.3.1 | · Software requirements analysis | 8 days | 49 | 53 | Fri 4/26/19 | Tue 5/7/19 | 2.2.3.2 | BA1 | 3 | Task | 9881.6
2.2.3.2 | ·Software design | 16 days | 52 | 54 | Wed 5/8/19 | Mon 6/24/19 | 2.2.3.3 | PA1,PM1 | 3 | Task | 49367.04
2.2.3.3 | · Development & coding | 4 days | 53 | 62 | Tue 6/25/19 | Fri 6/28/19 | 2.2.5.4 | PA2 | 3 | Task | 5228.16
2.2.4 | Client App: System management application | 22 days |  |  | Mon 2/25/19 | Tue 3/26/19 |  |  | 2 | Activity |  | 62928.16
2.2.4.1 | · Software requirements analysis | 13 days | 39 | 57 | Mon 2/25/19 | Wed 3/13/19 | 2.2.4.2 | PM1,BA1 | 3 | Task | 39176.8
2.2.4.2 | · Software design & code | 9 days | 56 | 59 | Thu 3/14/19 | Tue 3/26/19 | 2.2.5.1 | PA1,SA1 | 3 | Task | 23751.36
2.2.5 | Integrated User Interface: Provide integrated GUI to implement basic access stubs for all client apps. In Phase 1 | 88 days |  |  | Wed 3/27/19 | Fri 7/26/19 |  |  | 2 | Activity |  | 169823.2
2.2.5.1 | · User navigation requirements analysis | 17 days | 57 | 60 | Wed 3/27/19 | Thu 4/18/19 | 2.2.5.2 | UI1,PM1 | 3 | Task | 50480.48
2.2.5.2 | · UI design & scripting | 12 days | 59 | 61 | Fri 4/19/19 | Mon 5/6/19 | 2.2.5.3 | UI1,PA1 | 3 | Task | 29976.96
2.2.5.3 | · UI documentation and acceptance test | 12 days | 60 | 62 | Tue 5/7/19 | Wed 5/22/19 | 2.2.5.4 | UI1,PA2 | 3 | Task | 29976.96
2.2.5.4 | · Subsystem/component integration test & documentation | 20 days | 50,61,54 | 127 | Mon 7/1/19 | Fri 7/26/19 | 2.9.1.1 | PM1,UI1 | 3 | Task | 59388.8
2.3 | Develop Knowledge Management and Training subsystem | 88 days |  |  | Fri 3/22/19 | Tue 7/23/19 |  |  | 1 | Component |  |  | 213907.52
2.3.1 | DBMS: Knowledgebase database | 18 days |  |  | Fri 3/22/19 | Tue 4/16/19 |  |  | 2 | Activity |  | 58045.6
2.3.1.1 | · Design database | 8 days | 37 | 66 | Fri 3/22/19 | Tue 4/2/19 | 2.3.1.2 | PM1,DA1 | 3 | Task | 28790.4
2.3.1.2 | · Implement and test database structures | 10 days | 65 | 68 | Wed 4/3/19 | Tue 4/16/19 | 2.3.2.1 | DBA1,ST1 | 3 | Task | 29255.2
2.3.2 | Server App: Knowledgebase and Training Manual | 30 days |  |  | Wed 4/17/19 | Tue 5/28/19 |  |  | 2 | Activity |  | 79738.56
2.3.2.1 | · Software requirements analysis | 18 days | 66 | 69 | Wed 4/17/19 | Wed 5/15/19 | 2.3.2.2 | PM1,SA1 | 3 | Task | 55987.2
2.3.2.2 | · Software design& code | 9 days | 68 | 71 | Thu 5/16/19 | Tue 5/28/19 | 2.3.3.1 | PA1,SA1 | 3 | Task | 23751.36
2.3.3 | Client App: Training Manual and Knowledgebase application | 40 days |  |  | Wed 5/29/19 | Tue 7/23/19 |  |  | 2 | Activity |  | 76123.36
2.3.3.1 | · Software requirements analysis | 13 days | 69 | 72 | Wed 5/29/19 | Wed 7/3/19 | 2.3.3.2 | PM1,BA1 | 3 | Task | 39176.8
2.3.3.2 | · Software design& code | 14 days | 71 | 127 | Thu 7/4/19 | Tue 7/23/19 | 2.9.1.1 | PA1,SA1 | 3 | Task | 36946.56
2.4 | Develop Order Processing & Invoicing subsystem | 83 days |  |  | Mon 2/25/19 | Wed 6/19/19 |  |  | 1 | Component |  |  | 100402.56
2.4.1 | DBMS: Orders & Invoicing Database – Full implementation | 4 days |  |  | Mon 2/25/19 | Thu 2/28/19 |  |  | 2 | Activity |  | 13048.64
2.4.1.1 | · Design database | 2 days | 39 | 76,97 | Mon 2/25/19 | Tue 2/26/19 | 2.4.1.2,2.6.1.1 | DA1,PM1 | 3 | Task | 7197.6
2.4.1.2 | · Implement and test database structures | 2 days | 75 | 79 | Wed 2/27/19 | Thu 2/28/19 | 2.4.2.2 | DBA1,ST1 | 3 | Task | 5851.04
2.4.2 | Server App: Billing/Invoicing | 8 days |  |  | Mon 2/25/19 | Wed 3/6/19 |  |  | 2 | Activity |  | 10556.16
2.4.2.1 | · Software requirements analysis | 4 days | 39 | 79 | Mon 2/25/19 | Thu 2/28/19 | 2.4.2.2 | SA1 | 3 | Task | 5328
2.4.2.2 | · Software design & code | 4 days | 76,78 | 82 | Fri 3/1/19 | Wed 3/6/19 | 2.4.3.2 | PA2 | 3 | Task | 5228.16
2.4.3 | Client App: Sales | 65 days |  |  | Thu 3/21/19 | Wed 6/19/19 |  |  | 2 | Activity |  | 76797.76
2.4.3.1 | · Software requirements analysis | 16 days | 39 | 82 | Thu 3/21/19 | Thu 5/2/19 | 2.4.3.2 | PM1,BA1 | 3 | Task | 48217.6
2.4.3.2 | · Software design & code | 6 days | 81,79 | 83 | Tue 5/7/19 | Mon 6/3/19 | 2.4.3.3 | PA1,SA1 | 3 | Task | 15834.24
2.4.3.3 | · Subsystem/component integration test & documentation | 12 days | 82 | 127 | Tue 6/4/19 | Wed 6/19/19 | 2.9.1.1 | DS1 | 3 | Task | 12745.92
2.5 | Develop Billing/Accounting subsystem | 128 days |  |  | Wed 4/3/19 | Fri 9/27/19 |  |  | 1 | Component |  |  | 181944.08
2.5.1 | DBMS: Budgeting and Accounting | 51 days |  |  | Wed 4/3/19 | Wed 6/12/19 |  |  | 2 | Activity |  | 30369.36
2.5.1.1 | · Design database | 6 days | 39,98 | 87 | Wed 4/3/19 | Fri 6/7/19 | 2.5.1.2 | DA1,PM1 | 3 | Task | 21592.8
2.5.1.2 | · Implement and test database structures | 3 days | 86 | 90 | Mon 6/10/19 | Wed 6/12/19 | 2.5.2.2 | DBA1,ST1 | 3 | Task | 8776.56
2.5.2 | Server App: Billing/Invoicing | 60 days |  |  | Thu 4/18/19 | Wed 7/10/19 |  |  | 2 | Activity |  | 64861.76
2.5.2.1 | · Software requirements analysis | 8 days | 39 | 90,93 | Thu 4/18/19 | Thu 5/9/19 | 2.5.2.2,2.5.3.1 | BA1 | 3 | Task | 9881.6
2.5.2.2 | · Software design & code | 4 days | 87,89 | 91,94 | Thu 6/13/19 | Tue 6/18/19 | 2.5.2.3,2.5.3.2 | SA1,PA2 | 3 | Task | 10556.16
2.5.2.3 | · Unit test | 10 days | 90 | 127 | Wed 6/19/19 | Wed 7/10/19 | 2.9.1.1 | ST1,PM1,STE1 | 3 | Task | 44424
2.5.3 | Client App: Accounting | 43 days |  |  | Wed 7/31/19 | Fri 9/27/19 |  |  | 2 | Activity |  | 86712.96
2.5.3.1 | · Software requirements analysis | 16 days | 39,89 | 94 | Wed 7/31/19 | Fri 8/30/19 | 2.5.3.2 | PM1,SA1 | 3 | Task | 49766.4
2.5.3.2 | · Software design & code | 14 days | 93,90 | 107 | Mon 9/2/19 | Fri 9/27/19 | 2.7.1.1 | PA1,SA1 | 3 | Task | 36946.56
2.6 | Develop Interface and Security for Supplier Web UI | 107 days |  |  | Wed 2/27/19 | Thu 7/25/19 |  |  | 1 | Component |  |  | 275518.56
2.6.1 | DBMS: Update Orders and Invoicing Database – add quotations table | 18 days |  |  | Wed 2/27/19 | Fri 3/22/19 |  |  | 2 | Activity |  | 43818.4
2.6.1.1 | · Design database | 8 days | 75 | 98 | Wed 2/27/19 | Fri 3/8/19 | 2.6.1.2 | DA1 | 3 | Task | 14563.2
2.6.1.2 | · Implement and test database structures | 10 days | 97 | 100,86 | Mon 3/11/19 | Fri 3/22/19 | 2.6.2.1,2.5.1.1 | ST1,DBA1 | 3 | Task | 29255.2
2.6.2 | Server App: Purchasing/Inventory | 35 days |  |  | Mon 3/25/19 | Fri 5/10/19 |  |  | 2 | Activity |  | 91360.64
2.6.2.1 | · Software requirements analysis | 14 days | 98 | 101 | Mon 3/25/19 | Thu 4/11/19 | 2.6.2.2 | SA1,BA1 | 3 | Task | 35940.8
2.6.2.2 | · Software design& code | 21 days | 100 | 103 | Fri 4/12/19 | Fri 5/10/19 | 2.6.3.1 | SA1,PA2 | 3 | Task | 55419.84
2.6.3 | Client App: Supplier Web UI | 54 days |  |  | Mon 5/13/19 | Thu 7/25/19 |  |  | 2 | Activity |  | 140339.52
2.6.3.1 | · Software requirements analysis | 24 days | 101 | 104 | Mon 5/13/19 | Thu 6/13/19 | 2.6.3.2 | SA1,BA1,UI1 | 3 | Task | 90197.76
2.6.3.2 | · Software design& code | 19 days | 103 | 127 | Fri 6/14/19 | Thu 7/25/19 | 2.9.1.1 | PA1,SA1 | 3 | Task | 50141.76
2.7 | Develop Currency prediction and Conversion subsystem | 66 days |  |  | Mon 9/30/19 | Mon 12/30/19 |  |  | 1 | Component |  |  | 114782.4
2.7.1 | Server App: API to Vendor currency database | 66 days |  |  | Mon 9/30/19 | Mon 12/30/19 |  |  | 2 | Activity |  | 114782.4
2.7.1.1 | - Software requirements analysis | 6 days | 94 | 108 | Mon 9/30/19 | Fri 10/11/19 | 2.7.1.2 | PM1,BA1 | 3 | Task | 18081.6
2.7.1.2 | - Software design & code | 5 days | 107 | 110 | Mon 10/14/19 | Fri 10/18/19 | 2.7.1.3.1 | PA1,SA1 | 3 | Task | 13195.2
2.7.1.3 | Review Currency Prediction and Conversion subsystem | 51 days |  |  | Mon 10/21/19 | Mon 12/30/19 |  |  | 3 | Activity |  | 83505.6
2.7.1.3.1 | · Integration and regression testing for each component | 10 days | 108 | 111 | Mon 10/21/19 | Fri 11/1/19 | 2.7.1.3.2 | ST1,PM1 | 4 | Task | 31104
2.7.1.3.2 | · Validate and test results | 10 days | 110 | 112 | Mon 11/4/19 | Fri 11/15/19 | 2.7.1.3.3 | ST1 | 4 | Task | 13320
2.7.1.3.3 | · UAT | 10 days | 111 | 113 | Mon 11/18/19 | Fri 12/6/19 | 2.7.1.3.4 | STE1,ST1 | 4 | Task | 26640
2.7.1.3.4 | · Sign-off | 4 days | 112 | 158 | Mon 12/9/19 | Mon 12/30/19 | 2.10.4.2 | STE1,PM1 | 4 | Task | 12441.6
2.8 | Develop Inventory management subsystem | 158 days |  |  | Fri 3/1/19 | Tue 10/8/19 |  |  | 1 | Component |  |  | 176231.84
2.8.1 | DBMS: Resources & Inventory Database | 78 days |  |  | Fri 3/15/19 | Tue 7/2/19 |  |  | 2 | Activity |  | 25588.8
2.8.1.1 | · Design database | 6 days | 39 | 117 | Fri 3/15/19 | Thu 6/27/19 | 2.8.1.2 | DA1,PM1 | 3 | Task | 21592.8
2.8.1.2 | · Implement and test database structures | 3 days | 116 | 119 | Fri 6/28/19 | Tue 7/2/19 | 2.8.2.1 | STE1 | 3 | Task | 3996
2.8.2 | Server App: Purchasing & Inventory Management | 20 days |  |  | Wed 7/3/19 | Tue 7/30/19 |  |  | 2 | Activity |  | 25715.84
2.8.2.1 | · Software requirements analysis | 8 days | 39117 | 120 | Wed 7/3/19 | Fri 7/12/19 | 2.8.2.2 | BA1 | 3 | Task | 9881.6
2.8.2.2 | · Software design & code | 6 days | 119 | 124 | Mon 7/15/19 | Tue 7/30/19 | 2.8.3.3 | SA1,PA2 | 3 | Task | 15834.24
2.8.3 | Client App: Inventory Management | 158 days |  |  | Fri 3/1/19 | Tue 10/8/19 |  |  | 2 | Activity |  | 124927.2
2.8.3.1 | · Software requirements analysis | 10 days | 39 | 123 | Fri 3/1/19 | Wed 6/19/19 | 2.8.3.2 | SA1 | 3 | Task | 13320
2.8.3.2 | · Software design & code | 10 days | 122 | 127 | Thu 6/20/19 | Fri 7/12/19 | 2.9.1.1 | SA1,PA1 | 3 | Task | 26390.4
2.8.3.3 | · Subsystem/component integration test & documentation | 30 days | 120 | 144 | Wed 7/31/19 | Tue 10/8/19 | 2.10.1.1.1 | DS1,PM1 | 3 | Task | 85216.8
2.9 | Develop System Management Subsystem (advanced functions) | 192 days |  |  | Mon 2/25/19 | Tue 11/19/19 |  |  | 1 | Component |  |  | 274305.84
2.9.1 | DBMS: Logging & Audit Trail for Phase I functions. | 24 days |  |  | Mon 7/29/19 | Thu 8/29/19 |  |  | 2 | Activity |  | 59169.6
2.9.1.1 | · Design database | 12 days | 62,83,123,72,91,104 | 128 | Mon 7/29/19 | Tue 8/13/19 | 2.9.1.2 | DA1,PM1 | 3 | Task | 43185.6
2.9.1.2 | · Implement and test database structures | 12 days | 127 | 134 | Wed 8/14/19 | Thu 8/29/19 | 2.9.2.1.2 | STE1 | 3 | Task | 15984
2.9.2 | GUI & front-end menu implementation | 192 days |  |  | Mon 2/25/19 | Tue 11/19/19 |  |  | 2 | Activity |  | 215136.24
2.9.2.1 | Client App: Integrated user-navigation/access | 161 days |  |  | Mon 2/25/19 | Mon 10/7/19 |  |  | 3 | Subcomponent
2.9.2.1.1 | · Software requirements analysis | 137 days |  |  | Mon 2/25/19 | Tue 9/3/19 |  |  | 4 | Task
2.9.2.1.1.1 | · Requirment gathering | 28 days | 39 | 133 | Mon 2/25/19 | Tue 8/20/19 | 2.9.2.1.1.2 | PM1,DS1 | 5 | Subtask | 79535.68
2.9.2.1.1.2 | · Requirment analysis phase | 10 days | 132 | 134 | Wed 8/21/19 | Tue 9/3/19 | 2.9.2.1.2 | BA1 | 5 | Subtask | 12352
2.9.2.1.2 | · Software design & code | 12 days | 133128 | 135 | Wed 9/4/19 | Thu 9/19/19 | 2.9.2.1.3 | PA2,PA1 | 4 | Task | 31368.96
2.9.2.1.3 | · Subsystem/component integration test & documentation | 12 days | 134 | 140137 | Fri 9/20/19 | Mon 10/7/19 | 2.9.2.2.4,2.9.2.2.1 | DS1,PM1 | 4 | Task | 34086.72
2.9.2.2 | Client App: Provide advanced GUI to implement user menus and login form for UI client app. | 31 days |  |  | Tue 10/8/19 | Tue 11/19/19 |  |  | 3 | Subcomponent
2.9.2.2.1 | · User navigation requirements analysis | 8 days | 135 | 138 | Tue 10/8/19 | Thu 10/17/19 | 2.9.2.2.2 | UI1 | 4 | Task | 9528.32
2.9.2.2.2 | · UI design & scripting | 9 days | 137 | 139 | Fri 10/18/19 | Wed 10/30/19 | 2.9.2.2.3 | UI1 | 4 | Task | 10719.36
2.9.2.2.3 | · GUI unit tests | 7 days | 138 | 140 | Thu 10/31/19 | Fri 11/8/19 | 2.9.2.2.4 | UI1,STE1 | 4 | Task | 17661.28
2.9.2.2.4 | · UI documentation and acceptance test | 7 days | 135139 | 144 | Mon 11/11/19 | Tue 11/19/19 | 2.10.1.1.1 | DS1,PM1 | 4 | Task | 19883.92
2.10 | Phase I Delivery Activities | 52 days |  |  | Wed 11/20/19 | Thu 1/30/20 |  |  | 1 | Component |  |  | 99343.28
2.10.1 | Phase I Integration Test | 12 days |  |  | Wed 11/20/19 | Thu 12/5/19 |  |  | 2 | Activity |  | 15834.24
2.10.1.1 | · Integration test of Phase I software components | 12 days |  |  | Wed 11/20/19 | Thu 12/5/19 |  |  | 3 | Task
2.10.1.1.1 | · Redesign and rework following integration tests | 6 days | 140124 | 145 | Wed 11/20/19 | Wed 11/27/19 | 2.10.1.1.2 | PA1 | 4 | Subtask | 7842.24
2.10.1.1.2 | · Phase I software documentation and acceptance test | 6 days | 144 | 147160 | Thu 11/28/19 | Thu 12/5/19 | 2.10.2.1,3.1 | ST1 | 4 | Subtask | 7992
2.10.2 | Phase IChange management | 13 days |  |  | Tue 12/10/19 | Thu 12/26/19 |  |  | 2 | Activity |  | 28052.8
2.10.2.1 | · Training on new work procedures | 4 days | 145 | 148 | Tue 12/10/19 | Fri 12/13/19 | 2.10.2.2 | PM1,SA1 | 3 | Task | 12441.6
2.10.2.2 | · Business process changes | 4 days | 147 | 149 | Mon 12/16/19 | Tue 12/24/19 | 2.10.2.3 | BA1,PM1 | 3 | Task | 12054.4
2.10.2.3 | · User system training | 2 days | 148 | 151 | Wed 12/25/19 | Thu 12/26/19 | 2.10.3.1 | PM1 | 3 | Task | 3556.8
2.10.3 | New process & systems evaluation | 17 days |  |  | Fri 12/27/19 | Mon 1/20/20 |  |  | 2 | Activity |  | 41229.04
2.10.3.1 | · Phase I systems installation | 7 days | 149 | 152 | Fri 12/27/19 | Mon 1/6/20 | 2.10.3.2 | BA1,SA1 | 3 | Task | 17970.4
2.10.3.2 | · Phase I Testing | 6 days | 151 | 153 | Tue 1/7/20 | Tue 1/14/20 | 2.10.3.3 | STE1,ST1 | 3 | Task | 15984
2.10.3.3 | · Phase ISystem Documentation | 2 days | 152 | 154 | Wed 1/15/20 | Thu 1/16/20 | 2.10.3.4 | DS1 | 3 | Task | 2124.32
2.10.3.4 | · Phase I User evaluation | 1 day | 153 | 155 | Fri 1/17/20 | Fri 1/17/20 | 2.10.3.5 | PM1,DBA1 | 3 | Task | 3371.92
2.10.3.5 | · Evaluatethefeedback | 1 day | 154 | 157 | Mon 1/20/20 | Mon 1/20/20 | 2.10.4.1 | PM1 | 3 | Task | 1778.4
2.10.4 | Project Review | 8 days |  |  | Tue 1/21/20 | Thu 1/30/20 |  |  | 2 | Activity |  | 14227.2
2.10.4.1 | · Project plan review for Phase I | 4 days | 155 | 158 | Tue 1/21/20 | Fri 1/24/20 | 2.10.4.2 | PM1 | 3 | Task | 7113.6
2.10.4.2 | · Management approval and signoff for Phase I | 4 days | 157113 | 177 | Mon 1/27/20 | Thu 1/30/20 | 3.4.1.1 | PM1 | 3 | Task | 7113.6
3 | Phase II: Develop Advanced Integrated Business Management System | 177 days |  |  | Fri 12/6/19 | Mon 8/10/20 |  |  | 0 | Phase |  |  |  | 394102.24
3.1 | Phase 2 Kickoff Meeting | 2 days | 145 | 162163167177 | Fri 12/6/19 | Mon 12/9/19 | 3.2.1,3.2.2,3.3.1.1,3.4.1.1 | BA1,DBA1,DS1,PA1,PM1,SA1,UI1 | 1 | Task | 16528.32
3.2 | Phase 1 follow up | 6 days |  |  | Mon 12/16/19 | Mon 12/23/19 |  |  | 1 | Component |  |  | 16787.2
3.2.1 | Review Phase I software components | 5 days | 160 | 164 | Mon 12/16/19 | Fri 12/20/19 | 3.2.3 | PM1 | 2 | Task | 8892
3.2.2 | Review Phase I hardware components | 5 days | 160 | 174 | Mon 12/16/19 | Fri 12/20/19 | 3.3.3 | SA1 | 2 | Task | 6660
3.2.3 | Upgrade the software requirements | 1 day | 162 | 181171 | Mon 12/23/19 | Mon 12/23/19 | 3.4.2.1,3.3.2.1 | BA1 | 2 | Task | 1235.2
3.3 | Upgrade System Management Subsystem (Basic) | 46 days |  |  | Tue 12/10/19 | Tue 2/11/20 |  |  | 1 | Component |  |  | 52273.6
3.3.1 | Server App: Upgraded system management and security management | 29 days |  |  | Tue 12/10/19 | Fri 1/17/20 |  |  | 2 | Activity |  | 19246.4
3.3.1.1 | - Software requirements analysis | 5 days | 160 | 168 | Tue 12/10/19 | Mon 12/16/19 | 3.3.1.2 | BA1 | 3 | Task | 6176
3.3.1.2 | - Software design | 5 days | 167 | 169 | Tue 12/17/19 | Fri 1/10/20 | 3.3.1.3 | PA2 | 3 | Task | 6535.2
3.3.1.3 | - Software code | 5 days | 168 |  | Mon 1/13/20 | Fri 1/17/20 |  | PA2 | 3 | Task | 6535.2
3.3.2 | Client App: System management and security integration | 24 days |  |  | Tue 1/7/20 | Fri 2/7/20 |  |  | 2 | Activity |  | 30363.2
3.3.2.1 | - Software requirements analysis | 14 days | 164 | 172 | Tue 1/7/20 | Fri 1/24/20 | 3.3.2.2 | BA1 | 3 | Task | 17292.8
3.3.2.2 | - Software design | 5 days | 171 | 173 | Mon 1/27/20 | Fri 1/31/20 | 3.3.2.3 | PA2 | 3 | Task | 6535.2
3.3.2.3 | - Software code | 5 days | 172 | 174 | Mon 2/3/20 | Fri 2/7/20 | 3.3.3 | PA1 | 3 | Task | 6535.2
3.3.3 | Subsystem integration testing | 2 days | 173163 | 2.4122e+17 | Mon 2/10/20 | Tue 2/11/20 | 3.9.2.1,3.7.1.1,3.6.1.1,3.6.2.1,3.6.3.1,3.6.4.1 | STE1 | 2 | Task | 2664
3.4 | Develop Operations Management & Reporting subsystem | 75 days |  |  | Tue 12/24/19 | Mon 4/6/20 |  |  | 1 | Component |  |  | 58817.84
3.4.1 | DBMS: Sales and Market | 37 days |  |  | Fri 1/31/20 | Mon 3/23/20 |  |  | 2 | Activity |  | 35959.6
3.4.1.1 | - Design database by creating tables, developing packages and integrating with the server application | 10 days | 158160 | 178 | Fri 1/31/20 | Tue 2/25/20 | 3.4.1.2 | DBA1 | 3 | Task | 15935.2
3.4.1.2 | - Implement and test database structures | 6 days | 177 | 179194 | Fri 2/28/20 | Fri 3/6/20 | 3.4.1.3,3.5.1.1 | DA1 | 3 | Task | 10922.4
3.4.1.3 | - Gather information regarding previous sales and market demands. | 5 days | 178 | 187 | Tue 3/17/20 | Mon 3/23/20 | 3.4.3.2.1 | DA1 | 3 | Task | 9102
3.4.2 | Server App: Sales Analysis and Reporting | 13 days |  |  | Tue 12/24/19 | Thu 1/9/20 |  |  | 2 | Activity |  | 7483.04
3.4.2.1 | - Software requirements analysis | 5 days | 164 | 183194 | Tue 12/24/19 | Wed 1/8/20 | 3.4.2.2.1,3.5.1.1 | BA1 | 3 | Task | 6176
3.4.2.2 | - Software design & code | 1 day |  |  | Thu 1/9/20 | Thu 1/9/20 |  |  | 3 | Task
3.4.2.2.1 | - Write a program to display the analysis using charts and graphs for easy understanding. | 1 day | 181 | 185 | Thu 1/9/20 | Thu 1/9/20 | 3.4.3.1 | PA2 | 4 | Subtask | 1307.04
3.4.3 | Client App: Management and Reporting | 60 days |  |  | Fri 1/10/20 | Thu 4/2/20 |  |  | 2 | Activity |  | 12711.2
3.4.3.1 | - Software requirements analysis | 5 days | 183 | 187 | Fri 1/10/20 | Thu 1/16/20 | 3.4.3.2.1 | BA1 | 3 | Task | 6176
3.4.3.2 | - Software design & code | 5 days |  |  | Fri 3/27/20 | Thu 4/2/20 |  |  | 3 | Task
3.4.3.2.1 | - Develop a user friendly UI that shows the graph and charts of sales against time duration and scale. | 1 day | 185179 | 188 | Fri 3/27/20 | Fri 3/27/20 | 3.4.3.2.2 | PA1 | 4 | Subtask | 1307.04
3.4.3.2.2 | - Application used to report | 2 days | 187 | 189 | Mon 3/30/20 | Tue 3/31/20 | 3.4.3.2.3 | PA1 | 4 | Subtask | 2614.08
3.4.3.2.3 | - Develop the GUI | 1 day | 188 | 190 | Wed 4/1/20 | Wed 4/1/20 | 3.4.3.2.4 | PA1 | 4 | Subtask | 1307.04
3.4.3.2.4 | - Unit testing of GUI | 1 day | 189 | 191 | Thu 4/2/20 | Thu 4/2/20 | 3.4.4 | PA1 | 4 | Subtask | 1307.04
3.4.4 | Subsystem integration testing | 2 days | 190 | 241 | Fri 4/3/20 | Mon 4/6/20 | 3.9.2.1 | STE1 | 2 | Task | 2664
3.5 | Develop Forecasting and Analysis subsystem | 26 days |  |  | Mon 3/9/20 | Mon 4/13/20 |  |  | 1 | Component |  |  | 25551.2
3.5.1 | DBMS: Update Sales and Market Database – add forecasting & analysis table | 2 days |  |  | Mon 3/9/20 | Tue 3/10/20 |  |  | 2 | Activity |  | 3640.8
3.5.1.1 | - Implement and test database structures | 2 days | 181178 | 196 | Mon 3/9/20 | Tue 3/10/20 | 3.5.2.1 | DA1 | 3 | Task | 3640.8
3.5.2 | Server App: Demand Forecasting | 22 days |  |  | Wed 3/11/20 | Thu 4/9/20 |  |  | 2 | Activity |  | 19246.4
3.5.2.1 | - Software requirements analysis | 5 days | 194 | 197 | Wed 3/11/20 | Tue 3/17/20 | 3.5.2.2 | BA1 | 3 | Task | 6176
3.5.2.2 | - Software design | 5 days | 196 | 198 | Thu 3/19/20 | Thu 3/26/20 | 3.5.2.3 | PA1 | 3 | Task | 6535.2
3.5.2.3 | - Software code | 5 days | 197 | 199 | Fri 4/3/20 | Thu 4/9/20 | 3.5.3 | PA1 | 3 | Task | 6535.2
3.5.3 | Subsystem integration testing | 2 days | 198 | 241 | Fri 4/10/20 | Mon 4/13/20 | 3.9.2.1 | STE1 | 2 | Task | 2664
3.6 | Develop Product code database and Lookup subsystem | 16 days |  |  | Wed 2/12/20 | Wed 3/4/20 |  |  | 1 | Component |  |  | 46798.4
3.6.1 | DBMS: Product Management (only product code-related tables) | 12 days |  |  | Wed 2/12/20 | Thu 2/27/20 |  |  | 2 | Activity |  | 20029.76
3.6.1.1 | - Design database by creating tables, developing packages and integrating with the server application | 8 days | 174 | 203 | Wed 2/12/20 | Fri 2/21/20 | 3.6.1.2 | DBA1 | 3 | Task | 12748.16
3.6.1.2 | - Implement and test database structures | 4 days | 202 | 206 | Mon 2/24/20 | Thu 2/27/20 | 3.6.2.2 | DA1 | 3 | Task | 7281.6
3.6.2 | Server App: Marketing and Development (functions related to product code) | 11 days |  |  | Mon 2/17/20 | Mon 3/2/20 |  |  | 2 | Activity |  | 6319.68
3.6.2.1 | - Software requirements analysis | 3 days | 174 | 206 | Mon 2/17/20 | Wed 2/19/20 | 3.6.2.2 | BA1 | 3 | Task | 3705.6
3.6.2.2 | - Software design & code | 2 days | 205203 | 214 | Fri 2/28/20 | Mon 3/2/20 | 3.6.5 | PA1 | 3 | Task | 2614.08
3.6.3 | Client App: Marketing and Development Application (functions related to product code) | 9 days |  |  | Wed 2/12/20 | Mon 2/24/20 |  |  | 2 | Activity |  | 8801.28
3.6.3.1 | - Software requirements analysis | 3 days | 174 | 209 | Wed 2/12/20 | Fri 2/14/20 | 3.6.3.2 | UI1 | 3 | Task | 3573.12
3.6.3.2 | - Software design & code | 4 days | 208 | 214 | Wed 2/19/20 | Mon 2/24/20 | 3.6.5 | PA1 | 3 | Task | 5228.16
3.6.4 | Service: Product code lookup service | 7 days |  |  | Wed 2/12/20 | Thu 2/20/20 |  |  | 2 | Activity |  | 8983.68
3.6.4.1 | - Software requirements analysis | 3 days | 174 | 212 | Wed 2/12/20 | Fri 2/14/20 | 3.6.4.2 | BA1 | 3 | Task | 3705.6
3.6.4.2 | - Software design & code | 2 days | 211 | 213 | Mon 2/17/20 | Tue 2/18/20 | 3.6.4.3 | PA1 | 3 | Task | 2614.08
3.6.4.3 | - Integration testing | 2 days | 212 | 214 | Wed 2/19/20 | Thu 2/20/20 | 3.6.5 | ST1 | 3 | Task | 2664
3.6.5 | Subsystem integration testing | 2 days | 213206209 | 241222 | Tue 3/3/20 | Wed 3/4/20 | 3.9.2.1,3.8.1.1 | STE1 | 2 | Task | 2664
3.7 | Develop Currency prediction and Conversion subsystem | 7 days |  |  | Thu 2/20/20 | Fri 2/28/20 |  |  | 1 | Component |  |  | 8983.68
3.7.1 | Server App: API to Vendor currency database | 5 days |  |  | Thu 2/20/20 | Wed 2/26/20 |  |  | 2 | Activity |  | 6319.68
3.7.1.1 | - Software requirements analysis | 3 days | 174 | 218 | Thu 2/20/20 | Mon 2/24/20 | 3.7.1.2 | BA1 | 3 | Task | 3705.6
3.7.1.2 | - Software design & code | 2 days | 217 | 219 | Tue 2/25/20 | Wed 2/26/20 | 3.7.2 | PA1 | 3 | Task | 2614.08
3.7.2 | Subsystem integration testing | 2 days | 218 | 241 | Thu 2/27/20 | Fri 2/28/20 | 3.9.2.1 | STE1 | 2 | Task | 2664
3.8 | Upgrade System Management Subsystem (advanced functions) | 17 days |  |  | Thu 3/5/20 | Fri 3/27/20 |  |  | 1 | Component |  |  | 27459.76
3.8.1 | DBMS: Logging & Audit Trail for Phase II functions. | 6 days |  |  | Thu 3/5/20 | Thu 3/12/20 |  |  | 2 | Activity |  | 10014.88
3.8.1.1 | - Design database by creating tables, developing packages and integrating with the server application | 4 days | 214 | 223 | Thu 3/5/20 | Tue 3/10/20 | 3.8.1.2 | DBA1 | 3 | Task | 6374.08
3.8.1.2 | - Implement and test database structures | 2 days | 222 | 225 | Wed 3/11/20 | Thu 3/12/20 | 3.8.2.1 | DA1 | 3 | Task | 3640.8
3.8.2 | DBMS: Permissions for Phase II functions. | 2 days |  |  | Fri 3/13/20 | Mon 3/16/20 |  |  | 2 | Activity |  | 3640.8
3.8.2.1 | - Update database | 1 day | 223 | 226228 | Fri 3/13/20 | Fri 3/13/20 | 3.8.2.2,3.8.3.1 | DA1 | 3 | Task | 1820.4
3.8.2.2 | - Implement and test database structures | 1 day | 225 | 229 | Mon 3/16/20 | Mon 3/16/20 | 3.8.3.2 | DA1 | 3 | Task | 1820.4
3.8.3 | Server App: Upgraded system management and security application for Phase II functions | 3 days |  |  | Mon 3/16/20 | Wed 3/18/20 |  |  | 2 | Activity |  | 3777.44
3.8.3.1 | - Software requirements analysis | 2 days | 225 | 229 | Mon 3/16/20 | Tue 3/17/20 | 3.8.3.2 | BA1 | 3 | Task | 2470.4
3.8.3.2 | - Software design & code | 1 day | 228226 | 231 | Wed 3/18/20 | Wed 3/18/20 | 3.8.4.1 | PA1 | 3 | Task | 1307.04
3.8.4 | Client App: user-navigation/access and reporting for Phase II Enhancements | 2 days |  |  | Thu 3/19/20 | Fri 3/20/20 |  |  | 2 | Activity |  | 2542.24
3.8.4.1 | - Software requirements analysis | 1 day | 229 | 232 | Thu 3/19/20 | Thu 3/19/20 | 3.8.4.2 | BA1 | 3 | Task | 1235.2
3.8.4.2 | - Software design & code | 1 day | 231 | 234 | Fri 3/20/20 | Fri 3/20/20 | 3.8.5.1 | PA1 | 3 | Task | 1307.04
3.8.5 | Client app: Provide advanced GUI to implement user menus and login form for UI client app. (Phase II) | 3 days |  |  | Mon 3/23/20 | Wed 3/25/20 |  |  | 2 | Activity |  | 4820.4
3.8.5.1 | - User navigation requirements analysis | 1 day | 232 | 235 | Mon 3/23/20 | Mon 3/23/20 | 3.8.5.2 | BA1 | 3 | Task | 1235.2
3.8.5.2 | - UI design & scripting | 1 day | 234 | 236 | Tue 3/24/20 | Tue 3/24/20 | 3.8.5.3 | UI1 | 3 | Task | 1191.04
3.8.5.3 | - UI documentation and acceptance test | 1 day | 235 | 237 | Wed 3/25/20 | Wed 3/25/20 | 3.8.6 | DS1,ST1 | 3 | Task | 2394.16
3.8.6 | Subsystem integration testing | 2 days | 236 | 239 | Thu 3/26/20 | Fri 3/27/20 | 3.9.1 | STE1 | 2 | Task | 2664
3.9 | Phase II Delivery Activities | 87 days |  |  | Fri 4/10/20 | Mon 8/10/20 |  |  | 1 | Component |  |  | 140902.24
3.9.1 | Integrate all the software components developed. | 4 days | 237 | 241 | Fri 4/10/20 | Wed 4/15/20 | 3.9.2.1 | PA1 | 2 | Task | 5228.16
3.9.2 | Phase II Integration Test | 26 days |  |  | Thu 4/16/20 | Thu 5/21/20 |  |  | 2 | Activity |  | 43129.28
3.9.2.1 | - Integration test of Phase II software components | 8 days | 2.3922e+17 | 242 | Thu 4/16/20 | Mon 4/27/20 | 3.9.2.2 | ST1 | 3 | Task | 10656
3.9.2.2 | - Redesign and rework following integration tests | 10 days | 241 | 243 | Tue 4/28/20 | Mon 5/11/20 | 3.9.2.3 | STE1 | 3 | Task | 13320
3.9.2.3 | - Phase II software documentation and acceptance test | 8 days | 242 | 245258 | Tue 5/12/20 | Thu 5/21/20 | 3.9.3.1,4.1 | DS1,ST1 | 3 | Task | 19153.28
3.9.3 | Phase II change management | 3 days |  |  | Fri 5/22/20 | Tue 5/26/20 |  |  | 2 | Activity |  | 5335.2
3.9.3.1 | - Business process changes | 1 day | 243 | 246 | Fri 5/22/20 | Fri 5/22/20 | 3.9.3.2 | PM1 | 3 | Task | 1778.4
3.9.3.2 | - Training in new work procedures | 1 day | 245 | 247 | Mon 5/25/20 | Mon 5/25/20 | 3.9.3.3 | PM1 | 3 | Task | 1778.4
3.9.3.3 | - User system training | 1 day | 246 | 249 | Tue 5/26/20 | Tue 5/26/20 | 3.9.4.1 | PM1 | 3 | Task | 1778.4
3.9.4 | New process & systems evaluation | 30 days |  |  | Wed 5/27/20 | Tue 7/7/20 |  |  | 2 | Activity |  | 50659.2
3.9.4.1 | - Phase II systems installation | 10 days | 247 | 250 | Wed 5/27/20 | Tue 6/9/20 | 3.9.4.2 | PM1,SA1 | 3 | Task | 31104
3.9.4.2 | - Phase II pilot study | 8 days | 249 | 251 | Mon 6/22/20 | Wed 7/1/20 | 3.9.4.3 | PM1 | 3 | Task | 14227.2
3.9.4.3 | - Phase II user evaluation | 2 days | 250 | 252 | Thu 7/2/20 | Fri 7/3/20 | 3.9.4.4 | SA1 | 3 | Task | 2664
3.9.4.4 | - Evaluation feedback and client review | 2 days | 251 | 254 | Mon 7/6/20 | Tue 7/7/20 | 3.9.5.1 | ST1 | 3 | Task | 2664
3.9.5 | Project Review (Stagegate) | 24 days |  |  | Wed 7/8/20 | Mon 8/10/20 |  |  | 2 | Activity |  | 36550.4
3.9.5.1 | - Stagegate (project plan) review for Phase II | 4 days | 252 | 255 | Wed 7/8/20 | Fri 7/17/20 | 3.9.5.2 | PM1,BA1,SA1 | 3 | Task | 17382.4
3.9.5.2 | - Agreement of client issues to be remedied in Phase II | 4 days | 254 | 256 | Mon 7/20/20 | Thu 7/23/20 | 3.9.5.3 | PM1,BA1 | 3 | Task | 12054.4
3.9.5.3 | - Client approval and signoff for Phase II | 4 days | 255 | 275 | Wed 8/5/20 | Mon 8/10/20 | 4.4.1.1 | PM1 | 3 | Task | 7113.6
4 | Phase III: Develop Integrated Business Management System | 333 days |  |  | Fri 5/22/20 | Tue 8/31/21 |  |  | 0 | Phase |  |  |  | 2528296.32
4.1 | Phase III Kickoff Meeting | 4 days | 243 | 260 | Fri 5/22/20 | Thu 5/28/20 | 4.2.1 | BA1,PM1,PA1,SA1,DBA1,DA1,UI1 | 1 | Task | 36089.6
4.2 | Follow up on Phase II activities | 48 days |  |  | Fri 5/29/20 | Tue 8/4/20 |  |  | 1 | Component |  |  | 313676
4.2.1 | · Review lessons learned from Phase 2 prototype and user evaluation | 16 days | 258 | 261 | Fri 5/29/20 | Fri 6/19/20 | 4.2.2 | PM1,BA1,DA1,PA1,ST1,SA1,UI1 | 2 | Task | 159937.28
4.2.2 | · Review software and hardware requirements | 18 days | 260 | 262 | Mon 6/22/20 | Wed 7/15/20 | 4.2.3 | PM1,SA1,DA1,UI1 | 2 | Task | 110193.12
4.2.3 | · Agree on changes to be made and assign tasks | 14 days | 261 | 2.6527e+26 | Thu 7/16/20 | Tue 8/4/20 | 4.3.1.1,4.3.2.1,4.3.3.1,4.8.2.1,4.8.2.2,4.8.2.3,4.8.2.4,4.8.2.5,4.4.1.1 | PM1,SA1 | 2 | Task | 43545.6
4.3 | Upgrade System Management Subsystem (Basic) | 128 days |  |  | Wed 8/5/20 | Fri 1/29/21 |  |  | 1 | Component |  |  | 163325.44
4.3.1 | Server App: Upgraded system management and security management | 28 days |  |  | Wed 8/5/20 | Fri 9/11/20 |  |  | 2 | Activity |  | 65450.88
4.3.1.1 | · Software requirements analysis | 16 days | 262 | 266 | Wed 8/5/20 | Wed 8/26/20 | 4.3.1.2 | SA1,PM1 | 3 | Task | 49766.4
4.3.1.2 | · Software design& code | 12 days | 265 | 268318 | Thu 8/27/20 | Fri 9/11/20 | 4.3.2.1,4.8.1.1 | PA1 | 3 | Task | 15684.48
4.3.2 | Client App: System management and security integration | 58 days |  |  | Thu 9/24/20 | Mon 12/14/20 |  |  | 2 | Activity |  | 71671.68
4.3.2.1 | · Software requirements analysis | 18 days | 262266 | 269 | Thu 9/24/20 | Thu 11/26/20 | 4.3.2.2 | SA1,PM1 | 3 | Task | 55987.2
4.3.2.2 | · Software design& code | 12 days | 268 | 271318 | Fri 11/27/20 | Mon 12/14/20 | 4.3.3.1,4.8.1.1 | PA1 | 3 | Task | 15684.48
4.3.3 | Client app: Provide integrated GUI to implement basic access stubs for all client apps.In Phase II | 34 days |  |  | Tue 12/15/20 | Fri 1/29/21 |  |  | 2 | Activity |  | 26202.88
4.3.3.1 | · User navigation requirements analysis | 10 days | 262269 | 272 | Tue 12/15/20 | Mon 12/28/20 | 4.3.3.2 | UI1 | 3 | Task | 11910.4
4.3.3.2 | · UI design& scripting | 12 days | 271 | 318 | Tue 12/29/20 | Fri 1/29/21 | 4.8.1.1 | UI1 | 3 | Task | 14292.48
4.4 | Develop Product management subsystem | 152 days |  |  | Tue 8/11/20 | Wed 3/10/21 |  |  | 1 | Component |  |  | 201712.16
4.4.1 | DBMS: Product management - continue development | 22 days |  |  | Tue 8/11/20 | Wed 9/9/20 |  |  | 2 | Activity |  | 53310.24
4.4.1.1 | · Design additional tables | 10 days | 262256 | 276278285 | Tue 8/11/20 | Mon 8/24/20 | 4.4.1.2,4.4.2.1,4.5.1.1 | DA1 | 3 | Task | 18204
4.4.1.2 | · Implement and test database structures | 12 days | 275 | 278318295 | Tue 8/25/20 | Wed 9/9/20 | 4.4.2.1,4.8.1.1,4.6.1.1 | DBA1,ST1 | 3 | Task | 35106.24
4.4.2 | Server App: Update Marketing and Development Application | 22 days |  |  | Thu 9/10/20 | Fri 10/9/20 |  |  | 2 | Activity |  | 46788.48
4.4.2.1 | · Software requirements analysis | 10 days | 275276 | 279281 | Thu 9/10/20 | Wed 9/23/20 | 4.4.2.2,4.4.3.1 | SA1,PM1 | 3 | Task | 31104
4.4.2.2 | · Software design& code | 12 days | 278 | 281318298 | Thu 9/24/20 | Fri 10/9/20 | 4.4.3.1,4.8.1.1,4.6.2.1 | PA2 | 3 | Task | 15684.48
4.4.3 | Client App: Update Marketing and Development Application | 108 days |  |  | Mon 10/12/20 | Wed 3/10/21 |  |  | 2 | Activity |  | 101613.44
4.4.3.1 | · Software requirements analysis | 20 days | 278279 | 282 | Mon 10/12/20 | Fri 1/29/21 | 4.4.3.2 | PM1,UI1 | 3 | Task | 59388.8
4.4.3.2 | · Software design& code | 16 days | 281 | 318 | Mon 2/1/21 | Wed 3/10/21 | 4.8.1.1 | PA2,SA1 | 3 | Task | 42224.64
4.5 | Develop Customer and Vendor Relations subsystem | 106 days |  |  | Tue 8/25/20 | Tue 1/19/21 |  |  | 1 | Component |  |  | 206612.48
4.5.1 | DBMS: Customer Relationship Management | 24 days |  |  | Tue 8/25/20 | Fri 9/25/20 |  |  | 2 | Activity |  | 71473.92
4.5.1.1 | · Design database | 12 days | 275 | 286288 | Tue 8/25/20 | Wed 9/9/20 | 4.5.1.2,4.5.2.1 | DA1,PA2,BA1 | 3 | Task | 52351.68
4.5.1.2 | · Implement and test database structures | 12 days | 285 | 288318 | Thu 9/10/20 | Fri 9/25/20 | 4.5.2.1,4.8.1.1 | DBA1 | 3 | Task | 19122.24
4.5.2 | Server App: CRM& Vendor Relations | 24 days |  |  | Mon 9/28/20 | Thu 10/29/20 |  |  | 2 | Activity |  | 68993.28
4.5.2.1 | · Software requirements analysis | 12 days | 285286 | 289291 | Mon 9/28/20 | Tue 10/13/20 | 4.5.2.2,4.5.3.1 | SA1,PM1 | 3 | Task | 37324.8
4.5.2.2 | · Software design& code | 12 days | 288 | 291318 | Wed 10/14/20 | Thu 10/29/20 | 4.5.3.1,4.8.1.1 | PA1,ST1 | 3 | Task | 31668.48
4.5.3 | Client App: Customer and Vendor Relations | 46 days |  |  | Tue 11/17/20 | Tue 1/19/21 |  |  | 2 | Activity |  | 66145.28
4.5.3.1 | · Software requirements analysis | 20 days | 288289 | 292 | Tue 11/17/20 | Mon 12/14/20 | 4.5.3.2 | SA1,UI1 | 3 | Task | 50460.8
4.5.3.2 | · Software design& code | 12 days | 291 | 318 | Mon 1/4/21 | Tue 1/19/21 | 4.8.1.1 | PA2 | 3 | Task | 15684.48
4.6 | Upgrade Operations Management & Reporting subsystem | 70 days |  |  | Thu 9/10/20 | Wed 12/16/20 |  |  | 1 | Component |  |  | 295525.6
4.6.1 | DBMS: Sales and Market Phase III functions | 24 days |  |  | Thu 9/10/20 | Tue 10/13/20 |  |  | 2 | Activity |  | 55789.44
4.6.1.1 | · Design database | 12 days | 276 | 296 | Thu 9/10/20 | Fri 9/25/20 | 4.6.1.2 | DA1,BA1 | 3 | Task | 36667.2
4.6.1.2 | · Implement and test database structures | 12 days | 295 | 298318 | Mon 9/28/20 | Tue 10/13/20 | 4.6.2.1,4.8.1.1 | DBA1 | 3 | Task | 19122.24
4.6.2 | Server App: Upgraded Sales Analysis and Reporting for Phase III functions | 24 days |  |  | Wed 10/14/20 | Mon 11/16/20 |  |  | 2 | Activity |  | 74854.08
4.6.2.1 | · Software requirements analysis | 12 days | 296279 | 299301 | Wed 10/14/20 | Thu 10/29/20 | 4.6.2.2,4.6.3.1 | SA1,PM1,DA1 | 3 | Task | 59169.6
4.6.2.2 | · Software design& code | 12 days | 298 | 318302 | Fri 10/30/20 | Mon 11/16/20 | 4.8.1.1,4.6.3.2 | PA1 | 3 | Task | 15684.48
4.6.3 | Client App: Management and Reporting for Phase II and III enhancements | 34 days |  |  | Fri 10/30/20 | Wed 12/16/20 |  |  | 2 | Activity |  | 164882.08
4.6.3.1 | · Software requirements analysis | 12 days | 298 | 302 | Fri 10/30/20 | Mon 11/16/20 | 4.6.3.2 | SA1,UI1,PA2,ST1 | 3 | Task | 61944.96
4.6.3.2 | · Software design& code | 22 days | 301299 | 305318308 | Tue 11/17/20 | Wed 12/16/20 | 4.7.1.1,4.8.1.1,4.7.2.1 | PA2,PM1,DBA1 | 3 | Task | 102937.12
4.7 | Upgrade System Management Subsystem (advanced functions) | 72 days |  |  | Thu 12/17/20 | Fri 3/26/21 |  |  | 1 | Component |  |  | 544707.84
4.7.1 | DBMS: Logging & Audit Trail for Phase III functions. | 50 days |  |  | Thu 12/17/20 | Wed 2/24/21 |  |  | 2 | Activity |  | 187952.64
4.7.1.1 | · Design database | 24 days | 302 | 306 | Thu 12/17/20 | Tue 1/19/21 | 4.7.1.2 | DA1,PM1,PA1 | 3 | Task | 117740.16
4.7.1.2 | · Implement and test database structures | 24 days | 305 | 318309 | Wed 1/20/21 | Wed 2/24/21 | 4.8.1.1,4.7.2.2 | DBA1,SA1 | 3 | Task | 70212.48
4.7.2 | Server App: Upgraded system management and security application for Phase III functions | 62 days |  |  | Thu 12/17/20 | Fri 3/12/21 |  |  | 2 | Activity |  | 88320
4.7.2.1 | · Software requirements analysis | 12 days | 302 | 309311 | Thu 12/17/20 | Fri 1/1/21 | 4.7.2.2,4.7.3.1 | SA1,DA1,PA2 | 3 | Task | 53513.28
4.7.2.2 | · Software design & code | 12 days | 308306 | 318 | Thu 2/25/21 | Fri 3/12/21 | 4.8.1.1 | PA1,DBA1 | 3 | Task | 34806.72
4.7.3 | Client App: user-navigation/access and reporting for Phase II Enhancements | 26 days |  |  | Mon 1/4/21 | Mon 2/8/21 |  |  | 2 | Activity |  | 116871.68
4.7.3.1 | · Software requirements analysis | 14 days | 308 | 312314 | Mon 1/4/21 | Thu 1/21/21 | 4.7.3.2,4.7.4.1 | SA1,PM1,UI1 | 3 | Task | 60220.16
4.7.3.2 | · Software design & code | 12 days | 311 | 314318 | Fri 1/22/21 | Mon 2/8/21 | 4.7.4.1,4.8.1.1 | PA1,DBA1,DA1 | 3 | Task | 56651.52
4.7.4 | Web client: Provide advanced GUI to implement user menus & login form for UI client app. Phase III | 34 days |  |  | Tue 2/9/21 | Fri 3/26/21 |  |  | 2 | Activity |  | 151563.52
4.7.4.1 | · User navigation requirements analysis | 12 days | 311312 | 315 | Tue 2/9/21 | Wed 2/24/21 | 4.7.4.2 | UI1,PM1,SA1,PA2 | 3 | Task | 67301.76
4.7.4.2 | · UI design & scripting | 22 days | 314 | 318 | Thu 2/25/21 | Fri 3/26/21 | 4.8.1.1 | UI1,SA1,PA2 | 3 | Task | 84261.76
4.8 | Phase III Delivery Activities | 280 days |  |  | Wed 8/5/20 | Tue 8/31/21 |  |  | 1 | Component |  |  | 766647.2
4.8.1 | Phase III Integration Test | 30 days |  |  | Mon 3/29/21 | Fri 5/7/21 |  |  | 2 | Activity |  | 244806.24
4.8.1.1 | · Integration test of Phase III software components | 12 days | 2.6627e+47 | 319 | Mon 3/29/21 | Tue 4/13/21 | 4.8.1.2 | ST1,PM1,DBA1,DA1,PA1 | 3 | Task | 93976.32
4.8.1.2 | · Redesign and rework following integration tests | 12 days | 318 | 320 | Wed 4/14/21 | Thu 4/29/21 | 4.8.1.3 | ST1,PM1,DBA1,DA1,PA1,SA1 | 3 | Task | 109960.32
4.8.1.3 | · Phase I & II software documentation and acceptance test | 6 days | 319 | 328 | Fri 4/30/21 | Fri 5/7/21 | 4.8.3.1 | PM1,ST1,SA1,DS1,PA2 | 3 | Task | 40869.6
4.8.2 | Phase III Change Management | 134 days |  |  | Wed 8/5/20 | Mon 2/8/21 |  |  | 2 | Activity |  | 212686.4
4.8.2.1 | · Business process change | 4 days | 262 | 328 | Mon 9/28/20 | Tue 1/5/21 | 4.8.3.1 | PM1,BA1 | 3 | Task | 12054.4
4.8.2.2 | · Training on new work procedures | 16 days | 262 | 328 | Wed 8/5/20 | Mon 9/7/20 | 4.8.3.1 | PM1,DS1 | 3 | Task | 45448.96
4.8.2.3 | · Update standard operating procedures | 4 days | 262 | 328 | Mon 8/17/20 | Wed 12/16/20 | 4.8.3.1 | PM1,DS1 | 3 | Task | 11362.24
4.8.2.4 | · User training/train the trainer sessions | 16 days | 262 | 328 | Wed 8/5/20 | Mon 2/8/21 | 4.8.3.1 | PM1,BA1 | 3 | Task | 48217.6
4.8.2.5 | · Set up and train support team (first-level and second-level) | 22 days | 262 | 328 | Mon 8/17/20 | Mon 12/14/20 | 4.8.3.1 | PM1,SA1,BA1 | 3 | Task | 95603.2
4.8.3 | Process and System Evaluation | 30 days |  |  | Mon 5/10/21 | Fri 6/18/21 |  |  | 2 | Activity |  | 167344.32
4.8.3.1 | · Systems installation | 12 days | 3.2032e+17 | 329336 | Mon 5/10/21 | Tue 5/25/21 | 4.8.3.2,4.8.5.1 | PA2,SA1,DBA1,DA1 | 3 | Task | 72635.52
4.8.3.2 | · Pilot test | 12 days | 328 | 330 | Wed 5/26/21 | Thu 6/10/21 | 4.8.3.3 | ST1,BA1,DA1,SA1 | 3 | Task | 68635.2
4.8.3.3 | · User evaluation/feedback | 6 days | 329 | 332 | Fri 6/11/21 | Fri 6/18/21 | 4.8.4.1 | PM1,ST1,BA1 | 3 | Task | 26073.6
4.8.4 | Project Review (Stagegate) | 36 days |  |  | Mon 6/21/21 | Mon 8/9/21 |  |  | 2 | Activity |  | 99128.64
4.8.4.1 | Stagegate review for the final system | 12 days | 330 | 333 | Mon 6/21/21 | Tue 7/6/21 | 4.8.4.2 | PM1,SA1,DBA1 | 3 | Task | 56447.04
4.8.4.2 | Remediation of client issues | 12 days | 332 | 334337 | Wed 7/7/21 | Thu 7/22/21 | 4.8.4.3,4.8.5.2 | PM1 | 3 | Task | 21340.8
4.8.4.3 | Client approval and signoff for final system | 12 days | 333 | 338 | Fri 7/23/21 | Mon 8/9/21 | 4.8.5.3 | PM1 | 3 | Task | 21340.8
4.8.5 | Project Closure | 70 days |  |  | Wed 5/26/21 | Tue 8/31/21 |  |  | 2 | Activity |  | 42681.6
4.8.5.1 | Procurement close | 8 days | 328 | 338 | Wed 5/26/21 | Fri 6/4/21 | 4.8.5.3 | PM1 | 3 | Task | 14227.2
4.8.5.2 | Obtain formal acceptance | 12 days | 333 | 338 | Tue 8/10/21 | Wed 8/25/21 | 4.8.5.3 | PM1 | 3 | Task | 21340.8
4.8.5.3 | Release resources | 4 days | 334336337 |  | Thu 8/26/21 | Tue 8/31/21 |  | PM1 | 3 | Task | 7113.6

## RawLaborCosts-WBS5
WBS | Task Name | Duration | Predecessors | Successors | Start | Finish | WBS Successors | Resource Initials | WBS Level | Type | Task Cost | Activity Cost | Component Cost | Phase Cost | Total Cost
1 | Pre-Development Activities | 44 days |  |  | Mon 1/7/19 | Thu 3/7/19 |  |  | 0 | Phase |  |  |  | 238037.28 | 2926962.96
1.1 | Project Planning Kickoff | 1 day |  | 4,5,6,7,8,9FS+2 days | Mon 1/7/19 | Mon 1/7/19 | 1.2.1,1.2.2,1.2.3,1.2.4,1.2.5,1.2.6[FS+2 days] | BA1,BA2,CRA1,PM1,SA1,DS1 | 1 | Task | 8463.36
1.2 | Perform Business Analysis | 7 days |  |  | Tue 1/8/19 | Wed 1/16/19 |  |  | 1 | Activity |  | 46110.08
1.2.1 | Business Analysis Group 1 Observation and Meetings | 2 days | 2 | 12,10 | Tue 1/8/19 | Wed 1/9/19 | 1.2.9,1.2.7 | BA1 | 2 | Task | 2470.4
1.2.2 | Business Analysis Group 2 Observation and Meetings | 2 days | 2 | 12,11 | Tue 1/8/19 | Wed 1/9/19 | 1.2.9,1.2.8 | BA2 | 2 | Task | 2470.4
1.2.3 | Business Analysis Group 3 Observation and Meetings | 2 days | 2 | 12 | Tue 1/8/19 | Wed 1/9/19 | 1.2.9 | CRA1 | 2 | Task | 3640.8
1.2.4 | Business Analysis Group 4 Observation and Meetings | 2 days | 2 | 12 | Tue 1/8/19 | Wed 1/9/19 | 1.2.9 | PM1 | 2 | Task | 3556.8
1.2.5 | Business Analysis Group 5 Observation and Meetings | 2 days | 2 | 12 | Fri 1/11/19 | Mon 1/14/19 | 1.2.9 | CRA1 | 2 | Task | 3640.8
1.2.6 | Business Analysis Checkin Meeting | 1 day | 2FS+2 days | 12,10,11 | Thu 1/10/19 | Thu 1/10/19 | 1.2.9,1.2.7,1.2.8 | BA1,BA2,CRA1,PM1,SA1,DS1 | 2 | Task | 8463.36
1.2.7 | Business Analysis Group 1 Pt2 Observation and Meetings | 2 days | 4,9 | 12 | Fri 1/11/19 | Mon 1/14/19 | 1.2.9 | BA1 | 2 | Task | 2470.4
1.2.8 | Business Analysis Group 2 Pt2 Observation and Meetings | 2 days | 5,9 | 12 | Fri 1/11/19 | Mon 1/14/19 | 1.2.9 | BA2 | 2 | Task | 2470.4
1.2.9 | Business Analysis Wrapup Meeting | 2 days | 4,5,6,7,8,9,10,11 | 14 | Tue 1/15/19 | Wed 1/16/19 | 1.3.1 | BA1,BA2,CRA1,PM1,SA1,DS1 | 2 | Task | 16926.72
1.3 | Investigate Stakeholder Requirements | 11 days |  |  | Thu 1/17/19 | Thu 1/31/19 |  |  | 1 | Activity |  | 70282
1.3.1 | Management and Reporting - Conduct application design workshop #1 | 2 days | 12 | 15,16,17,18,19,20,21 | Thu 1/17/19 | Fri 1/18/19 | 1.3.2,1.3.3,1.3.4,1.3.5,1.3.6,1.3.7,1.3.8 | BA1,BA2,CRA1,PM1,SA1 | 2 | Task | 14802.4
1.3.2 | Sales - Conduct application design workshop | 1 day | 14 | 22,21 | Mon 1/21/19 | Mon 1/21/19 | 1.3.9,1.3.8 | BA1 | 2 | Task | 1235.2
1.3.3 | Marketing and Development - Conduct application design workshop | 1 day | 14 | 22,21 | Mon 1/21/19 | Mon 1/21/19 | 1.3.9,1.3.8 | BA2 | 2 | Task | 1235.2
1.3.4 | Manufacturing - Conduct application design workshop | 1 day | 14 | 22,21 | Tue 1/22/19 | Tue 1/22/19 | 1.3.9,1.3.8 | BA2 | 2 | Task | 1235.2
1.3.5 | Customer and Vendor Relations - Conduct application design workshop | 1 day | 14 | 22,21 | Wed 1/23/19 | Wed 1/23/19 | 1.3.9,1.3.8 | CRA1 | 2 | Task | 1820.4
1.3.6 | Purchasing and Inventory Management - Conduct application design workshop | 2 days | 14 | 22,21 | Mon 1/21/19 | Tue 1/22/19 | 1.3.9,1.3.8 | SA1 | 2 | Task | 2664
1.3.7 | Accounting - Conduct application design workshop | 2 days | 14 | 22,21 | Mon 1/21/19 | Tue 1/22/19 | 1.3.9,1.3.8 | CRA1 | 2 | Task | 3640.8
1.3.8 | Management and Reporting - Conduct application design workshop #2 | 2 days | 14,15,16,17,18,19,20 | 22 | Thu 1/24/19 | Fri 1/25/19 | 1.3.9 | BA1,BA2,CRA1,PM1,SA1,DS1 | 2 | Task | 16926.72
1.3.9 | System Administration - Conduct application design workshop | 1 day | 15,16,17,18,19,20,21 | 23 | Mon 1/28/19 | Mon 1/28/19 | 1.3.10 | SA1 | 2 | Task | 1332
1.3.10 | Analyze system user requirements gathered from application design workshops | 3 days | 22 | 25,26,28,29,30 | Tue 1/29/19 | Thu 1/31/19 | 1.4.1,1.4.2,1.4.4,1.4.5,1.4.6 | BA1,BA2,CRA1,PM1,SA1,DS1 | 2 | Task | 25390.08
1.4 | Perform feasibility study: | 4 days |  |  | Fri 2/1/19 | Wed 2/6/19 |  |  | 1 | Activity |  | 28812.32
1.4.1 | Analyze the system configuration requirements for scale and interoperability/portability. | 3 days | 23 | 32 | Fri 2/1/19 | Tue 2/5/19 | 1.5.1 | SA1 | 2 | Task | 3996
1.4.2 | Begin a technology trawl to identify hardware and software required to deliver the system | 2 days | 23 | 27 | Fri 2/1/19 | Mon 2/4/19 | 1.4.3 | CRA1 | 2 | Task | 3640.8
1.4.3 | Review and complete technology trawl | 2 days | 26 | 32 | Tue 2/5/19 | Wed 2/6/19 | 1.5.1 | CRA1,SA1 | 2 | Task | 6304.8
1.4.4 | Research and identify services that we might contract with to perform currency tracking | 3 days | 23 | 32FF | Fri 2/1/19 | Tue 2/5/19 | 1.5.1[FF] | BA1,BA2 | 2 | Task | 7411.2
1.4.5 | Research and identify services that we might contract with to perform fax-to-email | 2 days | 23 | 32FF | Fri 2/1/19 | Mon 2/4/19 | 1.5.1[FF] | DS1 | 2 | Task | 2124.32
1.4.6 | Research and identify RFID and barcode labeling requirements and suppliers | 3 days | 23 | 32 | Fri 2/1/19 | Tue 2/5/19 | 1.5.1 | PM1 | 2 | Task | 5335.2
1.5 | Project planning: | 21 days |  |  | Thu 2/7/19 | Thu 3/7/19 |  |  | 1 | Activity |  | 84369.52
1.5.1 | Revisit system requirements, integrating input from the stakeholder analysis and the feasibility study | 4 days | 25,28FF,29FF,30,27 | 33 | Thu 2/7/19 | Tue 2/12/19 | 1.5.2 | PM1,SA1,DS1,CRA1,BA1,BA2 | 2 | Task | 33853.44
1.5.2 | Discuss and agree upon plan scope with key stakeholders | 3 days | 32 | 34 | Wed 2/13/19 | Fri 2/15/19 | 1.5.3 | BA1,DS1,PM1,CRA1 | 2 | Task | 17688.48
1.5.3 | Rearrange interim deliverables, to reflect what we've learned | 1 day | 33 | 35,39FS+2 days | Mon 2/18/19 | Mon 2/18/19 | 1.5.4,2.1[FS+2 days] | PM1 | 2 | Task | 1778.4
1.5.4 | Revise the project plan, resource plan, effort, time and budget estimates and project schedule | 5 days | 34 | 36 | Tue 2/19/19 | Wed 2/27/19 | 1.5.5 | PM1 | 2 | Task | 8892
1.5.5 | Review and agree estimate and timescale changes with upper management | 5 days | 35 | 37 | Thu 2/28/19 | Wed 3/6/19 | 1.5.6 | BA1,DS1,PM1 | 2 | Task | 20378.8
1.5.6 | Revise project plans to accommodate any revisions to scope | 1 day | 36 | 65 | Thu 3/7/19 | Thu 3/7/19 | 2.3.1.1 | PM1 | 2 | Task | 1778.4
2 | Phase I: Develop Basic Integrated Business Management System | 228 days |  |  | Thu 2/21/19 | Mon 1/6/20 |  |  | 0 | Phase |  |  |  | 988559.76
2.1 | Phase 1 Kickoff Meeting | 2 days | 34FS+2 days | 42,48,56,78,81,75,86,89,93,116,119,122,132 | Thu 2/21/19 | Fri 2/22/19 | 2.2.1.1,2.2.2.1,2.2.4.1,2.4.2.1,2.4.3.1,2.4.1.1,2.5.1.1,2.5.2.1,2.5.3.1,2.8.1.1,2.8.2.1,2.8.3.1,2.9.2.1.1.1 | PM1,PA1,BA1,DA1,SA1 | 1 | Task | 5681.12
2.2 | Develop Initial System Management Subsystem | 82 days |  |  | Mon 2/25/19 | Tue 6/18/19 |  |  | 1 | Component |  |  | 175000.08
2.2.1 | DBMS: Install & Configure DBMS Engine & SQL Interface | 38 days |  |  | Mon 2/25/19 | Wed 4/17/19 |  |  | 2 | Activity |  | 33121.12
2.2.1.1 | · Installing hardware server | 4 days | 39 | 43 | Mon 2/25/19 | Thu 2/28/19 | 2.2.1.2 | CNS1,PA1 | 3 | Task | 11852.16
2.2.1.2 | · TestNetwork connections | 2 days | 42 | 44 | Fri 3/1/19 | Mon 3/4/19 | 2.2.1.3 | CNS1,ST1 | 3 | Task | 5926.08
2.2.1.3 | · Install & Configure DBMS engine | 2 days | 43 | 45 | Thu 3/21/19 | Fri 3/22/19 | 2.2.1.4 | DA1 | 3 | Task | 3640.8
2.2.1.4 | · Install and test SQL interface software | 4 days | 44 | 46 | Mon 4/8/19 | Thu 4/11/19 | 2.2.1.5 | DBA1 | 3 | Task | 6374.08
2.2.1.5 | · Evaluate the system | 4 days | 45 | 49 | Fri 4/12/19 | Wed 4/17/19 | 2.2.2.2 | SA1 | 3 | Task | 5328
2.2.2 | DBMS: User Accounts and Permissions | 24 days |  |  | Mon 3/25/19 | Thu 4/25/19 |  |  | 2 | Activity |  | 13756.56
2.2.2.1 | · Design database | 2 days | 39 | 49 | Mon 3/25/19 | Tue 3/26/19 | 2.2.2.2 | DA1 | 3 | Task | 3640.8
2.2.2.2 | · Implement and test database structure | 3 days | 46,48 | 50,52 | Thu 4/18/19 | Mon 4/22/19 | 2.2.2.3,2.2.3.1 | DBA1 | 3 | Task | 4780.56
2.2.2.3 | · Test accounts | 3 days | 49 | 62 | Tue 4/23/19 | Thu 4/25/19 | 2.2.5.4 | PM1 | 3 | Task | 5335.2
2.2.3 | Server App: System management and security application | 20 days |  |  | Tue 4/23/19 | Mon 5/20/19 |  |  | 2 | Activity |  | 25566.08
2.2.3.1 | · Software requirements analysis | 8 days | 49 | 53 | Tue 4/23/19 | Thu 5/2/19 | 2.2.3.2 | BA1 | 3 | Task | 9881.6
2.2.3.2 | ·Software design | 8 days | 52 | 54 | Fri 5/3/19 | Tue 5/14/19 | 2.2.3.3 | PA1 | 3 | Task | 10456.32
2.2.3.3 | · Development & coding | 4 days | 53 | 62 | Wed 5/15/19 | Mon 5/20/19 | 2.2.5.4 | PA2 | 3 | Task | 5228.16
2.2.4 | Client App: System management application | 17 days |  |  | Fri 3/8/19 | Mon 4/1/19 |  |  | 2 | Activity |  | 25990.56
2.2.4.1 | · Software requirements analysis | 8 days | 39 | 57 | Fri 3/8/19 | Tue 3/19/19 | 2.2.4.2 | PM1 | 3 | Task | 14227.2
2.2.4.2 | · Software design & code | 9 days | 56 | 59 | Wed 3/20/19 | Mon 4/1/19 | 2.2.5.1 | PA1 | 3 | Task | 11763.36
2.2.5 | Integrated User Interface: Provide integrated GUI to implement basic access stubs for all client apps. In Phase 1 | 56 days |  |  | Tue 4/2/19 | Tue 6/18/19 |  |  | 2 | Activity |  | 76565.76
2.2.5.1 | · User navigation requirements analysis | 12 days | 57 | 60 | Tue 4/2/19 | Wed 4/17/19 | 2.2.5.2 | UI1 | 3 | Task | 14292.48
2.2.5.2 | · UI design & scripting | 12 days | 59 | 61 | Thu 4/18/19 | Fri 5/3/19 | 2.2.5.3 | UI1 | 3 | Task | 14292.48
2.2.5.3 | · UI documentation and acceptance test | 12 days | 60 | 62 | Mon 5/6/19 | Tue 5/21/19 | 2.2.5.4 | PM1 | 3 | Task | 21340.8
2.2.5.4 | · Subsystem/component integration test & documentation | 20 days | 50,61,54 | 127 | Wed 5/22/19 | Tue 6/18/19 | 2.9.1.1 | ST1 | 3 | Task | 26640
2.3 | Develop Knowledge Management and Training subsystem | 85 days |  |  | Mon 3/11/19 | Fri 7/5/19 |  |  | 1 | Component |  |  | 87346.72
2.3.1 | DBMS: Knowledgebase database | 20 days |  |  | Mon 3/11/19 | Fri 4/5/19 |  |  | 2 | Activity |  | 30498.4
2.3.1.1 | · Design database | 8 days | 37 | 66 | Mon 3/11/19 | Wed 3/20/19 | 2.3.1.2 | DA1 | 3 | Task | 14563.2
2.3.1.2 | · Implement and test database structures | 10 days | 65 | 68 | Mon 3/25/19 | Fri 4/5/19 | 2.3.2.1 | DBA1 | 3 | Task | 15935.2
2.3.2 | Server App: Knowledgebase and Training Manual | 18 days |  |  | Mon 4/8/19 | Wed 5/1/19 |  |  | 2 | Activity |  | 27768.96
2.3.2.1 | · Software requirements analysis | 9 days | 66 | 69 | Mon 4/8/19 | Thu 4/18/19 | 2.3.2.2 | PM1 | 3 | Task | 16005.6
2.3.2.2 | · Software design& code | 9 days | 68 | 71 | Fri 4/19/19 | Wed 5/1/19 | 2.3.3.1 | PA1 | 3 | Task | 11763.36
2.3.3 | Client App: Training Manual and Knowledgebase application | 47 days |  |  | Thu 5/2/19 | Fri 7/5/19 |  |  | 2 | Activity |  | 29079.36
2.3.3.1 | · Software requirements analysis | 13 days | 69 | 72 | Thu 5/2/19 | Thu 6/6/19 | 2.3.3.2 | SA1 | 3 | Task | 17316
2.3.3.2 | · Software design& code | 9 days | 71 | 127 | Fri 6/7/19 | Fri 7/5/19 | 2.9.1.1 | PA1 | 3 | Task | 11763.36
2.4 | Develop Order Processing & Invoicing subsystem | 41 days |  |  | Mon 2/25/19 | Mon 4/22/19 |  |  | 1 | Component |  |  | 48278.24
2.4.1 | DBMS: Orders & Invoicing Database – Full implementation | 4 days |  |  | Mon 2/25/19 | Thu 2/28/19 |  |  | 2 | Activity |  | 6827.84
2.4.1.1 | · Design database | 2 days | 39 | 76,97 | Mon 2/25/19 | Tue 2/26/19 | 2.4.1.2,2.6.1.1 | DA1 | 3 | Task | 3640.8
2.4.1.2 | · Implement and test database structures | 2 days | 75 | 79 | Wed 2/27/19 | Thu 2/28/19 | 2.4.2.2 | DBA1 | 3 | Task | 3187.04
2.4.2 | Server App: Billing/Invoicing | 8 days |  |  | Mon 2/25/19 | Wed 3/6/19 |  |  | 2 | Activity |  | 10556.16
2.4.2.1 | · Software requirements analysis | 4 days | 39 | 79 | Mon 2/25/19 | Thu 2/28/19 | 2.4.2.2 | SA1 | 3 | Task | 5328
2.4.2.2 | · Software design & code | 4 days | 76,78 | 82 | Fri 3/1/19 | Wed 3/6/19 | 2.4.3.2 | PA2 | 3 | Task | 5228.16
2.4.3 | Client App: Sales | 24 days |  |  | Wed 3/20/19 | Mon 4/22/19 |  |  | 2 | Activity |  | 30894.24
2.4.3.1 | · Software requirements analysis | 8 days | 39 | 82 | Wed 3/20/19 | Fri 3/29/19 | 2.4.3.2 | PM1 | 3 | Task | 14227.2
2.4.3.2 | · Software design & code | 3 days | 81,79 | 83 | Tue 4/2/19 | Thu 4/4/19 | 2.4.3.3 | PA1 | 3 | Task | 3921.12
2.4.3.3 | · Subsystem/component integration test & documentation | 12 days | 82 | 127 | Fri 4/5/19 | Mon 4/22/19 | 2.9.1.1 | DS1 | 3 | Task | 12745.92
2.5 | Develop Billing/Accounting subsystem | 81 days |  |  | Wed 3/27/19 | Wed 7/17/19 |  |  | 1 | Component |  |  | 56237.28
2.5.1 | DBMS: Budgeting and Accounting | 15 days |  |  | Wed 3/27/19 | Tue 4/16/19 |  |  | 2 | Activity |  | 10241.76
2.5.1.1 | · Design database | 3 days | 39,98 | 87 | Wed 3/27/19 | Fri 3/29/19 | 2.5.1.2 | DA1 | 3 | Task | 5461.2
2.5.1.2 | · Implement and test database structures | 3 days | 86 | 90 | Fri 4/12/19 | Tue 4/16/19 | 2.5.2.2 | DBA1 | 3 | Task | 4780.56
2.5.2 | Server App: Billing/Invoicing | 65 days |  |  | Mon 4/1/19 | Fri 6/28/19 |  |  | 2 | Activity |  | 24883.2
2.5.2.1 | · Software requirements analysis | 8 days | 39 | 90,93 | Mon 4/1/19 | Tue 6/18/19 | 2.5.2.2,2.5.3.1 | PM1 | 3 | Task | 14227.2
2.5.2.2 | · Software design & code | 3 days | 87,89 | 91,94 | Wed 6/19/19 | Fri 6/21/19 | 2.5.2.3,2.5.3.2 | SA1 | 3 | Task | 3996
2.5.2.3 | · Unit test | 5 days | 90 | 127 | Mon 6/24/19 | Fri 6/28/19 | 2.9.1.1 | STE1 | 3 | Task | 6660
2.5.3 | Client App: Accounting | 18 days |  |  | Mon 6/24/19 | Wed 7/17/19 |  |  | 2 | Activity |  | 21112.32
2.5.3.1 | · Software requirements analysis | 8 days | 39,89 | 94 | Mon 6/24/19 | Wed 7/3/19 | 2.5.3.2 | SA1 | 3 | Task | 10656
2.5.3.2 | · Software design & code | 8 days | 93,90 | 107 | Mon 7/8/19 | Wed 7/17/19 | 2.7.1.1 | PA1 | 3 | Task | 10456.32
2.6 | Develop Interface and Security for Supplier Web UI | 90 days |  |  | Wed 2/27/19 | Tue 7/2/19 |  |  | 1 | Component |  |  | 198071.2
2.6.1 | DBMS: Update Orders and Invoicing Database – add quotations table | 18 days |  |  | Wed 2/27/19 | Fri 3/22/19 |  |  | 2 | Activity |  | 43818.4
2.6.1.1 | · Design database | 8 days | 75 | 98 | Wed 2/27/19 | Fri 3/8/19 | 2.6.1.2 | DA1 | 3 | Task | 14563.2
2.6.1.2 | · Implement and test database structures | 10 days | 97 | 100,86 | Mon 3/11/19 | Fri 3/22/19 | 2.6.2.1,2.5.1.1 | ST1,DBA1 | 3 | Task | 29255.2
2.6.2 | Server App: Purchasing/Inventory | 24 days |  |  | Mon 3/25/19 | Thu 4/25/19 |  |  | 2 | Activity |  | 31668.48
2.6.2.1 | · Software requirements analysis | 12 days | 98 | 101 | Mon 3/25/19 | Tue 4/9/19 | 2.6.2.2 | SA1 | 3 | Task | 15984
2.6.2.2 | · Software design& code | 12 days | 100 | 103 | Wed 4/10/19 | Thu 4/25/19 | 2.6.3.1 | PA2 | 3 | Task | 15684.48
2.6.3 | Client App: Supplier Web UI | 48 days |  |  | Fri 4/26/19 | Tue 7/2/19 |  |  | 2 | Activity |  | 122584.32
2.6.3.1 | · Software requirements analysis | 36 days | 101 | 104 | Fri 4/26/19 | Fri 6/14/19 | 2.6.3.2 | UI1,PM1 | 3 | Task | 106899.84
2.6.3.2 | · Software design& code | 12 days | 103 | 127 | Mon 6/17/19 | Tue 7/2/19 | 2.9.1.1 | PA1 | 3 | Task | 15684.48
2.7 | Develop Currency prediction and Conversion subsystem | 54 days |  |  | Mon 7/29/19 | Thu 10/10/19 |  |  | 1 | Component |  |  | 118535.04
2.7.1 | Server App: API to Vendor currency database | 54 days |  |  | Mon 7/29/19 | Thu 10/10/19 |  |  | 2 | Activity |  | 118535.04
2.7.1.1 | - Software requirements analysis | 3 days | 94 | 108 | Mon 7/29/19 | Wed 7/31/19 | 2.7.1.2 | PM1 | 3 | Task | 5335.2
2.7.1.2 | - Software design & code | 5 days | 107 | 110 | Thu 8/1/19 | Wed 8/7/19 | 2.7.1.3.1 | PA1 | 3 | Task | 6535.2
2.7.1.3 | Review Currency Prediction and Conversion subsystem | 46 days |  |  | Thu 8/8/19 | Thu 10/10/19 |  |  | 3 | Activity |  | 106664.64
2.7.1.3.1 | · Integration and regression testing for each component | 10 days | 108 | 111 | Thu 8/8/19 | Wed 8/21/19 | 2.7.1.3.2 | ST1,PM1 | 4 | Task | 31104
2.7.1.3.2 | · Validate and test results | 10 days | 110 | 112 | Thu 8/22/19 | Wed 9/4/19 | 2.7.1.3.3 | ST1,SA1 | 4 | Task | 44424
2.7.1.3.3 | · UAT | 10 days | 111 | 113 | Thu 9/5/19 | Wed 9/25/19 | 2.7.1.3.4 | SA1 | 4 | Task | 13320
2.7.1.3.4 | · Sign-off | 6 days | 112 | 158 | Thu 9/26/19 | Thu 10/10/19 | 2.10.4.2 | PM1,UI1 | 4 | Task | 17816.64
2.8 | Develop Inventory management subsystem | 106 days |  |  | Fri 3/1/19 | Fri 7/26/19 |  |  | 1 | Component |  |  | 69791.12
2.8.1 | DBMS: Resources & Inventory Database | 6 days |  |  | Mon 4/1/19 | Mon 4/8/19 |  |  | 2 | Activity |  | 9457.2
2.8.1.1 | · Design database | 3 days | 39 | 117 | Mon 4/1/19 | Wed 4/3/19 | 2.8.1.2 | DA1 | 3 | Task | 5461.2
2.8.1.2 | · Implement and test database structures | 3 days | 116 | 119 | Thu 4/4/19 | Mon 4/8/19 | 2.8.2.1 | STE1 | 3 | Task | 3996
2.8.2 | Server App: Purchasing & Inventory Management | 16 days |  |  | Tue 4/9/19 | Tue 4/30/19 |  |  | 2 | Activity |  | 13802.72
2.8.2.1 | · Software requirements analysis | 8 days | 39117 | 120 | Tue 4/9/19 | Thu 4/18/19 | 2.8.2.2 | BA1 | 3 | Task | 9881.6
2.8.2.2 | · Software design & code | 3 days | 119 | 124 | Fri 4/26/19 | Tue 4/30/19 | 2.8.3.3 | PA2 | 3 | Task | 3921.12
2.8.3 | Client App: Inventory Management | 106 days |  |  | Fri 3/1/19 | Fri 7/26/19 |  |  | 2 | Activity |  | 46531.2
2.8.3.1 | · Software requirements analysis | 10 days | 39 | 123 | Fri 3/1/19 | Thu 3/14/19 | 2.8.3.2 | SA1 | 3 | Task | 13320
2.8.3.2 | · Software design & code | 5 days | 122 | 127 | Fri 3/15/19 | Mon 4/8/19 | 2.9.1.1 | PA1 | 3 | Task | 6535.2
2.8.3.3 | · Subsystem/component integration test & documentation | 15 days | 120 | 144 | Mon 7/8/19 | Fri 7/26/19 | 2.10.1.1.1 | PM1 | 3 | Task | 26676
2.9 | Develop System Management Subsystem (advanced functions) | 134 days |  |  | Mon 4/22/19 | Thu 10/24/19 |  |  | 1 | Component |  |  | 140515.6
2.9.1 | DBMS: Logging & Audit Trail for Phase I functions. | 24 days |  |  | Mon 7/8/19 | Thu 8/8/19 |  |  | 2 | Activity |  | 37828.8
2.9.1.1 | · Design database | 12 days | 62,83,123,72,91,104 | 128 | Mon 7/8/19 | Tue 7/23/19 | 2.9.1.2 | DA1 | 3 | Task | 21844.8
2.9.1.2 | · Implement and test database structures | 12 days | 127 | 134 | Wed 7/24/19 | Thu 8/8/19 | 2.9.2.1.2 | STE1 | 3 | Task | 15984
2.9.2 | GUI & front-end menu implementation | 134 days |  |  | Mon 4/22/19 | Thu 10/24/19 |  |  | 2 | Activity |  | 102686.8
2.9.2.1 | Client App: Integrated user-navigation/access | 103 days |  |  | Mon 4/22/19 | Wed 9/11/19 |  |  | 3 | Subcomponent
2.9.2.1.1 | · Software requirements analysis | 65 days |  |  | Mon 4/22/19 | Fri 7/19/19 |  |  | 4 | Task
2.9.2.1.1.1 | · Requirment gathering | 14 days | 39 | 133 | Mon 4/22/19 | Fri 7/5/19 | 2.9.2.1.1.2 | PM1 | 5 | Subtask | 24897.6
2.9.2.1.1.2 | · Requirment analysis phase | 10 days | 132 | 134 | Mon 7/8/19 | Fri 7/19/19 | 2.9.2.1.2 | BA1 | 5 | Subtask | 12352
2.9.2.1.2 | · Software design & code | 12 days | 133128 | 135 | Fri 8/9/19 | Mon 8/26/19 | 2.9.2.1.3 | PA2 | 4 | Task | 15684.48
2.9.2.1.3 | · Subsystem/component integration test & documentation | 12 days | 134 | 140137 | Tue 8/27/19 | Wed 9/11/19 | 2.9.2.2.4,2.9.2.2.1 | DS1 | 4 | Task | 12745.92
2.9.2.2 | Client App: Provide advanced GUI to implement user menus and login form for UI client app. | 31 days |  |  | Thu 9/12/19 | Thu 10/24/19 |  |  | 3 | Subcomponent
2.9.2.2.1 | · User navigation requirements analysis | 8 days | 135 | 138 | Thu 9/12/19 | Mon 9/23/19 | 2.9.2.2.2 | UI1 | 4 | Task | 9528.32
2.9.2.2.2 | · UI design & scripting | 9 days | 137 | 139 | Tue 9/24/19 | Fri 10/4/19 | 2.9.2.2.3 | UI1 | 4 | Task | 10719.36
2.9.2.2.3 | · GUI unit tests | 7 days | 138 | 140 | Mon 10/7/19 | Tue 10/15/19 | 2.9.2.2.4 | STE1 | 4 | Task | 9324
2.9.2.2.4 | · UI documentation and acceptance test | 7 days | 135139 | 144 | Wed 10/16/19 | Thu 10/24/19 | 2.10.1.1.1 | DS1 | 4 | Task | 7435.12
2.10 | Phase I Delivery Activities | 52 days |  |  | Fri 10/25/19 | Mon 1/6/20 |  |  | 1 | Component |  |  | 89103.36
2.10.1 | Phase I Integration Test | 12 days |  |  | Fri 10/25/19 | Mon 11/11/19 |  |  | 2 | Activity |  | 15834.24
2.10.1.1 | · Integration test of Phase I software components | 12 days |  |  | Fri 10/25/19 | Mon 11/11/19 |  |  | 3 | Task
2.10.1.1.1 | · Redesign and rework following integration tests | 6 days | 140124 | 145 | Fri 10/25/19 | Fri 11/1/19 | 2.10.1.1.2 | PA1 | 4 | Subtask | 7842.24
2.10.1.1.2 | · Phase I software documentation and acceptance test | 6 days | 144 | 147160 | Mon 11/4/19 | Mon 11/11/19 | 2.10.2.1,3.1 | ST1 | 4 | Subtask | 7992
2.10.2 | Phase IChange management | 13 days |  |  | Thu 11/14/19 | Mon 12/2/19 |  |  | 2 | Activity |  | 28052.8
2.10.2.1 | · Training on new work procedures | 4 days | 145 | 148 | Thu 11/14/19 | Tue 11/19/19 | 2.10.2.2 | PM1,SA1 | 3 | Task | 12441.6
2.10.2.2 | · Business process changes | 4 days | 147 | 149 | Wed 11/20/19 | Thu 11/28/19 | 2.10.2.3 | BA1,PM1 | 3 | Task | 12054.4
2.10.2.3 | · User system training | 2 days | 148 | 151 | Fri 11/29/19 | Mon 12/2/19 | 2.10.3.1 | PM1 | 3 | Task | 3556.8
2.10.3 | New process & systems evaluation | 17 days |  |  | Tue 12/3/19 | Wed 12/25/19 |  |  | 2 | Activity |  | 30989.12
2.10.3.1 | · Phase I systems installation | 7 days | 149 | 152 | Tue 12/3/19 | Wed 12/11/19 | 2.10.3.2 | SA1 | 3 | Task | 9324
2.10.3.2 | · Phase I Testing | 6 days | 151 | 153 | Thu 12/12/19 | Thu 12/19/19 | 2.10.3.3 | STE1,ST1 | 3 | Task | 15984
2.10.3.3 | · Phase I System Documentation | 2 days | 152 | 154 | Fri 12/20/19 | Mon 12/23/19 | 2.10.3.4 | DS1 | 3 | Task | 2124.32
2.10.3.4 | · Phase I User evaluation | 1 day | 153 | 155 | Tue 12/24/19 | Tue 12/24/19 | 2.10.3.5 | PM1 | 3 | Task | 1778.4
2.10.3.5 | · Evaluate the feedback | 1 day | 154 | 157 | Wed 12/25/19 | Wed 12/25/19 | 2.10.4.1 | PM1 | 3 | Task | 1778.4
2.10.4 | Project Review | 8 days |  |  | Thu 12/26/19 | Mon 1/6/20 |  |  | 2 | Activity |  | 14227.2
2.10.4.1 | · Project plan review for Phase I | 4 days | 155 | 158 | Thu 12/26/19 | Tue 12/31/19 | 2.10.4.2 | PM1 | 3 | Task | 7113.6
2.10.4.2 | · Management approval and signoff for Phase I | 4 days | 157113 | 177 | Wed 1/1/20 | Mon 1/6/20 | 3.4.1.1 | PM1 | 3 | Task | 7113.6
3 | Phase II: Develop Advanced Integrated Business Management System | 167 days |  |  | Tue 11/12/19 | Wed 7/1/20 |  |  | 0 | Phase |  |  |  | 385161.44
3.1 | Phase 2 Kickoff Meeting | 2 days | 145 | 162163167177 | Tue 11/12/19 | Wed 11/13/19 | 3.2.1,3.2.2,3.3.1.1,3.4.1.1 | BA1,DBA1,DS1,PA1,PM1,SA1,UI1 | 1 | Task | 16528.32
3.2 | Phase 1 follow up | 6 days |  |  | Wed 11/20/19 | Wed 11/27/19 |  |  | 1 | Component |  |  | 16787.2
3.2.1 | Review Phase I software components | 5 days | 160 | 164 | Wed 11/20/19 | Tue 11/26/19 | 3.2.3 | PM1 | 2 | Task | 8892
3.2.2 | Review Phase I hardware components | 5 days | 160 | 174 | Wed 11/20/19 | Tue 11/26/19 | 3.3.3 | SA1 | 2 | Task | 6660
3.2.3 | Upgrade the software requirements | 1 day | 162 | 181171 | Wed 11/27/19 | Wed 11/27/19 | 3.4.2.1,3.3.2.1 | BA1 | 2 | Task | 1235.2
3.3 | Upgrade System Management Subsystem (Basic) | 36 days |  |  | Thu 11/14/19 | Thu 1/2/20 |  |  | 1 | Component |  |  | 52273.6
3.3.1 | Server App: Upgraded system management and security management | 34 days |  |  | Thu 11/14/19 | Tue 12/31/19 |  |  | 2 | Activity |  | 19246.4
3.3.1.1 | - Software requirements analysis | 5 days | 160 | 168 | Thu 11/14/19 | Wed 11/20/19 | 3.3.1.2 | BA1 | 3 | Task | 6176
3.3.1.2 | - Software design | 5 days | 167 | 169 | Thu 11/21/19 | Tue 12/17/19 | 3.3.1.3 | PA2 | 3 | Task | 6535.2
3.3.1.3 | - Software code | 5 days | 168 |  | Wed 12/25/19 | Tue 12/31/19 |  | PA2 | 3 | Task | 6535.2
3.3.2 | Client App: System management and security integration | 24 days |  |  | Thu 11/28/19 | Tue 12/31/19 |  |  | 2 | Activity |  | 30363.2
3.3.2.1 | - Software requirements analysis | 14 days | 164 | 172 | Thu 11/28/19 | Tue 12/17/19 | 3.3.2.2 | BA1 | 3 | Task | 17292.8
3.3.2.2 | - Software design | 5 days | 171 | 173 | Wed 12/18/19 | Tue 12/24/19 | 3.3.2.3 | PA2 | 3 | Task | 6535.2
3.3.2.3 | - Software code | 5 days | 172 | 174 | Wed 12/25/19 | Tue 12/31/19 | 3.3.3 | PA1 | 3 | Task | 6535.2
3.3.3 | Subsystem integration testing | 2 days | 173163 | 2.4122e+17 | Wed 1/1/20 | Thu 1/2/20 | 3.9.2.1,3.7.1.1,3.6.1.1,3.6.2.1,3.6.3.1,3.6.4.1 | STE1 | 2 | Task | 2664
3.4 | Develop Operations Management & Reporting subsystem | 71 days |  |  | Thu 11/28/19 | Thu 3/5/20 |  |  | 1 | Component |  |  | 58817.84
3.4.1 | DBMS: Sales and Market | 27 days |  |  | Wed 1/15/20 | Thu 2/20/20 |  |  | 2 | Activity |  | 35959.6
3.4.1.1 | - Design database by creating tables, developing packages and integrating with the server application | 10 days | 158160 | 178 | Wed 1/15/20 | Tue 1/28/20 | 3.4.1.2 | DBA1 | 3 | Task | 15935.2
3.4.1.2 | - Implement and test database structures | 6 days | 177 | 179194 | Wed 1/29/20 | Wed 2/5/20 | 3.4.1.3,3.5.1.1 | DA1 | 3 | Task | 10922.4
3.4.1.3 | - Gather information regarding previous sales and market demands. | 5 days | 178 | 187 | Fri 2/14/20 | Thu 2/20/20 | 3.4.3.2.1 | DA1 | 3 | Task | 9102
3.4.2 | Server App: Sales Analysis and Reporting | 6 days |  |  | Thu 11/28/19 | Thu 12/5/19 |  |  | 2 | Activity |  | 7483.04
3.4.2.1 | - Software requirements analysis | 5 days | 164 | 183194 | Thu 11/28/19 | Wed 12/4/19 | 3.4.2.2.1,3.5.1.1 | BA1 | 3 | Task | 6176
3.4.2.2 | - Software design & code | 1 day |  |  | Thu 12/5/19 | Thu 12/5/19 |  |  | 3 | Task
3.4.2.2.1 | - Write a program to display the analysis using charts and graphs for easy understanding. | 1 day | 181 | 185 | Thu 12/5/19 | Thu 12/5/19 | 3.4.3.1 | PA2 | 4 | Subtask | 1307.04
3.4.3 | Client App: Management and Reporting | 63 days |  |  | Fri 12/6/19 | Tue 3/3/20 |  |  | 2 | Activity |  | 12711.2
3.4.3.1 | - Software requirements analysis | 5 days | 183 | 187 | Fri 12/6/19 | Thu 12/12/19 | 3.4.3.2.1 | BA1 | 3 | Task | 6176
3.4.3.2 | - Software design & code | 5 days |  |  | Wed 2/26/20 | Tue 3/3/20 |  |  | 3 | Task
3.4.3.2.1 | - Develop a user friendly UI that shows the graph and charts of sales against time duration and scale. | 1 day | 185179 | 188 | Wed 2/26/20 | Wed 2/26/20 | 3.4.3.2.2 | PA1 | 4 | Subtask | 1307.04
3.4.3.2.2 | - Application used to report | 2 days | 187 | 189 | Thu 2/27/20 | Fri 2/28/20 | 3.4.3.2.3 | PA1 | 4 | Subtask | 2614.08
3.4.3.2.3 | - Develop the GUI | 1 day | 188 | 190 | Mon 3/2/20 | Mon 3/2/20 | 3.4.3.2.4 | PA1 | 4 | Subtask | 1307.04
3.4.3.2.4 | - Unit testing of GUI | 1 day | 189 | 191 | Tue 3/3/20 | Tue 3/3/20 | 3.4.4 | PA1 | 4 | Subtask | 1307.04
3.4.4 | Subsystem integration testing | 2 days | 190 | 241 | Wed 3/4/20 | Thu 3/5/20 | 3.9.2.1 | STE1 | 2 | Task | 2664
3.5 | Develop Forecasting and Analysis subsystem | 26 days |  |  | Thu 2/6/20 | Thu 3/12/20 |  |  | 1 | Component |  |  | 25551.2
3.5.1 | DBMS: Update Sales and Market Database – add forecasting & analysis table | 2 days |  |  | Thu 2/6/20 | Fri 2/7/20 |  |  | 2 | Activity |  | 3640.8
3.5.1.1 | - Implement and test database structures | 2 days | 181178 | 196 | Thu 2/6/20 | Fri 2/7/20 | 3.5.2.1 | DA1 | 3 | Task | 3640.8
3.5.2 | Server App: Demand Forecasting | 22 days |  |  | Mon 2/10/20 | Tue 3/10/20 |  |  | 2 | Activity |  | 19246.4
3.5.2.1 | - Software requirements analysis | 5 days | 194 | 197 | Mon 2/10/20 | Fri 2/14/20 | 3.5.2.2 | BA1 | 3 | Task | 6176
3.5.2.2 | - Software design | 5 days | 196 | 198 | Tue 2/18/20 | Tue 2/25/20 | 3.5.2.3 | PA1 | 3 | Task | 6535.2
3.5.2.3 | - Software code | 5 days | 197 | 199 | Wed 3/4/20 | Tue 3/10/20 | 3.5.3 | PA1 | 3 | Task | 6535.2
3.5.3 | Subsystem integration testing | 2 days | 198 | 241 | Wed 3/11/20 | Thu 3/12/20 | 3.9.2.1 | STE1 | 2 | Task | 2664
3.6 | Develop Product code database and Lookup subsystem | 16 days |  |  | Fri 1/3/20 | Fri 1/24/20 |  |  | 1 | Component |  |  | 46798.4
3.6.1 | DBMS: Product Management (only product code-related tables) | 12 days |  |  | Fri 1/3/20 | Mon 1/20/20 |  |  | 2 | Activity |  | 20029.76
3.6.1.1 | - Design database by creating tables, developing packages and integrating with the server application | 8 days | 174 | 203 | Fri 1/3/20 | Tue 1/14/20 | 3.6.1.2 | DBA1 | 3 | Task | 12748.16
3.6.1.2 | - Implement and test database structures | 4 days | 202 | 206 | Wed 1/15/20 | Mon 1/20/20 | 3.6.2.2 | DA1 | 3 | Task | 7281.6
3.6.2 | Server App: Marketing and Development (functions related to product code) | 11 days |  |  | Wed 1/8/20 | Wed 1/22/20 |  |  | 2 | Activity |  | 6319.68
3.6.2.1 | - Software requirements analysis | 3 days | 174 | 206 | Wed 1/8/20 | Fri 1/10/20 | 3.6.2.2 | BA1 | 3 | Task | 3705.6
3.6.2.2 | - Software design & code | 2 days | 205203 | 214 | Tue 1/21/20 | Wed 1/22/20 | 3.6.5 | PA1 | 3 | Task | 2614.08
3.6.3 | Client App: Marketing and Development Application (functions related to product code) | 9 days |  |  | Fri 1/3/20 | Wed 1/15/20 |  |  | 2 | Activity |  | 8801.28
3.6.3.1 | - Software requirements analysis | 3 days | 174 | 209 | Fri 1/3/20 | Tue 1/7/20 | 3.6.3.2 | UI1 | 3 | Task | 3573.12
3.6.3.2 | - Software design & code | 4 days | 208 | 214 | Fri 1/10/20 | Wed 1/15/20 | 3.6.5 | PA1 | 3 | Task | 5228.16
3.6.4 | Service: Product code lookup service | 7 days |  |  | Fri 1/3/20 | Mon 1/13/20 |  |  | 2 | Activity |  | 8983.68
3.6.4.1 | - Software requirements analysis | 3 days | 174 | 212 | Fri 1/3/20 | Tue 1/7/20 | 3.6.4.2 | BA1 | 3 | Task | 3705.6
3.6.4.2 | - Software design & code | 2 days | 211 | 213 | Wed 1/8/20 | Thu 1/9/20 | 3.6.4.3 | PA1 | 3 | Task | 2614.08
3.6.4.3 | - Integration testing | 2 days | 212 | 214 | Fri 1/10/20 | Mon 1/13/20 | 3.6.5 | ST1 | 3 | Task | 2664
3.6.5 | Subsystem integration testing | 2 days | 213206209 | 241222 | Thu 1/23/20 | Fri 1/24/20 | 3.9.2.1,3.8.1.1 | STE1 | 2 | Task | 2664
3.7 | Develop Currency prediction and Conversion subsystem | 7 days |  |  | Mon 1/13/20 | Tue 1/21/20 |  |  | 1 | Component |  |  | 8983.68
3.7.1 | Server App: API to Vendor currency database | 5 days |  |  | Mon 1/13/20 | Fri 1/17/20 |  |  | 2 | Activity |  | 6319.68
3.7.1.1 | - Software requirements analysis | 3 days | 174 | 218 | Mon 1/13/20 | Wed 1/15/20 | 3.7.1.2 | BA1 | 3 | Task | 3705.6
3.7.1.2 | - Software design & code | 2 days | 217 | 219 | Thu 1/16/20 | Fri 1/17/20 | 3.7.2 | PA1 | 3 | Task | 2614.08
3.7.2 | Subsystem integration testing | 2 days | 218 | 241 | Mon 1/20/20 | Tue 1/21/20 | 3.9.2.1 | STE1 | 2 | Task | 2664
3.8 | Upgrade System Management Subsystem (advanced functions) | 21 days |  |  | Wed 1/29/20 | Wed 2/26/20 |  |  | 1 | Component |  |  | 27459.76
3.8.1 | DBMS: Logging & Audit Trail for Phase II functions. | 10 days |  |  | Wed 1/29/20 | Tue 2/11/20 |  |  | 2 | Activity |  | 10014.88
3.8.1.1 | - Design database by creating tables, developing packages and integrating with the server application | 4 days | 214 | 223 | Wed 1/29/20 | Mon 2/3/20 | 3.8.1.2 | DBA1 | 3 | Task | 6374.08
3.8.1.2 | - Implement and test database structures | 2 days | 222 | 225 | Mon 2/10/20 | Tue 2/11/20 | 3.8.2.1 | DA1 | 3 | Task | 3640.8
3.8.2 | DBMS: Permissions for Phase II functions. | 2 days |  |  | Wed 2/12/20 | Thu 2/13/20 |  |  | 2 | Activity |  | 3640.8
3.8.2.1 | - Update database | 1 day | 223 | 226228 | Wed 2/12/20 | Wed 2/12/20 | 3.8.2.2,3.8.3.1 | DA1 | 3 | Task | 1820.4
3.8.2.2 | - Implement and test database structures | 1 day | 225 | 229 | Thu 2/13/20 | Thu 2/13/20 | 3.8.3.2 | DA1 | 3 | Task | 1820.4
3.8.3 | Server App: Upgraded system management and security application for Phase II functions | 3 days |  |  | Thu 2/13/20 | Mon 2/17/20 |  |  | 2 | Activity |  | 3777.44
3.8.3.1 | - Software requirements analysis | 2 days | 225 | 229 | Thu 2/13/20 | Fri 2/14/20 | 3.8.3.2 | BA1 | 3 | Task | 2470.4
3.8.3.2 | - Software design & code | 1 day | 228226 | 231 | Mon 2/17/20 | Mon 2/17/20 | 3.8.4.1 | PA1 | 3 | Task | 1307.04
3.8.4 | Client App: user-navigation/access and reporting for Phase II Enhancements | 2 days |  |  | Tue 2/18/20 | Wed 2/19/20 |  |  | 2 | Activity |  | 2542.24
3.8.4.1 | - Software requirements analysis | 1 day | 229 | 232 | Tue 2/18/20 | Tue 2/18/20 | 3.8.4.2 | BA1 | 3 | Task | 1235.2
3.8.4.2 | - Software design & code | 1 day | 231 | 234 | Wed 2/19/20 | Wed 2/19/20 | 3.8.5.1 | PA1 | 3 | Task | 1307.04
3.8.5 | Client app: Provide advanced GUI to implement user menus and login form for UI client app. (Phase II) | 3 days |  |  | Thu 2/20/20 | Mon 2/24/20 |  |  | 2 | Activity |  | 4820.4
3.8.5.1 | - User navigation requirements analysis | 1 day | 232 | 235 | Thu 2/20/20 | Thu 2/20/20 | 3.8.5.2 | BA1 | 3 | Task | 1235.2
3.8.5.2 | - UI design & scripting | 1 day | 234 | 236 | Fri 2/21/20 | Fri 2/21/20 | 3.8.5.3 | UI1 | 3 | Task | 1191.04
3.8.5.3 | - UI documentation and acceptance test | 1 day | 235 | 237 | Mon 2/24/20 | Mon 2/24/20 | 3.8.6 | DS1,ST1 | 3 | Task | 2394.16
3.8.6 | Subsystem integration testing | 2 days | 236 | 239 | Tue 2/25/20 | Wed 2/26/20 | 3.9.1 | STE1 | 2 | Task | 2664
3.9 | Phase II Delivery Activities | 81 days |  |  | Wed 3/11/20 | Wed 7/1/20 |  |  | 1 | Component |  |  | 131961.44
3.9.1 | Integrate all the software components developed. | 4 days | 237 | 241 | Wed 3/11/20 | Mon 3/16/20 | 3.9.2.1 | PA1 | 2 | Task | 5228.16
3.9.2 | Phase II Integration Test | 26 days |  |  | Tue 3/17/20 | Tue 4/21/20 |  |  | 2 | Activity |  | 42879.68
3.9.2.1 | - Integration test of Phase II software components | 8 days | 2.3922e+17 | 242 | Tue 3/17/20 | Thu 3/26/20 | 3.9.2.2 | ST1 | 3 | Task | 10656
3.9.2.2 | - Redesign and rework following integration tests | 10 days | 241 | 243 | Fri 3/27/20 | Thu 4/9/20 | 3.9.2.3 | PA1 | 3 | Task | 13070.4
3.9.2.3 | - Phase II software documentation and acceptance test | 8 days | 242 | 245258 | Fri 4/10/20 | Tue 4/21/20 | 3.9.3.1,4.1 | DS1,ST1 | 3 | Task | 19153.28
3.9.3 | Phase II change management | 3 days |  |  | Wed 4/22/20 | Fri 4/24/20 |  |  | 2 | Activity |  | 5335.2
3.9.3.1 | - Business process changes | 1 day | 243 | 246 | Wed 4/22/20 | Wed 4/22/20 | 3.9.3.2 | PM1 | 3 | Task | 1778.4
3.9.3.2 | - Training in new work procedures | 1 day | 245 | 247 | Thu 4/23/20 | Thu 4/23/20 | 3.9.3.3 | PM1 | 3 | Task | 1778.4
3.9.3.3 | - User system training | 1 day | 246 | 249 | Fri 4/24/20 | Fri 4/24/20 | 3.9.4.1 | PM1 | 3 | Task | 1778.4
3.9.4 | New process & systems evaluation | 30 days |  |  | Mon 4/27/20 | Fri 6/5/20 |  |  | 2 | Activity |  | 50659.2
3.9.4.1 | - Phase II systems installation | 10 days | 247 | 250 | Mon 4/27/20 | Fri 5/8/20 | 3.9.4.2 | PM1,SA1 | 3 | Task | 31104
3.9.4.2 | - Phase II pilot study | 8 days | 249 | 251 | Thu 5/21/20 | Mon 6/1/20 | 3.9.4.3 | PM1 | 3 | Task | 14227.2
3.9.4.3 | - Phase II user evaluation | 2 days | 250 | 252 | Tue 6/2/20 | Wed 6/3/20 | 3.9.4.4 | SA1 | 3 | Task | 2664
3.9.4.4 | - Evaluation feedback and client review | 2 days | 251 | 254 | Thu 6/4/20 | Fri 6/5/20 | 3.9.5.1 | ST1 | 3 | Task | 2664
3.9.5 | Project Review (Stagegate) | 18 days |  |  | Mon 6/8/20 | Wed 7/1/20 |  |  | 2 | Activity |  | 27859.2
3.9.5.1 | - Stagegate (project plan) review for Phase II | 2 days | 252 | 255 | Mon 6/8/20 | Tue 6/9/20 | 3.9.5.2 | PM1,BA1,SA1 | 3 | Task | 8691.2
3.9.5.2 | - Agreement of client issues to be remedied in Phase II | 4 days | 254 | 256 | Wed 6/10/20 | Mon 6/15/20 | 3.9.5.3 | PM1,BA1 | 3 | Task | 12054.4
3.9.5.3 | - Client approval and signoff for Phase II | 4 days | 255 | 275 | Fri 6/26/20 | Wed 7/1/20 | 4.4.1.1 | PM1 | 3 | Task | 7113.6
4 | Phase III: Develop Integrated Business Management System | 331 days |  |  | Wed 4/22/20 | Wed 7/28/21 |  |  | 0 | Phase |  |  |  | 1315204.48
4.1 | Phase III Kickoff Meeting | 4 days | 243 | 260 | Wed 4/22/20 | Tue 4/28/20 | 4.2.1 | BA1,PM1,PA1,SA1,DBA1,DA1,UI1 | 1 | Task | 36089.6
4.2 | Follow up on Phase II activities | 42 days |  |  | Wed 4/29/20 | Thu 6/25/20 |  |  | 1 | Component |  |  | 227677.76
4.2.1 | · Review lessons learned from Phase 2 prototype and user evaluation | 16 days | 258 | 261 | Wed 4/29/20 | Wed 5/20/20 | 4.2.2 | PM1,BA1,PA1,SA1 | 2 | Task | 159937.28
4.2.2 | · Review software and hardware requirements | 12 days | 260 | 262 | Thu 5/21/20 | Fri 6/5/20 | 4.2.3 | SA1,DA1,UI1 | 2 | Task | 53513.28
4.2.3 | · Agree on changes to be made and assign tasks | 8 days | 261 | 2.6527e+26 | Tue 6/16/20 | Thu 6/25/20 | 4.3.1.1,4.3.2.1,4.3.3.1,4.8.2.1,4.8.2.2,4.8.2.3,4.8.2.4,4.8.2.5,4.4.1.1 | PM1 | 2 | Task | 14227.2
4.3 | Upgrade System Management Subsystem (Basic) | 68 days |  |  | Fri 6/26/20 | Tue 9/29/20 |  |  | 1 | Component |  |  | 91339.84
4.3.1 | Server App: Upgraded system management and security management | 24 days |  |  | Fri 6/26/20 | Wed 7/29/20 |  |  | 2 | Activity |  | 31668.48
4.3.1.1 | · Software requirements analysis | 12 days | 262 | 266 | Fri 6/26/20 | Mon 7/13/20 | 4.3.1.2 | SA1 | 3 | Task | 15984
4.3.1.2 | · Software design& code | 12 days | 265 | 268318 | Tue 7/14/20 | Wed 7/29/20 | 4.3.2.1,4.8.1.1 | PA1 | 3 | Task | 15684.48
4.3.2 | Client App: System management and security integration | 22 days |  |  | Thu 7/30/20 | Fri 8/28/20 |  |  | 2 | Activity |  | 33468.48
4.3.2.1 | · Software requirements analysis | 10 days | 262266 | 269 | Thu 7/30/20 | Wed 8/12/20 | 4.3.2.2 | PM1 | 3 | Task | 17784
4.3.2.2 | · Software design& code | 12 days | 268 | 271318 | Thu 8/13/20 | Fri 8/28/20 | 4.3.3.1,4.8.1.1 | PA1 | 3 | Task | 15684.48
4.3.3 | Client app: Provide integrated GUI to implement basic access stubs for all client apps.In Phase II | 22 days |  |  | Mon 8/31/20 | Tue 9/29/20 |  |  | 2 | Activity |  | 26202.88
4.3.3.1 | · User navigation requirements analysis | 10 days | 262269 | 272 | Mon 8/31/20 | Fri 9/11/20 | 4.3.3.2 | UI1 | 3 | Task | 11910.4
4.3.3.2 | · UI design& scripting | 12 days | 271 | 318 | Mon 9/14/20 | Tue 9/29/20 | 4.8.1.1 | UI1 | 3 | Task | 14292.48
4.4 | Develop Product management subsystem | 68 days |  |  | Thu 7/2/20 | Mon 10/5/20 |  |  | 1 | Component |  |  | 99799.2
4.4.1 | DBMS: Product management - continue development | 22 days |  |  | Thu 7/2/20 | Fri 7/31/20 |  |  | 2 | Activity |  | 37326.24
4.4.1.1 | · Design additional tables | 10 days | 262256 | 276278285 | Thu 7/2/20 | Wed 7/15/20 | 4.4.1.2,4.4.2.1,4.5.1.1 | DA1 | 3 | Task | 18204
4.4.1.2 | · Implement and test database structures | 12 days | 275 | 278318295 | Thu 7/16/20 | Fri 7/31/20 | 4.4.2.1,4.8.1.1,4.6.1.1 | DBA1 | 3 | Task | 19122.24
4.4.2 | Server App: Update Marketing and Development Application | 22 days |  |  | Mon 8/3/20 | Tue 9/1/20 |  |  | 2 | Activity |  | 29004.48
4.4.2.1 | · Software requirements analysis | 10 days | 275276 | 279281 | Mon 8/3/20 | Fri 8/14/20 | 4.4.2.2,4.4.3.1 | SA1 | 3 | Task | 13320
4.4.2.2 | · Software design& code | 12 days | 278 | 281318298 | Mon 8/17/20 | Tue 9/1/20 | 4.4.3.1,4.8.1.1,4.6.2.1 | PA2 | 3 | Task | 15684.48
4.4.3 | Client App: Update Marketing and Development Application | 22 days |  |  | Fri 9/4/20 | Mon 10/5/20 |  |  | 2 | Activity |  | 33468.48
4.4.3.1 | · Software requirements analysis | 10 days | 278279 | 282 | Fri 9/4/20 | Thu 9/17/20 | 4.4.3.2 | PM1 | 3 | Task | 17784
4.4.3.2 | · Software design& code | 12 days | 281 | 318 | Fri 9/18/20 | Mon 10/5/20 | 4.8.1.1 | PA2 | 3 | Task | 15684.48
4.5 | Develop Customer and Vendor Relations subsystem | 94 days |  |  | Thu 7/16/20 | Tue 11/24/20 |  |  | 1 | Component |  |  | 109660.8
4.5.1 | DBMS: Customer Relationship Management | 24 days |  |  | Thu 7/16/20 | Tue 8/18/20 |  |  | 2 | Activity |  | 40967.04
4.5.1.1 | · Design database | 12 days | 275 | 286288 | Thu 7/16/20 | Fri 7/31/20 | 4.5.1.2,4.5.2.1 | DA1 | 3 | Task | 21844.8
4.5.1.2 | · Implement and test database structures | 12 days | 285 | 288318 | Mon 8/3/20 | Tue 8/18/20 | 4.5.2.1,4.8.1.1 | DBA1 | 3 | Task | 19122.24
4.5.2 | Server App: CRM& Vendor Relations | 24 days |  |  | Wed 8/19/20 | Mon 9/21/20 |  |  | 2 | Activity |  | 37025.28
4.5.2.1 | · Software requirements analysis | 12 days | 285286 | 289291 | Wed 8/19/20 | Thu 9/3/20 | 4.5.2.2,4.5.3.1 | PM1 | 3 | Task | 21340.8
4.5.2.2 | · Software design& code | 12 days | 288 | 291318 | Fri 9/4/20 | Mon 9/21/20 | 4.5.3.1,4.8.1.1 | PA1 | 3 | Task | 15684.48
4.5.3 | Client App: Customer and Vendor Relations | 34 days |  |  | Thu 10/8/20 | Tue 11/24/20 |  |  | 2 | Activity |  | 31668.48
4.5.3.1 | · Software requirements analysis | 12 days | 288289 | 292 | Thu 10/8/20 | Fri 10/23/20 | 4.5.3.2 | SA1 | 3 | Task | 15984
4.5.3.2 | · Software design& code | 12 days | 291 | 318 | Mon 11/9/20 | Tue 11/24/20 | 4.8.1.1 | PA2 | 3 | Task | 15684.48
4.6 | Upgrade Operations Management & Reporting subsystem | 70 days |  |  | Mon 8/3/20 | Fri 11/6/20 |  |  | 1 | Component |  |  | 104304
4.6.1 | DBMS: Sales and Market Phase III functions | 24 days |  |  | Mon 8/3/20 | Thu 9/3/20 |  |  | 2 | Activity |  | 40967.04
4.6.1.1 | · Design database | 12 days | 276 | 296 | Mon 8/3/20 | Tue 8/18/20 | 4.6.1.2 | DA1 | 3 | Task | 21844.8
4.6.1.2 | · Implement and test database structures | 12 days | 295 | 298318 | Wed 8/19/20 | Thu 9/3/20 | 4.6.2.1,4.8.1.1 | DBA1 | 3 | Task | 19122.24
4.6.2 | Server App: Upgraded Sales Analysis and Reporting for Phase III functions | 24 days |  |  | Fri 9/4/20 | Wed 10/7/20 |  |  | 2 | Activity |  | 31668.48
4.6.2.1 | · Software requirements analysis | 12 days | 296279 | 299301 | Fri 9/4/20 | Mon 9/21/20 | 4.6.2.2,4.6.3.1 | SA1 | 3 | Task | 15984
4.6.2.2 | · Software design& code | 12 days | 298 | 318302 | Tue 9/22/20 | Wed 10/7/20 | 4.8.1.1,4.6.3.2 | PA1 | 3 | Task | 15684.48
4.6.3 | Client App: Management and Reporting for Phase II and III enhancements | 34 days |  |  | Tue 9/22/20 | Fri 11/6/20 |  |  | 2 | Activity |  | 31668.48
4.6.3.1 | · Software requirements analysis | 12 days | 298 | 302 | Tue 9/22/20 | Wed 10/7/20 | 4.6.3.2 | SA1 | 3 | Task | 15984
4.6.3.2 | · Software design& code | 12 days | 301299 | 305318308 | Thu 10/8/20 | Fri 11/6/20 | 4.7.1.1,4.8.1.1,4.7.2.1 | PA2 | 3 | Task | 15684.48
4.7 | Upgrade System Management Subsystem (advanced functions) | 60 days |  |  | Mon 11/9/20 | Fri 1/29/21 |  |  | 1 | Component |  |  | 175271.04
4.7.1 | DBMS: Logging & Audit Trail for Phase III functions. | 34 days |  |  | Mon 11/9/20 | Thu 12/24/20 |  |  | 2 | Activity |  | 40967.04
4.7.1.1 | · Design database | 12 days | 302 | 306 | Mon 11/9/20 | Tue 11/24/20 | 4.7.1.2 | DA1 | 3 | Task | 21844.8
4.7.1.2 | · Implement and test database structures | 12 days | 305 | 318309 | Wed 11/25/20 | Thu 12/24/20 | 4.8.1.1,4.7.2.2 | DBA1 | 3 | Task | 19122.24
4.7.2 | Server App: Upgraded system management and security application for Phase III functions | 48 days |  |  | Mon 11/9/20 | Wed 1/13/21 |  |  | 2 | Activity |  | 31668.48
4.7.2.1 | · Software requirements analysis | 12 days | 302 | 309311 | Mon 11/9/20 | Tue 11/24/20 | 4.7.2.2,4.7.3.1 | SA1 | 3 | Task | 15984
4.7.2.2 | · Software design & code | 12 days | 308306 | 318 | Tue 12/29/20 | Wed 1/13/21 | 4.8.1.1 | PA1 | 3 | Task | 15684.48
4.7.3 | Client App: user-navigation/access and reporting for Phase II Enhancements | 24 days |  |  | Wed 11/25/20 | Mon 12/28/20 |  |  | 2 | Activity |  | 37025.28
4.7.3.1 | · Software requirements analysis | 12 days | 308 | 312314 | Wed 11/25/20 | Thu 12/10/20 | 4.7.3.2,4.7.4.1 | PM1 | 3 | Task | 21340.8
4.7.3.2 | · Software design & code | 12 days | 311 | 314318 | Fri 12/11/20 | Mon 12/28/20 | 4.7.4.1,4.8.1.1 | PA1 | 3 | Task | 15684.48
4.7.4 | Web client: Provide advanced GUI to implement user menus & login form for UI client app. Phase III | 24 days |  |  | Tue 12/29/20 | Fri 1/29/21 |  |  | 2 | Activity |  | 65610.24
4.7.4.1 | · User navigation requirements analysis | 12 days | 311312 | 315 | Tue 12/29/20 | Wed 1/13/21 | 4.7.4.2 | UI1,PM1 | 3 | Task | 35633.28
4.7.4.2 | · UI design & scripting | 12 days | 314 | 318 | Thu 1/14/21 | Fri 1/29/21 | 4.8.1.1 | UI1,PA2 | 3 | Task | 29976.96
4.8 | Phase III Delivery Activities | 284 days |  |  | Fri 6/26/20 | Wed 7/28/21 |  |  | 1 | Component |  |  | 471062.24
4.8.1 | Phase III Integration Test | 30 days |  |  | Mon 2/1/21 | Fri 3/12/21 |  |  | 2 | Activity |  | 94831.2
4.8.1.1 | · Integration test of Phase III software components | 12 days | 2.6627e+47 | 319 | Mon 2/1/21 | Tue 2/16/21 | 4.8.1.2 | ST1,PM1,DA1 | 3 | Task | 37324.8
4.8.1.2 | · Redesign and rework following integration tests | 12 days | 318 | 320 | Wed 2/17/21 | Thu 3/4/21 | 4.8.1.3 | PM1,DBA1,PA1,SA1 | 3 | Task | 40463.04
4.8.1.3 | · Phase I & II software documentation and acceptance test | 6 days | 319 | 328326325 | Fri 3/5/21 | Fri 3/12/21 | 4.8.3.1,4.8.2.5,4.8.2.4 | PM1,DS1 | 3 | Task | 17043.36
4.8.2 | Phase III Change Management | 202 days |  |  | Fri 6/26/20 | Mon 4/5/21 |  |  | 2 | Activity |  | 151141.76
4.8.2.1 | · Business process change | 4 days | 262 | 328 | Fri 6/26/20 | Wed 7/15/20 | 4.8.3.1 | PM1,BA1 | 3 | Task | 12054.4
4.8.2.2 | · Training on new work procedures | 12 days | 262 | 328 | Fri 6/26/20 | Mon 7/13/20 | 4.8.3.1 | PM1,DS1 | 3 | Task | 34086.72
4.8.2.3 | · Update standard operating procedures | 4 days | 262 | 328 | Wed 7/8/20 | Fri 7/17/20 | 4.8.3.1 | PM1,DS1 | 3 | Task | 11362.24
4.8.2.4 | · User training/train the trainer sessions | 8 days | 262320 | 328 | Mon 3/15/21 | Wed 3/24/21 | 4.8.3.1 | PM1,BA1 | 3 | Task | 24108.8
4.8.2.5 | · Set up and train support team (first-level and second-level) | 16 days | 262320 | 328 | Mon 3/15/21 | Mon 4/5/21 | 4.8.3.1 | PM1,SA1,BA1 | 3 | Task | 69529.6
4.8.3 | Process and System Evaluation | 30 days |  |  | Tue 4/6/21 | Mon 5/17/21 |  |  | 2 | Activity |  | 102401.28
4.8.3.1 | · Systems installation | 12 days | 3.2032e+17 | 329336 | Tue 4/6/21 | Wed 4/21/21 | 4.8.3.2,4.8.5.1 | PA2,DBA1,DA1 | 3 | Task | 15684.48
4.8.3.2 | · Pilot test | 12 days | 328 | 330 | Thu 4/22/21 | Fri 5/7/21 | 4.8.3.3 | ST1,DA1,SA1 | 3 | Task | 68635.2
4.8.3.3 | · User evaluation/feedback | 6 days | 329 | 332 | Mon 5/10/21 | Mon 5/17/21 | 4.8.4.1 | PM1,BA1 | 3 | Task | 18081.6
4.8.4 | Project Review (Stagegate) | 36 days |  |  | Tue 5/18/21 | Tue 7/6/21 |  |  | 2 | Activity |  | 80006.4
4.8.4.1 | Stagegate review for the final system | 12 days | 330 | 333 | Tue 5/18/21 | Wed 6/2/21 | 4.8.4.2 | PM1,SA1 | 3 | Task | 37324.8
4.8.4.2 | Remediation of client issues | 12 days | 332 | 334337 | Thu 6/3/21 | Fri 6/18/21 | 4.8.4.3,4.8.5.2 | PM1 | 3 | Task | 21340.8
4.8.4.3 | Client approval and signoff for final system | 12 days | 333 | 338 | Mon 6/21/21 | Tue 7/6/21 | 4.8.5.3 | PM1 | 3 | Task | 21340.8
4.8.5 | Project Closure | 70 days |  |  | Thu 4/22/21 | Wed 7/28/21 |  |  | 2 | Activity |  | 42681.6
4.8.5.1 | Procurement close | 8 days | 328 | 338 | Thu 4/22/21 | Mon 5/3/21 | 4.8.5.3 | PM1 | 3 | Task | 14227.2
4.8.5.2 | Obtain formal acceptance | 12 days | 333 | 338 | Wed 7/7/21 | Thu 7/22/21 | 4.8.5.3 | PM1 | 3 | Task | 21340.8
4.8.5.3 | Release resources | 4 days | 334336337 |  | Fri 7/23/21 | Wed 7/28/21 |  | PM1 | 3 | Task | 7113.6

## ResourceCosts
Resource Name | Initials | Group | Std. Rate | Cost/Use | Daily Cost | Resources in gray have been removed from the project
Business Analyst 1 | BA1 | Analysts | $154.40/hr | 0 | 1235.2
Business Analyst 2 | BA2 | Analysts | $154.40/hr | 0 | 1235.2
Consultant Network Specialist | CNS1 | Consultants | $138.00/hr | 552 | 1656
Consultant Requirements Analyst | CRA1 | Consultants; Analysts | $151.70/hr | 606.8 | 1820.4
Database Administrator | DBA1 | Database Analysts | $44.79/hr | 0 | 358.32
Database Analyst 1 | DA1 | Database Analysts | $144.80/hr | 0 | 1158.4
Documentation Specialist | DS1 | Documentation Specialists | $132.77/hr | 0 | 1062.16
Programmer 1 | PA1 |  | $163.38/hr | 0 | 1307.04
Programmer 2 | PA2 |  | $163.38/hr | 0 | 1307.04
Programmer 3 | PA3 |  | $163.38/hr | 0 | 1307.04
Project Manager | PM1 | Project Managers | $222.30/hr | 0 | 1778.4
Software Test Engineer | STE1 |  | $44.98/hr | 0 | 359.84
Software Tester 1 | ST1 | Software Testing | $33.60/hr | 0 | 268.8
Software Tester 2 | ST2 | Software Testing | $33.60/hr | 0 | 268.8
System Analyst | SA1 | Analysts | $166.50/hr | 0 | 1332
UI Designer 1 | UI1 | Designer | $148.88/hr | 0 | 1191.04
UI Designer 2 | UI2 | Designer | $148.88/hr | 0 | 1191.04

## CostLookup
Resource Initials | Total Daily Cost | BA1 | BA2 | CNS1 | CRA1 | DBA1 | DA1 | DS1 | PA1 | PA2 | PA3 | PM1 | STE1 | ST1 | ST2 | SA1 | UI1 | UI2
BA1 | 1235.2 | 1235.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BA1,BA2 | 2470.4 | 1235.2 | 1235.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BA1,BA2,CRA1,PM1,SA1 | 7401.2 | 1235.2 | 1235.2 | 0 | 1820.4 | 0 | 0 | 0 | 0 | 0 | 0 | 1778.4 | 0 | 0 | 0 | 1332 | 0 | 0
BA1,BA2,CRA1,PM1,SA1,DS1 | 8463.36 | 1235.2 | 1235.2 | 0 | 1820.4 | 0 | 0 | 1062.16 | 0 | 0 | 0 | 1778.4 | 0 | 0 | 0 | 1332 | 0 | 0
BA1,DBA1,DS1,PA1,PM1,SA1,UI1 | 8264.16 | 1235.2 | 0 | 0 | 0 | 358.32 | 0 | 1062.16 | 1307.04 | 0 | 0 | 1778.4 | 0 | 0 | 0 | 1332 | 1191.04 | 0
BA1,DS1,PM1 | 4075.76 | 1235.2 | 0 | 0 | 0 | 0 | 0 | 1062.16 | 0 | 0 | 0 | 1778.4 | 0 | 0 | 0 | 0 | 0 | 0
BA1,DS1,PM1,CRA1 | 5896.16 | 1235.2 | 0 | 0 | 1820.4 | 0 | 0 | 1062.16 | 0 | 0 | 0 | 1778.4 | 0 | 0 | 0 | 0 | 0 | 0
BA1,PM1 | 3013.6 | 1235.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1778.4 | 0 | 0 | 0 | 0 | 0 | 0
BA1,PM1,PA1,SA1,DBA1,DA1,UI1 | 9022.4 | 1235.2 | 0 | 0 | 0 | 358.32 | 1820.4 | 0 | 1307.04 | 0 | 0 | 1778.4 | 0 | 0 | 0 | 1332 | 1191.04 | 0
BA1,SA1 | 2567.2 | 1235.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1332 | 0 | 0
BA2 | 1235.2 | 0 | 1235.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CNS1 | 1656 | 0 | 0 | 1656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CNS1,PA1 | 2963.04 | 0 | 0 | 1656 | 0 | 0 | 0 | 0 | 1307.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CRA1 | 1820.4 | 0 | 0 | 0 | 1820.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CRA1,SA1 | 3152.4 | 0 | 0 | 0 | 1820.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1332 | 0 | 0
DA1 | 1820.4 | 0 | 0 | 0 | 0 | 0 | 1820.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DA1,BA1 | 3055.6 | 1235.2 | 0 | 0 | 0 | 0 | 1820.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DA1,PA2,BA1 | 4362.64 | 1235.2 | 0 | 0 | 0 | 0 | 1820.4 | 0 | 0 | 1307.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DA1,PM1 | 3598.8 | 0 | 0 | 0 | 0 | 0 | 1820.4 | 0 | 0 | 0 | 0 | 1778.4 | 0 | 0 | 0 | 0 | 0 | 0
DA1,PM1,PA1 | 4905.84 | 0 | 0 | 0 | 0 | 0 | 1820.4 | 0 | 1307.04 | 0 | 0 | 1778.4 | 0 | 0 | 0 | 0 | 0 | 0
DA1,ST1 | 3152.4 | 0 | 0 | 0 | 0 | 0 | 1820.4 | 0 | 0 | 0 | 0 | 0 | 0 | 1332 | 0 | 0 | 0 | 0
DBA1 | 1593.52 | 1235.2 | 0 | 0 | 0 | 358.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DBA1,PM1 | 3371.92 | 1235.2 | 0 | 0 | 0 | 358.32 | 0 | 0 | 0 | 0 | 0 | 1778.4 | 0 | 0 | 0 | 0 | 0 | 0
DBA1,SA1 | 2925.52 | 1235.2 | 0 | 0 | 0 | 358.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1332 | 0 | 0
DBA1,ST1 | 2925.52 | 1235.2 | 0 | 0 | 0 | 358.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1332 | 0 | 0 | 0 | 0
DS1 | 1062.16 | 0 | 0 | 0 | 0 | 0 | 0 | 1062.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS1,PM1 | 2840.56 | 0 | 0 | 0 | 0 | 0 | 0 | 1062.16 | 0 | 0 | 0 | 1778.4 | 0 | 0 | 0 | 0 | 0 | 0
DS1,ST1 | 2394.16 | 0 | 0 | 0 | 0 | 0 | 0 | 1062.16 | 0 | 0 | 0 | 0 | 0 | 1332 | 0 | 0 | 0 | 0
PA1 | 1307.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1307.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PA1,DBA1 | 2900.56 | 1235.2 | 0 | 0 | 0 | 358.32 | 0 | 0 | 1307.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PA1,DBA1,DA1 | 4720.96 | 1235.2 | 0 | 0 | 0 | 358.32 | 1820.4 | 0 | 1307.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PA1,PM1 | 3085.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1307.04 | 0 | 0 | 1778.4 | 0 | 0 | 0 | 0 | 0 | 0
PA1,SA1 | 2639.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1307.04 | 0 | 0 | 0 | 0 | 0 | 0 | 1332 | 0 | 0
PA1,ST1 | 2639.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1307.04 | 0 | 0 | 0 | 0 | 1332 | 0 | 0 | 0 | 0
PA2 | 1307.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1307.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PA2,PA1 | 2614.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1307.04 | 1307.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PA2,PM1,DBA1 | 4678.96 | 1235.2 | 0 | 0 | 0 | 358.32 | 0 | 0 | 0 | 1307.04 | 0 | 1778.4 | 0 | 0 | 0 | 0 | 0 | 0
PA2,SA1 | 2639.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1307.04 | 0 | 0 | 0 | 0 | 0 | 1332 | 0 | 0
PA2,SA1,DBA1,DA1 | 6052.96 | 1235.2 | 0 | 0 | 0 | 358.32 | 1820.4 | 0 | 0 | 1307.04 | 0 | 0 | 0 | 0 | 0 | 1332 | 0 | 0
PM1 | 1778.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1778.4 | 0 | 0 | 0 | 0 | 0 | 0
PM1,BA1 | 3013.6 | 1235.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1778.4 | 0 | 0 | 0 | 0 | 0 | 0
PM1,BA1,DA1,PA1,ST1,SA1,UI1 | 9996.08 | 1235.2 | 0 | 0 | 0 | 0 | 1820.4 | 0 | 1307.04 | 0 | 0 | 1778.4 | 0 | 1332 | 0 | 1332 | 1191.04 | 0
PM1,BA1,SA1 | 4345.6 | 1235.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1778.4 | 0 | 0 | 0 | 1332 | 0 | 0
PM1,DA1 | 3598.8 | 0 | 0 | 0 | 0 | 0 | 1820.4 | 0 | 0 | 0 | 0 | 1778.4 | 0 | 0 | 0 | 0 | 0 | 0
PM1,DBA1 | 3371.92 | 1235.2 | 0 | 0 | 0 | 358.32 | 0 | 0 | 0 | 0 | 0 | 1778.4 | 0 | 0 | 0 | 0 | 0 | 0
PM1,DS1 | 2840.56 | 0 | 0 | 0 | 0 | 0 | 0 | 1062.16 | 0 | 0 | 0 | 1778.4 | 0 | 0 | 0 | 0 | 0 | 0
PM1,PA1,BA1,DBA1,DA1,ST1,SA1,UI1 | 10354.4 | 1235.2 | 0 | 0 | 0 | 358.32 | 1820.4 | 0 | 1307.04 | 0 | 0 | 1778.4 | 0 | 1332 | 0 | 1332 | 1191.04 | 0
PM1,SA1 | 3110.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1778.4 | 0 | 0 | 0 | 1332 | 0 | 0
PM1,SA1,BA1 | 4345.6 | 1235.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1778.4 | 0 | 0 | 0 | 1332 | 0 | 0
PM1,SA1,DA1,UI1 | 6121.84 | 0 | 0 | 0 | 0 | 0 | 1820.4 | 0 | 0 | 0 | 0 | 1778.4 | 0 | 0 | 0 | 1332 | 1191.04 | 0
PM1,SA1,DBA1 | 4703.92 | 1235.2 | 0 | 0 | 0 | 358.32 | 0 | 0 | 0 | 0 | 0 | 1778.4 | 0 | 0 | 0 | 1332 | 0 | 0
PM1,SA1,DS1,CRA1,BA1,BA2 | 8463.36 | 1235.2 | 1235.2 | 0 | 1820.4 | 0 | 0 | 1062.16 | 0 | 0 | 0 | 1778.4 | 0 | 0 | 0 | 1332 | 0 | 0
PM1,ST1 | 3110.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1778.4 | 0 | 1332 | 0 | 0 | 0 | 0
PM1,ST1,BA1 | 4345.6 | 1235.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1778.4 | 0 | 1332 | 0 | 0 | 0 | 0
PM1,ST1,SA1,DS1,PA2 | 6811.6 | 0 | 0 | 0 | 0 | 0 | 0 | 1062.16 | 0 | 1307.04 | 0 | 1778.4 | 0 | 1332 | 0 | 1332 | 0 | 0
PM1,UI1 | 2969.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1778.4 | 0 | 0 | 0 | 0 | 1191.04 | 0
SA1 | 1332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1332 | 0 | 0
SA1,BA1 | 2567.2 | 1235.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1332 | 0 | 0
SA1,BA1,UI1 | 3758.24 | 1235.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1332 | 1191.04 | 0
SA1,DA1,PA2 | 4459.44 | 0 | 0 | 0 | 0 | 0 | 1820.4 | 0 | 0 | 1307.04 | 0 | 0 | 0 | 0 | 0 | 1332 | 0 | 0
SA1,PA1 | 2639.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1307.04 | 0 | 0 | 0 | 0 | 0 | 0 | 1332 | 0 | 0
SA1,PA2 | 2639.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1307.04 | 0 | 0 | 0 | 0 | 0 | 1332 | 0 | 0
SA1,PM1 | 3110.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1778.4 | 0 | 0 | 0 | 1332 | 0 | 0
SA1,PM1,DA1 | 4930.8 | 0 | 0 | 0 | 0 | 0 | 1820.4 | 0 | 0 | 0 | 0 | 1778.4 | 0 | 0 | 0 | 1332 | 0 | 0
SA1,PM1,UI1 | 4301.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1778.4 | 0 | 0 | 0 | 1332 | 1191.04 | 0
SA1,UI1 | 2523.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1332 | 1191.04 | 0
SA1,UI1,PA2,ST1 | 5162.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1307.04 | 0 | 0 | 0 | 1332 | 0 | 1332 | 1191.04 | 0
ST1 | 1332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1332 | 0 | 0 | 0 | 0
ST1,BA1,DA1,SA1 | 5719.6 | 1235.2 | 0 | 0 | 0 | 0 | 1820.4 | 0 | 0 | 0 | 0 | 0 | 0 | 1332 | 0 | 1332 | 0 | 0
ST1,DBA1 | 2925.52 | 1235.2 | 0 | 0 | 0 | 358.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1332 | 0 | 0 | 0 | 0
ST1,PM1 | 3110.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1778.4 | 0 | 1332 | 0 | 0 | 0 | 0
ST1,PM1,DBA1,DA1,PA1 | 7831.36 | 1235.2 | 0 | 0 | 0 | 358.32 | 1820.4 | 0 | 1307.04 | 0 | 0 | 1778.4 | 0 | 1332 | 0 | 0 | 0 | 0
ST1,PM1,DBA1,DA1,PA1,SA1 | 9163.36 | 1235.2 | 0 | 0 | 0 | 358.32 | 1820.4 | 0 | 1307.04 | 0 | 0 | 1778.4 | 0 | 1332 | 0 | 1332 | 0 | 0
ST1,PM1,STE1 | 4442.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1778.4 | 1332 | 1332 | 0 | 0 | 0 | 0
STE1 | 1332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1332 | 0 | 0 | 0 | 0 | 0
STE1,PM1 | 3110.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1778.4 | 1332 | 0 | 0 | 0 | 0 | 0
STE1,ST1 | 2664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1332 | 1332 | 0 | 0 | 0 | 0
UI1 | 1191.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1191.04 | 0
UI1,PA1 | 2498.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1307.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1191.04 | 0
UI1,PA2 | 2498.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1307.04 | 0 | 0 | 0 | 0 | 0 | 0 | 1191.04 | 0
UI1,PM1 | 2969.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1778.4 | 0 | 0 | 0 | 0 | 1191.04 | 0
UI1,PM1,SA1,PA2 | 5608.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1307.04 | 0 | 1778.4 | 0 | 0 | 0 | 1332 | 1191.04 | 0
UI1,SA1,PA2 | 3830.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1307.04 | 0 | 0 | 0 | 0 | 0 | 1332 | 1191.04 | 0
UI1,STE1 | 2523.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1332 | 0 | 0 | 0 | 1191.04 | 0